Tentative Timeline and Activities of Proposal

Opening: 15 May 2025

Deadline(s): 16 Sep 2025

| What | Who | When |
| --- | --- | --- |
| Background document, including basic information about the call, the proposal, preliminary WP structure, key research themese & objectives and RQs, proposed partners, available resources, timeline, etc. | EUI & UM | End of September 2024 |
| Workshop with core partners on Excellence and Impact sections (Parts B.1 and B.2) of the proposal, on contents of individual WPs, defining and designating partners’ input on specific themes covered in the Excellence and Impact Sections | Core partners | October 2024 |
| Partners send their input to project leads, including first drafts of WP concepts | WP leads | November 2024 |
| First draft section B.1 Excellence | EUI & UM | January 2024 |
| Partners comment on B.1 Excellence draft | All partners | February 2025 |
| First draft/ concept section B.2 Impact | EUI & UM | February 2025 |
| Partners comment on section B.2 Impact | All partners | March 2025 |
| First complete draft of B.1 Excellence and B.2 Impact |  | April 2025 |
| Workshop with all partners for feedback on draft Excellence and Impact sections | All partners | April 2025 |
| Budget negotiations and optaining background information on relevant expertise from partners (for section B.3) | EUI & UM with all partners | April 2025 |
| First draft of part A (WP descriptions, deliverables, milestones, risks, etc) | EUI & UM | May 2025 |
| Draft section B.3 (Quality and Efficiency of the Implementation) | EUI & UM | June 2025 |
| Draft section B.4 (Ethics self-assessment) | EUI & UM | June 2025 |
| First complete draft of PARTS A and B | EUI & UM | End of June 2025 |
| Feedback from partners on entire proposal (PARTS A and B) | All partners, via email | August 2025 |
| Finalisation of proposal & submission | EUI & UM | August & first week of September 2025 |