Work package number 2 (Karina Shyrokykh (SU) and Honorata Mazepus (UvA) )

Work package title Public Opinion Survey

Objectives

O2.1 Generate theoretical expectations on the predictors of public support for enlargement Theory development will be conducted in close collaboration with WP1. The theoretical framework will address how citizens' attitudes about past enlargement affect their opinion on future enlargement, as such, and in the case of individual countries. O2.2 Collect data in several select EU member states and neighbouring countries Collect individual-level data (a representative sample of the surveyed counties’ populations) using survey and survey experiment methodology. The data collection process will be conducted by employing independent research organisations specialising in opinion polls. The collected data will inform the analysis conducted in WP2. O2.3 Test theoretical expectations generating scholarly insights and policy recommendations Using survey and survey experiment data collected (T2.2, T2.3), we will test the theoretical assumptions developed in WP2 (T2.1). We will perform data analysis using the statistical software Stata or R. The results of the test for our hypotheses will be reported in an academic article (D2.2) and a policy brief (D2.3). Also, the test of the hypotheses will inform WPs 4-8 about the effectiveness of various communication strategies.

T2.1 Systematic literature review, ensuring that survey questions address key research areas and generate novel theoretical expectations (lead: SU, partners: all; M1-6) T2.2 Conduct a pilot survey with a small sample of respondents to refine questions and identify potential issues (lead: UvA, partner: all; M6- M10) T2.3 Administer online surveys using sociological companies in multiple languages (lead: SU, partner: all; M10- M16) T2.4 Perform data cleaning using statistical software (e.g., Stata, R) to prepare for analysis (lead: SU, partner: all; M16- M18) T2.5 Using the data, conduct statistical analysis identifying statistically significant associations between individuals’ beliefs and their support to enlargement and identifying how adoption of various communicative strategies affects individuals’ support to enlargement (lead: SU, partner: all; M18- M32). T2.6 Based on the collected data and statistical analysis, generate policy-relevant recommendations for practitioners (lead: UvA, partner: all; M32- M36).

D2.1 Survey and survey experiment data in original languages in select EU member states and neighbouring countries (lead: SU, partner: all; M6- M18) D2.2 Building on the collected survey and survey experiment data, write an academic article on the drivers and obstacles of support for enlargement and on the effects of (mis-)information about enlargement on people's support for future EU enlargement (lead: UvA, partner: all; M18- M32). D2.3 Policy brief for practitioners (lead: UvA, partner: all; M32- M36).