WP5: Economic Dimensions of Enlargement

| Field | Description |
| --- | --- |
| Lead Beneficiary | SWPS |
| Co-lead | CEU DI |
| Start Month | 7 |
| End Month | 32 |

| Objective | Description |
| --- | --- |
| O5.1 | Conduct a comprehensive analysis and problematising of the economic costs and benefits of enlargement for the EU, its member states, and candidate countries. Develop tailored recommendations and narratives for effectively communicating these findings in different national contexts. |
| O5.2 | Applying thematic political economic lessons from previous EU enlargements, what does it mean in terms of the underlying political economy and identify similarities and differences with today’s candidate countries. |
| O5.3 | Assess the long-term economic impacts of EU enlargement and post-accession developments, and their relationship with political attitudes and behaviors across member states, with focused analysis on Hungary and Poland. This includes comparing absolute and relative socio-economic changes (national/EU averages), their effects on political divides, and the influence of subjective socio-economic evaluations and political trust using survey data. This includes exploring patterns of citizen inclusion/exclusion in the accession process, particularly in Ukraine. |
| O5.4 | Examine variation in the governance of using EU funds, with special attention to differences within and between member states and candidate countries at the level of subnational regional development. |
| O5.5 | Synthesize findings to provide adaptive, flexible policy recommendations for future enlargement, ensuring responsiveness to regional, national, and EU-level economic challenges and opportunities, and engage stakeholders (FUSE Civil Society Network and Expert Hub) throughout the lifetime of the WP to validate its methodology, findings and actionable policy recommendations. |

| Task | Details |
| --- | --- |
| Task 5.1: | - Systematic literature review including a review of previous Horizon project findings, with a focus on the limitations on the static quantitative assessments of the economic costs and benefits of enlargement for the EU, member states, and candidate countries. - Systematic literature review - including a review of previous Horizon project findings - of enlargement rounds, focusing on economic terms and conditions of accession treaties (e.g., transition periods, funding arrangements) (lead: CEU DI, partner: SWPS; M7-18). |
| Task 5.2: | - Critical literature review - including a review of previous Horizon project findings, systematic comparison of the key elements of the integration strategies during the Southern enlargement, the previous wave of Eastern enlargement and the recent wave (lead: CEU DI, partner: SWPS; M7-18) |
| Task 5.3: | - Design a longitudinal and comparative analysis methodology to capture citizens’ perceptions of the enlargement process in socio-economic developments in post-accession periods using absolute and relative indicators (growth, decline, stagnation - Systematic data research and data collection to analyze long-term post-accession socio-economic developments and their relationship to political attitudes and behaviors, with a focus on Hungary and Poland. Compare absolute and relative socio-economic changes (national/EU averages) and their impact on political divides and attitudes toward EU integration (lead: SWPS, partner: CEU DI; M13-24). |
| Task 5.4: | - Exploring secondary materials about regional and subnational variations in the governance of EU funding, with particular attention to Hungary and Poland. - Explore patterns of citizen inclusion/exclusion in the EU accession process based on fieldwork (case studies) in two Ukraine regions (lead: CEU DI, partner: SWPS, including ESS and collaboration with WP2, Expert hub; M13-24) |
| Task 5.5: | - Synthesize findings into actionable, adaptive policy recommendations for future enlargement, responsive to regional and national governance differences. (lead: SWPS, partner: CEU DI, Expert hub, TEPSA; M7-24) |

| Deliverable | Description |
| --- | --- |
| D5.1 | Policy report on the ambiguity of measuring economic costs and benefits of enlargement without considering the way enlargement governance can shape costs and benefits, formulation of recommendations for tailored communication strategies (narratives) on enlargement governance that can provides mutually beneficial outcomes for EU member states and accession countries. (lead: CEU DI, partner: SWPS, M25-32) |
| D5.2 | Policy report on the patterns of exclusion and inclusion of diverse stakeholders in Ukraine. Regions with comparison to EU strategies during the previous wave of Eastern enlargement, including actionable policy recommendations. (lead: SWPS, partner: CEU DI, M25-32) |
| D5.3 | Research report on a longitudinal and comparative analysis of citizens’ perceptions of the enlargement process in socio-economic developments in post-accession periods using absolute and relative indicators (growth, decline, stagnation) with a focus on Hungary, Poland, and Ukraine, including actionable policy recommendations. (lead: SWPS, partner:, CEU DI M25-32) |