Work package WP5 – Economic Dimensions of Enlargement

Work Package Number WP1 Lead Beneficiary 1. SPWS 2.CEU DI

Work Package Name Economic Dimensions of Enlargement

Start Month 13 End Month 36

Objectives

Lead: SPWS/CEU DI Objectives O5.1 Assess the long-term relationship between post-accession socio-economic developments and political attitudes and behaviors across EU member states, with a focus on Hungary and Poland. O5.2 Compare absolute and relative socio-economic changes, particularly in relation to national and EU averages, and examine their impact on political divides and attitudes toward EU integration. O5.3 Understand regional variation in the ability to absorb and utilize EU funding, with special attention to subnational differences and political economy geography. O5.4 Explore the patterns of citizen inclusion/exclusion in the EU accession process in two selected regions of Western Ukraine. O5.5 Investigate subjective socio-economic evaluations and their influence on political attitudes through survey integration (WP2 collaboration). O5.6 Analyze political trust, satisfaction with governance, and social trust across different socio-demographic groups using existing European Survey Data (ESS).

Tasks T5.1 Design a longitudinal and comparative analysis methodology to analyse citizens’ perceptions of the enlargement process in socio-economic developments in post-accession periods using absolute and relative indicators (growth, decline, stagnation). Utilize European Social Survey (ESS) data to study attitudes toward political trust, governance satisfaction, and social trust. Disaggregate findings by age, gender, religiosity, education, income sources, and occupational class. T5.2 Use panel studies and longitudinal datasets for regional-level analysis. Aggregate and harmonize data at NUTS2/NUTS3 levels for robust regional comparison T5.3 Apply a political economy geography framework to trace subnational trajectories in Hungary and Poland. T5.4 Design and insert a short block of questions into the WP2 survey on retrospective and prospective evaluations of personal, local, and national socio-economic conditions. Analyze how these subjective evaluations correlate with political attitudes and behavior. T5.4 Conduct fieldwork in two Western Ukrainian regions to identify patterns of citizen participation or exclusion in accession-related governance. Identify institutional, political, and civil society actors shaping these inclusion/exclusion patterns.

Deliverables D5.1 Collection of framing papers and research reports in preparation of journal articles (lead: partner: SPWS; M13-24). D5.2 Comparative analysis report on post-accession socio-economic and political developments in Hungary, Poland, and selected EU regions. Policy brief on regional absorption capacities for EU funding and implications for cohesion policy (lead: partner: SPWS; M13-24). D5.3 Fieldwork summary report from Western Ukraine on citizen engagement in the accession process (lead: partner: CEU DI; M19-36). D5.3 Integrated dataset and metadata combining ESS, national, and regional sources, ready for secondary use (lead: partner: SPWS; M24-36).