WP2: Identifying the challenges to liberal democracy M2-6 (Lead: SWPS)

Activities performed The SWPS team submitted two deliverables in the 5-months span of WP2: i.e., D2.1 Literature review: Illiberalism, Authoritarianism and Populism (in M5) and D2.2 Guidelines for empirical data collection (in M6). In both instances, several online and in-person meetings were held both at the SWPS team level (bi-weekly meetings), with the CEU team and with other partners from the Consortium (Jan 18, Jan 31, Feb 8, Feb 13, Feb 21, Feb 24, Feb 28, Mar 10, Mar 21). In case of D2.1, after an initial period of in-depth review of existing literature (with all involved partners suggesting their reading list on top of the literature gathered by the SWPS team), several drafts were compiled with important input from the CEU and other consortium members. These drafts were presented and discussed among consortium members during several online meetings. The most important one was the The AUTHLIB consortium first virtual workshop on February 24, 2023 during which we discussed on three key challenges identified by the team—illiberalism, authoritarianism, and populism—and sought to delimit these concepts and to explore the relationship and potential sequencing among them. The workshop synthesized inputs from the consortium members before the finalization of the literature review that lays the conceptual groundwork for the AUTHLIB project and paves the way for the operationalization of its key variables ahead of the start of a series of empirical work packages in April 2023. These meetings allowed for fine-tuning the final version of the deliverable, in which the definitions of the key concepts were put forward and solid theoretical and analytical frameworks for the following WPs was developed. The key findings of D2.1 were gathered in an AUTHLIB blog entry “What Lies Behind the Labels? Analyzing Illiberalism, Populism, and Authoritarianism” to reach a broader audience. Regarding D2.2, the following issues were addressed to offer guidelines for the empirical work of the subsequent WPs. First, research questions were specified and – were possible – structured hypotheses put forward. Second, the levels and units of analysis were identified. Third, methods and existing data sources were outlined. Fourth, central issues and dimensions were described. All of these in close collaboration with the CEU team and with input from all consortium members. Particularly the hybrid internal workshop held on March 29, 2023 on-site at the University of Vienna and online was relevant for advancing the discussion and laying out the general methodological approach of the project. The final draft was elaborated hand-in-hand with the CEU team.

WP3: Ideological configurations M7-25 (Lead: Sciences Po)

Activities performed [Piotr] Wpisalem tutaj nieduzo godzin do rozliczenia – ale nie za bardzo wiem, co wpisac. [Ben] Ja również mam ten problem. Jeśli dobrze pamiętam, godziny, które tu podałem, odnoszą się wyłącznie do spotkań.

WP4: Survey-based data-collection and experiments on public attitudes M7-25 (Lead: SWPS)

Activities performed The key axes around which several activities were carried out in WP4 until now are the design of the survey questionnaire and of the survey-embedded conjoint experiment. Regarding the former, the first task performed was the compilation of existing studies, measures and indicators relevant for the AUTHLIB survey. Data from such public opinion survey datasets as European Social Survey, Comparative Study of Electoral Systems, World Values Survey (and European Values Survey), International Social Survey Programme, together with expert survey data such as V-Dem (Varieties of Democracy) and Chapel Hill Expert Survey were thoroughly reviewed by the SWPS team. A compilation of relevant survey questions was then gathered and presented to Consortium partners. Discussions around drafting the survey questionnaire have taken place in several rounds. The first collection of relevant items was presented at the in-person project meeting at the University of Vienna on 29-30 March, 2023, where partners agreed on which elements of previous surveys may be worth incorporating to ensure comparability, and where previous items were not fine-tuned enough to measure our core concepts, justifying the development of original items. After a careful selection of questions and compilation of new ones, a first draft of the questionnaire as well as the options for polling companies to administer the survey were further discussed at the in-person meeting in Prague during the ECPR General Conference (4-8 September 2023). Subsequently, in close collaboration especially with Sciences Po, but also with other partners, several batteries and indicators from the ESS and WVS were analyzed using such statistical methods a Principal Factor Analysis and pairwise correlations regarding their consistency and relevance for the project. In parallel, SWPS team is preparing the tender to choose the research agency that will realize the fieldwork of the AUTHLIB survey research in our seven countries. Regarding the former, the conjoint experiment that will be an integral part of the survey was also discussed in several meetings. The SWPS team reviewed existing studies in this regard and is working in close collaboration with the University of Vienna and Sciences Po (and other partners) in designing the experiment. Issues such as statistical power, the optimal number of iterations per participant, number of attributes and their levels were discussed and the idea of varying levels of populism/illiberalism/ authoritarianism of a candidate in terms of policy implementation gained ground. Next steps include fine-tuning the specific phrasing, inclusion of additional candidate characteristics, etc.

WP5: Rhetorical and emotional appeals M7-25 (Lead: UOXF)

Activities performed

WP6: Illiberalism in power M7-15 (Lead: CEU)

Activities performed The SWPS participated in several ways in WP6. First, we assisted in data gathering of discourses of relevant figures of illiberalism in power in Poland. Second, the SWPS team has also aided CEU in translating and proof-reading them. Third, we reviewed extant literature on illiberal cultural policies, and described and analyzed such policies implemented by the Law and Justice government in Poland since 2015. As required by WP6 lead, ideological underpinnings, institutional changes and strategies of influence were assessed, paying additional attention to the financial aspects of implementation of these policies. Considerable parts of the SWPS input were directly introduced to the Report on ‘Illiberalism in Power: Educational and Cultural Policies’ drafted by the CEU team. Fourth, a paper proposal on ‘Illiberal cultural policies in Central and Eastern Europe: A Comparative Review’ has been submitted and accepted for presentation at the CES Conference in Lyon in June 2024. Fifth, as part of the work conducted within this work package, Ben Stanley produced four chapters of a co-authored monograph (under contract at Stanford University Press, to be published in 2025) on the nature and consequences of the illiberal-populist Law and Justice government’s term in office from 2015 to 2023. This monograph will provide one of the first book-length English-language analyses of the sustained assault on liberal-democratic institutions, values and norms in Poland, and will lead to further work on the aftermath of illiberalism in power, looking at how the consequences of illiberalism are dealt with by parties committed to liberal democracy.

WP7: International cooperation and diffusion M7-21 (Lead: SNS)

Activities performed The lead organization (SNS) asked SWPS to assist in identifying key far-right and illiberal organizations, media outlets, and social media pages in Poland to facilitate its protest event analysis via identifying relevant actors. Actors were collected and revised by the SWPS team based on a template that rendered actors into several different categories (political parties, media, cultural institutions etc.) Additionally, an entry for the AUTHLIB blog on ‘How the War in Ukraine Has Eroded the Links between Putin and the European Far Right’, summarizing the findings of a paper from West European Politics, was published. It appeared on the EUROPP – European Politics and Policy blog run by the London School of Economics and Political Science as well.

WP8: Historical embedding M13-28 (Lead: CEU)

Activities performed Ben Stanley co-authored an article with Zsolt Enyedi of CEU on the intellectual sources of challenges to the liberal consensus in Hungary and Poland, and the consequences of these ideas for the exercise of power in both countries. This article has been submitted to a special issue of a journal and is currently under review.

WP12: Delivering the results – impact and outreach M1-36 (Lead: TF)

Activities performed

WP13: Ethics requirements M1-36 (Lead: CEU)

Activities performed

Actual or potential problems

Explain the reasons for deviations from Annex 1, the reasons for failing to achieve critical objectives and/or not being on schedule and explain the impact on other tasks as well as on available resources and planning.

- Outline and provide the necessary explanation of any difficulties/problems (internal or external) you faced during project implementation over the reporting period.

- How did you manage to address / solve those problems (if you have managed to do so)? What were the corrective actions you took and/or plan to take?

- What was the outcome of your corrective action(s)?

Changes in the project team

Outline changes (if any) in:

- the legal status of your organisation; and

- the project team from your organisation (i.e. those people involved in project activities)