WP12 – notes after Utrecht network meeting

Substantive matters

The work package description and milestones meet with Femke and Ton's approval, but we need to add some information about questions other work packages would like to put on the survey. As some of the participants were more concrete in their answers to this question than others, it would probably be best if I simply give more detail about the new questions we are going to be proposing (touching on e.g. sovereignty and the rule of law) and link them in the WP12 text to specific work packages. At this stage, we simply need to show that we are coordinating our thinking about the survey with the substantive research agendas of specific WPs.

Femke and Ton raised the problem with including peer-reviewed articles and monographs as deliverables. Since deliverables consist in hard deadlines for the production of concrete outputs, publications which depend on external decisions (journal editors, publishers) cannot be included as a deliverable. After discussion, it was agreed that Femke and Ton would find out whether submission, rather than publication, could be considered as a deliverable.  As regards outputs from the project overall, there will not be a co-authored monograph edited centrally by the project leaders, but individual work packages are free to develop their own ideas for this, whether individually or in tandem with other WPs.

There is a general consensus that the 12 countries we have selected for the survey are appropriate to the broader needs of the project. Concerns were raised about two countries, Greece and the UK. Pascal suggested including Greece, and this is something we need to make a decision on. It was noted that the UK might be a difficult case to include in light of Brexit, and we need to clarify whether the Commission has any particular position on this.

Participants were generally receptive to our explanations for why we have selected those countries, but it was felt that the division between net contributors and net beneficiaries was problematic, as this may change over the lifespan of the project due to Brexit. Instead, it was suggested that we replace this with a distinction between countries that have experienced a rule of law crisis, countries which are vulnerable to one, and countries which are highly unlikely to experience one. In practical terms this does not have any implications for our country choices, as we already have a good spread of countries on that criterion.

Femke and Ton noted that some explicit reference needs to be made in the work package description to measuring responses to narratives about sovereignty, the rule of law etc. Apparently this was present in the draft for the first round of the application but has been removed from subsequent drafts.

The survey

The issues with the survey boil down to three choices: (a) mode; (b) number of respondents; (c) number of countries.

- Mode: the choice is between face to face or online; there is a consensus that telephone polling will not be adequate to our needs. Face to face methods will be better from the perspective of obtaining a representative sample and conducting some elements of the analysis that require the use of scenarios/vignettes, but will be more expensive. Online methods will be cheaper, but are likely to result in a less representative sample. The question here is whether there are methods of weighting that could potentially be used to compensate for the inadequacies of an online sample.

- Number of respondents: the minimum we need is 1000, but there is a preference for 1500 if this can be afforded.

- Number of countries: having 12 countries seemed to us to be the optimal choice, but this may need to be varied depending on the costs implied by our choices of mode and number of respondents.

Pascal will prepare estimates for different combinations of mode and number of respondents. On this basis, we will be able to discuss with Femke and Ton which of these options gives us the most desirable tradeoff of country coverage, representativeness, and cost.

While work package 4 will have a survey element, it must be kept separate in execution from the main survey, as there are experimental elements that require careful sequencing. It would be a good idea to explain that WPs 4 and 12 will liaise to ensure that there is no unnecessary repetition of questions across the two surveys.

Organisational issues

The main issue here is the budget, which, according to Utrecht's research officer, needs to give greater detail about participant costs. This needs to be dealt with directly, by contacting Michael Robinson at m.g.robinson@uu.nl.

I queried the situation with Femke regarding the budgeting of funds for travel, and she clarified that costs for attending consortium-organised conferences and workshops will be disbursed centrally by Utrecht, but that work packages will need to budget separately for travel costs that are incurred as a result of activities that only involve that work package. So, for example, if Radek and I travel to consortium meetings, or if Warsaw hosts one of the consortium meetings, the costs of travel (or, in the second case, hosting) will be covered by Utrecht, but if Radek or I travel to one of the participant countries to discuss issues relating to the survey, then such costs must be budgeted for by WP 12.

Ton and Femke mentioned the need to provide short bios for the project - two or three lines, with affiliation and major publications.