## Calendar
|  |  | 2019-09-01 | [5 empty] | 2020-03-01 | [5 empty] | 2020-09-01 | [5 empty] | 2021-03-01 | [5 empty] | 2021-09-01 | [5 empty] | 2022-03-01 | [6 empty] | 2022-10-01
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
WP1
task 1.1 Conceptualisation and critical reflection
task 1.2 Mapping criteria
task 1.3 Drafting reports
Deliverables | [7 empty] | D1.1 |  |  |  |  | D1.2
WP2
task 2.1 Sample selection
task 2.2 Interview guidelines definition, preparation and fieldwork
task 2.3 Analysis
task 2.4. Draft report
Deliverables | [9 empty] | D2.1 | [5 empty] | D2.2
WP3
task 3.1 Case study of Eurosceptic campaigns
task 3.2 Mapping of EU responses to populism
task 3.2 Drafting report
Deliverables | [16 empty] | D3.1
WP4
task 4.1 Codebook preparation
task 4.2 Sampling and pretest
task 4.3 Coding
task 4.4 Analysis
task 4.5 Drafting report
Deliverables | [18 empty] | D4.1 | [6 empty] | D4.2
WP5
task 5.1 Questionnaire preparation
task 5.2 Sampling pretest and data retrieval
task 5.3 Analysis
task 5.4 Drafting report
Deliverables | [23 empty] | D5.1 |  |  | D5.2
WP6
task 6.1 Experimental protocols preparation (to be updated until end of wp)
task 6.2 Data collection
task 6.3 Analysis
task 6.4 Drafting reports
Deliverables | [29 empty] | D6.1 |  |  |  |  | D6.2 | D6.3
WP7 Dissemination
task 7.1 Dissemination and explotation plan
task 7.2 Comic
task 7.3 Summer school and camp
task 7.4 Claims data preparation
task 7.5 Survey data preparation
task 7.6 Teaching unit
task 7.7 Café workshops
task 7.8. Edited book proposal
task 7.9 Article elaboration, presentation in conferences and submission
Deliverables |  |  |  | D7.1 | [10 empty] | D7.2 | [10 empty] | D7.3 |  | D7.4 | D7.5 |  |  |  | D7.6 |  |  | D7.7 |  | D7.8 |  | D7.9, D7.10, D7.11, D7.12, D7.13
WP8 Communication and policy outreach
task 8.1 Communication plan
task 8.2 Web and blog
task 8.3 Social media
task 8.4 Op-eds
task 8.5 Review of results for policy briefs and prescriptive report
task 8.6 Policy and prescriptive reports drafting
task 8.7 Video production
task 8.8 Final conference
Deliverables |  |  |  |  | D8.1 | D8.2, D8.3 | [11 empty] | D8.4, D8.5 | [11 empty] | D8.4, D8.6 | [5 empty] | D8.4, D8.7 |  | D8.8
WP9
Task 9.1 Data management plan
task 9.2 Scientific coordination
task 9.3 Scientific reporting
task 9.4 Financial reporting
task 9.5 Quality management
Deliverables |  |  |  | D9.1 | [16 empty] | D9.1, D9.2, D9.3 | [18 empty] | D9.1, D9.2, D9.3
Milestones |  |  | M1 | [5 empty] | M2 | [5 empty] | M3 | [5 empty] | M4 | [5 empty] | M5 | [5 empty] | M6 | [6 empty] | M7
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40

## PM
Personnel effort
|  | PI | Coordination and academic dissemination wp leaders in yellow | [8 empty] | WP execution | [8 empty] | Total
|  |  | wp1 | wp2 | wp3 | wp4 | wp5 | wp6 | wp7 | wp8 | wp9 | wp1 | wp2 | wp3 | wp4 | wp5 | wp6 | wp7 | wp8 | wp9 | ip | coord | exec | Total
1 | UAB | 1.5 | 1 | 1 | 1 | 1 | 1 | 4 | 8 | 9 | 18 | 0.5 | 6 | 0.5 | 7.5 | 1 | 2 | 4 | 1 | 1 | 1.5 | 44 | 23.5 | 69
2 | Unige | 1.5 |  |  |  | 4 |  |  | 3 | 1 |  | 0.5 | 6 |  | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 8 | 21 | 30.5
3 | Shefield | 1.5 |  |  |  |  | 4 |  | 3 | 1 |  | 0.5 | 6 | 0.5 | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 8 | 21.5 | 31
4 | Siegen | 1.5 |  | 4 |  |  |  |  | 3 | 1 |  | 0.5 | 6 |  | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 8 | 21 | 30.5
5 | Salento | 1.5 | 2 | [5 empty] | 1 | 1 |  | 3 | 6 |  | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 4 | 23.5 | 29
6 | Bergen | 1.5 | [5 empty] | 3 | 2 | 1 |  | 0.5 | 6 |  | 7.5 | 1 | 2 | 4 | 1 | 1 | 1.5 | 6 | 23 | 30.5
7 | Scuola Normale Superiore | 1.5 | 1 | 2 | 2 |  |  |  | 2 | 1 |  | 0.5 |  | 3 |  |  |  | 4 | 1 | 1 | 1.5 | 8 | 9.5 | 19
8 | Leuven | 1.5 | [5 empty] | 3 | 2 | 2 |  | 0.5 | 6 | 0.5 | 7.5 | 1 | 2 | 4 | 1 | 1 | 1.5 | 7 | 23.5 | 32
9 | Ekke, Athens | 1.5 | [5 empty] | 1 | 3 | 1 | 1 | 0.5 | 6 | 0.5 | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 6 | 21.5 | 29
10 | Charles | 1.5 |  |  | 1 |  |  |  | 2 | 1 | 1 | 0.5 | 6 | 0.5 | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 5 | 21.5 | 28
11 | Lille | 1.5 |  |  |  | 2 |  |  | 2 | 1 | 1 | 0.5 | 6 |  | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 6 | 21 | 28.5
12 | Warsaw | 1.5 | 1 | [5 empty] | 2 | 1 | 1 | 0.5 | 6 | 0.5 | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 5 | 21.5 | 28
13 | Sofia | 1.5 |  |  |  |  | 1 |  | 2 | 1 | 1 | 0.5 | 6 |  | 7.5 | 1 |  | 4 | 1 | 1 | 1.5 | 5 | 21 | 27.5
14 | Eureopan Alternatives | 1.5 | [6 empty] | 2 | 6 | 1 | [9 empty] | 1.5 | 9 | 0 | 10.5
| Total | 21 | 5 | 7 | 4 | 7 | 6 | 11 | 37 | 28 | 24 | 9 | 72 | 6 | 90 | 12 | 6 | 52 | 13 | 13 | 21 | 129 | 273 | 423
| Total pm effort by wp |  | concept | interviews | eu case | claims | survey | experim | diss | com | manag
|  |  | wp1 | wp2 | wp3 | wp4 | wp5 | wp6 | wp7 | wp8 | wp9 | Total
1 | UAB |  | 1.5 | 7 | 1.5 | 8.5 | 2 | 6 | 12 | 10 | 20.5 | 69
2 | Unige |  | 0.5 | 6 | 0 | 11.5 | 1 | 0 | 7 | 2 | 2.5 | 30.5
3 | Shefield |  | 0.5 | 6 | 0.5 | 7.5 | 5 | 0 | 7 | 2 | 2.5 | 31
4 | Siegen |  | 0.5 | 10 | 0 | 7.5 | 1 | 0 | 7 | 2 | 2.5 | 30.5
5 | Salento |  | 5 | 6 | 0 | 7.5 | 1 | 0 | 5 | 2 | 2.5 | 29
6 | Bergen |  | 0.5 | 6 | 0 | 7.5 | 1 | 5 | 6 | 2 | 2.5 | 30.5
7 | Scuola Normale Superiore |  | 1.5 | 2 | 5 | 0 | 0 | 0 | 6 | 2 | 2.5 | 19
8 | Leuven |  | 0.5 | 6 | 0.5 | 7.5 | 1 | 5 | 6 | 3 | 2.5 | 32
9 | Ekke, Athens |  | 0.5 | 6 | 0.5 | 7.5 | 1 | 1 | 7 | 2 | 3.5 | 29
10 | Charles |  | 0.5 | 6 | 1.5 | 7.5 | 1 | 0 | 6 | 2 | 3.5 | 28
11 | Lille |  | 0.5 | 6 | 0 | 9.5 | 1 | 0 | 6 | 2 | 3.5 | 28.5
12 | Warsaw |  | 1.5 | 6 | 0.5 | 7.5 | 1 | 0 | 6 | 2 | 3.5 | 28
13 | Sofia |  | 0.5 | 6 | 0 | 7.5 | 2 | 0 | 6 | 2 | 3.5 | 27.5
14 | Eureopan Alternatives |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 2.5 | 10.5
| Total |  | 14 | 79 | 10 | 97 | 18 | 17 | 89 | 41 | 58 | 423
|  |  | 3.31% | 18.68% | 2.364% | 22.93% | 4.255% | 4.019% | 21.04% | 9.693% | 13.71%

## 3.1a 3.1c
Work package No | Work Package Title | Lead Participant No | Lead Participant Short Name | Person-Months | Start Month | End month
Total person- months
Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date
(in months)
| WPn | WPn+1 | WPn+2 | Total Person-
Months per Participant
Participant Number/Short Name
ParticipantNumber/
Short Name
Participant Number/
Short Name
Total Person Months
Participant Number/Short Name | Cost (€) | Justification
Travel
Equipment
Other goods and services
Total