## Gantt
|  |  | 2019-09-01 | [5 empty] | 2020-03-01 | [5 empty] | 2020-09-01 | [5 empty] | 2021-03-01 | [5 empty] | 2021-09-01 | [5 empty] | 2022-03-01 | [6 empty] | 2022-10-01
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | [7 empty] | Month
WP1 | [41 empty] | M1 | Kick off: conceptual issues and interview guidelines |  |  |  |  | 3
task 1.1 Conceptualisation and critical reflection | [41 empty] | M2 | Interview's initial results and first discussion of codebook draft for WP4 |  |  |  |  | 9
task 1.2 Mapping criteria | [41 empty] | M3 | Final codebook wp4 and first discussion of questionnaire contents for WP5 |  |  |  |  | 15
task 1.3 Drafting reports | [41 empty] | M4 | Final questionnaire for WP5 and first discussion of experimental designs WP6 |  |  |  |  | 21
Deliverables | [7 empty] | D1.1 |  |  |  |  | D1.2 | [28 empty] | M5 | Discussion of WP6 and dissemination |  |  |  |  | 27
WP2 | [41 empty] | M6 | International conference |  |  |  |  | 33
task 2.1 Preparation | [41 empty] | M7 | Final conference |  |  |  |  | 40
task 2.2 Fieldwork
task 2.3 Analysis
task 2.4. Draft report | [41 empty] | Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date
Deliverables | [9 empty] | D2.1 | [5 empty] | D2.2 | [24 empty] | 1 | D1.1 | What is populism? A conceptual report | 1 | UNISALENTO | R | PU | 8
WP3 | [40 empty] | 2 | D1.2 | Mapping populism in Europe | 1 | UNISALENTO | R | PU | 13
task 3.1 Case study of Eurosceptic campaigns | [40 empty] | 3 | D2.1 | Interview guidelines | 2 | UNISIEGEN | R | PU | 10
task 3.2 Mapping of EU responses to populism | [40 empty] | 4 | D2.2 | Integrated report on populism and the political establishment | 2 | UNISIEGEN | R | PU | 16
task 3.2 Drafting report | [40 empty] | 5 | D3.1 | Integrated report on discourses, organisations and forms of populist eurosceptic actors | 3 | SNS | R | PU | 17
Deliverables | [16 empty] | D3.1 | [23 empty] | 6 | D4.1 | Codebook for political claims analysis | 4 | UNIGE | R | PU | 16
WP4 | [40 empty] | 7 | D4.2 | Integrated rerpot on populism in the public sphere | 4 | UNIGE | R | PU | 24
task 4.1 Codebook preparation | [40 empty] | 8 | D5.1 | Questionnaire for the analysis of populism among European citizens | 5 | USFD | R | PU | 22
task 4.2 Sampling and pretest | [40 empty] | 9 | D5.2 | Comparative report on populism among European societies | 5 | USFD | R | PU | 30
task 4.3 Coding | [40 empty] | 10 | D6.1 | Experimental protocols | 6 | UiB | R | PU | 28
task 4.4 Analysis | [40 empty] | 11 | D6.2 | Report on the consequences of types of populism | 6 | UiB | R | PU | 35
task 4.5 Drafting report | [40 empty] | 12 | D6.3 | Report on the consequences of populist and anti-populist discourses | 6 | KULEUVEN | R | PU | 36
Deliverables | [15 empty] | D4.1 | [7 empty] | D4.2 | [16 empty] | 13 | D7.1 | Dissemination and exploitation plan | 7 | UAB | R | CO | 4
WP5 | [40 empty] | 14 | D7.2 | Comic book | 7 | UAB | DEC | PU | 21
task 5.1 Questionnaire preparation | [40 empty] | 15 | D7.3 | Summer school program | 7 | SNS | DEC | PU | 24
task 5.2 Sampling, pretest and data retrieval | [40 empty] | 16 | D7.4 | Comparative dataset on populist and anti-populist discourses in the public domain | 7 | UNIGE | OTHER | CO | 28
task 5.3 Analysis | [40 empty] | 17 | D7.5 | Comparative individual-level survey dataset | 7 | USFD | OTHER | CO | 29
task 5.4 Drafting report | [40 empty] | 18 | D7.6 | Teaching unit and education materials | 7 | EKKE | DEC | PU | 33
Deliverables | [21 empty] | D5.1 | [7 empty] | D5.2 | [10 empty] | 19 | D7.7 | World café workshops programs | 7 | EA | DEC | PU | 36
WP6 | [40 empty] | 20 | D7.8 | Proposal for special issue or edited book | 7 | UAB | R | CO | 38
task 6.1 Experimental protocols preparation | [40 empty] | 21 | D7.9 | Paper submission to academic journal with results from WP2 | 7 | UNISIEGEN | R | PU | 40
task 6.2 Data collection | [40 empty] | 22 | D7.10 | Paper submission to academic journal with results from WP3 | 7 | SNS | R | PU | 40
task 6.3 Analysis | [40 empty] | 23 | D7.11 | Paper submission to academic journal with results from WP4 | 7 | UNIGE | R | PU | 40
task 6.4 Drafting reports | [40 empty] | 24 | D7.12 | Paper submission to academic journal with results from WP5 | 7 | USFD | R | PU | 40
Deliverables | [27 empty] | D6.1 | [6 empty] | D6.2 | D6.3 |  |  |  |  | 25 | D7.13 | Paper submission to academic journal with results from WP6 | 7 | UiB | R | PU | 40
WP7 Dissemination | [40 empty] | 26 | D8.1 | Communication and policy outreach plan | 8 | UAB | R | CO | 5
task 7.1 Dissemination and explotation plan | [40 empty] | 27 | D8.2 | Project website and blog | 8 | UAB | DEC | PU | 6
task 7.2 Comic | [40 empty] | 28 | D8.3 | Project’s social media accounts | 8 | UAB | DEC | PU | 6
task 7.3 Summer school | [40 empty] | 29 | D8.4 | Policy brief 1 based on WP2 and WP3 | 8 | EA | R | PU | 24
task 7.4 Claims data preparation | [40 empty] | 30 | D8.5 | Policy brief 2 based on WP2 and WP4 | 8 | EA | R | PU | 30
task 7.5 Survey data preparation | [40 empty] | 31 | D8.6 | Prescriptive report based on WP5 and WP6 | 8 | EA | R | PU | 36
task 7.6 Teaching unit | [40 empty] | 32 | D8.7 | Press releases and op-eds | 8 | UAB | DEC | PU | 24, 30, 36
task 7.7 Café workshops | [40 empty] | 33 | D8.8 | Video materials summarizing the most relevant findings of the project | 8 | EA | DEC | PU | 38
task 7.8. Edited book proposal | [40 empty] | 34 | D9.1 | Data management plan | 9 | UAB | R | CO | 4, 21, 40
task 7.9 Article elaboration, presentation in conferences and submission | [40 empty] | 35 | D9.2 | Scientific report | 9 | UAB | R | PU | 21, 40
Deliverables |  |  |  | D7.1 | [16 empty] | D7.2 |  |  | D7.3 |  |  |  | D7.4 | D7.5 |  |  |  | D7.6 |  |  | D7.7 |  | D7.8 |  | D7.9, D7.10, D7.11, D7.12, D7.13 | 36 | D9.3 | Financial report | 9 | UAB | R | PU | 21,40
WP8 Communication and policy outreach
task 8.1 Communication plan
task 8.2 Web and blog
task 8.3 Social media
task 8.5 Review of results for policy briefs and prescriptive report
task 8.6 Policy and prescriptive reports drafting
task 8.4 Op-eds
task 8.7 Video production
task 8.8 Final conference
Deliverables |  |  |  |  | D8.1 | D8.2, D8.3 | [16 empty] | D8.4, D8.7 | [6 empty] | D8.5, D8.7 | [5 empty] | D8.6, D8.7 |  | D8.8
WP9
Task 9.1 Data management plan
task 9.2 Scientific coordination
task 9.3 Scientific reporting
task 9.4 Financial reporting
task 9.5 Quality management
Deliverables |  |  |  | D9.1 | [16 empty] | D9.1, D9.2, D9.3 | [18 empty] | D9.1, D9.2, D9.3
Milestones |  |  | M1 | [5 empty] | M2 | [5 empty] | M3 | [5 empty] | M4 | [5 empty] | M5 | [5 empty] | M6 | [6 empty] | M7
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40

## 3.1a 3.1c
Work package No | Work Package Title | Lead Participant No | Lead Participant Short Name | Person-Months | Start Month | End month
Total person- months
Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date
(in months)
| WPn | WPn+1 | WPn+2 | Total Person-
Months per Participant
Participant Number/Short Name
ParticipantNumber/
Short Name
Participant Number/
Short Name
Total Person Months
Participant Number/Short Name | Cost (€) | Justification
Travel
Equipment
Other goods and services
Total