| Work package number | 3 |  | Lead Beneficiary |  |  | SWPS University of Social Sciences and Humanities, Warsaw |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Testing Micro-level Causes of Populism |  |  |  |  |  |  |
| Participant number |  |  |  |  |  |  |  |
| Short name of participant |  |  |  |  |  |  |  |
| Person months per participant: |  |  |  |  |  |  |  |
| Start month: 1 |  |  |  | End Month: 36 |  |  |  |
| Objectives: This work package has the following objectives: - to collect all significant survey data sets on populism currently available and created over the lifetime of the project; - to evaluate the relevance of these existing datasets to the overall aims of the current project; - if feasible, to create a merged dataset from the relevant individual-level variables and appropriate contextual-level data; - to design and carry out new state-of-the-art surveys using individual and contextual variables derived from the merged dataset, and integrating new theoretical and methodological insights into the measurement of populism (both those generated by the project itself and those found in the emerging literature on this topic); - to carry out analyses of the impact of contextual and individual-level factors on populist attitudes and preferences for populist candidates for office. |  |  |  |  |  |  |  |
| Description of work (where appropriate, broken down into tasks), lead partner and role of participants This work package will examine the interaction of contextual and individual-level factors in the activation of populist attitudes and the shaping of preferences for populist candidates for office. Recent years have seen the emergence of a variety of cross-national and single-country survey datasets measuring populist attitudes and their ideological and socio-demographic correlates. In our analysis of the micro-level causes of populism, we will primarily draw on these data, merging them into a master dataset and supplementing them with appropriate contextual variables. To achieve these goals, this work package will accomplish the following tasks: - With attention to the work undertaken by other work packages, in particular WPs 1, 2 and 4, we will collect and analyse all available survey datasets measuring populist attitudes and related phenomena. This first phase of the analysis will enable us to establish on what basis we can combine existing datasets (or, at least, a selection of them) into a single, merged data file that can be used for the comparative analysis of populist attitudes and their ideological and socio-demographic determinants. - On the basis of an exhaustive evaluation of the quality of the existing datasets we have collected in the first stage, we will design a ‘gold-standard’ survey for the analysis of the micro-level causes of populism, and administer this survey in several countries (to be selected in light of our evaluation of the quality of existing datasets and the broader needs of the project). - Subsequently, we will use both the existing and the new datasets to answer our research questions concerning the causes of varieties of populism across the contemporary world, and in in Europe in particular. This will involve explaining the distinct and interacting impacts of macro-contextual determinants and individual-level factors on the activation of populist attitudes and the determination of voter behaviour with respect to populist parties. - In collaboration with WP4 (which focuses on the consequences of populism) our team will measure and explore the links between the causes of populism and its varied manifestations on the one hand, and the varying consequences of populism on the other. - Finally, WP3 will contribute to policy recommendations concerning the possibilities and methods of mitigating populist attitudes, on the principle that knowledge of the causes of populism is vital to an understanding of how to combat the threats it poses. Among the existing comparative studies on populism to be used by this project are: - the Comparative Study of Electoral Systems (CSES) module 5, which will generate between 20 – 25 country datasets by the end of 2020, each of which will be available to the project; - the LIVEWHAT dataset, collected in 2015 in France, Germany, Greece, Italy, Poland, Spain, Sweden, Switzerland, and the United Kingdom; - the 2016 Multi-Country Socio-Political Survey, collected by a project funded by the Baltic Sea Foundation at Södertörn University, covering Bulgaria, Croatia, Czech Republic, Hungary, Poland, Romania, Slovakia and Slovenia (access is currently restricted, but there are realistic prospects of gaining complete access before the beginning of this project). We will also make use of a variety of single-country surveys mostly conducted under the auspices of the Team Populism network. Many members of the POPCON project have connections with this project, facilitating access to the data. Tasks of participants: the great majority of the work will be accomplished by the WP3 team based at SWPS, but it is expected that all Work Packages will contribute ideas and feedback to the furtherance of the substantive tasks of the project. In particular, we envisage the input of the participants of WP4 and WP5 (which focus on the consequences of populism) in the analysis of survey data, while participants of WP1 and WP2 will be consulted with respect to the conceptualisation of contextual factors. |  |  |  |  |  |  |  |
| Deliverables (brief description and month of delivery) - A short report summarising our investigation of the technical feasibility of a merged data set based on existing data sets (month 4). - A detailed report summarising the findings of our secondary analysis of existing datasets (month 18). - A publicly available dataset used for the secondary analysis above, combining relevant individual-level questions with contextual variables (month 30). - Budget permitting, a new dataset, based on our ‘gold standard’ for the analysis of the micro-causes of populism, that combines populism questions with those individual-level and contextual variables that are of most use in explaining populism, and updates our stock of data to the end date of the project (month 36). - Submission of two key articles to top-ranked journals: one which accompanies the release of the consolidated dataset, introducing our ‘gold standard’ approach to the analysis of the micro-level causes of populism, and one which sets out and tests hypotheses about the causes of populism, using the accumulated data (month 36). |  |  |  |  |  |  |  |