| Work package number | 3 |  |  | Start Date or Starting Event |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Political claims analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 13 | 14 | 15 |
| Short name of participant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Person/months per participant: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Objectives The aim of this workpackage is to study populist and anti-populist discourses in the public domain. This is a key aspect of the study of populism insofar as the latter can be conceptualized as a discourse that grows on an opportunity based on the crisis of representation fueled by cultural and economic threats, most recently epitomized by economic recession, migration crisis, and the erosion of national sovereignty due to globalization. We will examine the positions of collective actors with regard to issues that can are related to populism and more specifically populist discourse, such the moral distinction between the people and the elite, the idea that politics is about respecting popular sovereignty, conceptions of democracy, forms of political representation, political corruption, and so forth. We will cover both populist and anti-populist discourses. We expect populist discourses to have significant consequences on a number of political outcomes: appearance of anti-populist discourses, engagement and participation, democratic values, expectations and evaluations about the functioning of democracy, EU integration preferences and evaluations of the functioning and benefits derived from EU membership. Our main goal is to analyze how populist discourses are articulated, what are their consequences, and the challenges they introduce in European democracies, and how they can be offset. Analyzing populist discourses in the public domain, as seen in both printed and online media, is an important step towards this end. All kinds of actors (from the left as well as from the right) will be covered. This includes “typical” populist parties and movements, according to the definition adopted in the project, as well as all other actors (including state actors and policy-makers) who intervene in the public domain by saying or doing something on topics related to populism.

Description of work (where appropriate, broken down into tasks), lead partner and role of participants: Following the method of political claims analysis, which has already proven fruitful in previous research, we will study systematically the actors intervening in public debates, the issues they address, their policy positions, the frames they advance, and more generally the in which populist argument are presented and framed in the public domain. Our national representative samples will enable us to focus not only on atypical events (usually most visible in the media), but also include the everyday debate about populism and related issues. At the same time, our period of study will allow for assessing diachronic changes in terms of public reactions to these issues. The systematic data collection and analysis will be carried out in each country based on common guidelines. The information will be first summarized in national reports and then an integrated report (and dataset) will be elaborated allowing for cross-national comparative analyses. Participant X (UNIGE) coordinates WP2. This also includes preparing the codebook and writing the integrated report, which will be based on national reports provided by participants. All the participants will carry out the data collection and analysis on their own country for this workpackage. Task 3.1: Preparation of codebook for the political claim analysis This task consists in preparing the codebook for the political claims analysis. It will be made of two parts. The first part will include instructions concerning the definition, sampling, and coding of claims. The second part will include the variables and categories to be used in the coding. The main variables refer to the actors intervening in public debates, the issues they address, their policy positions, the frames they advance, and more generally the way in which populist argument are presented and framed in the public domain. Participant X (UNIGE) will be responsible for the preparation of the codebook. Task 3.2: Sampling and pretest Sampling will follow a two-step procedure. In the first step, we will select five national newspapers in each country (available online through sources as Lexis-nexis) and sample from them by relevant keyword searches for each country for the period 2007-2017 (or the latest data available). This period allows to connect populist discourse to the economic crisis that has struck Europe in the past ten years. From the set of articles thus generated, we will draw a representative sample of interventions in each country. The sample should be large enough to have a sufficient number of cases in the analytical categories to allow for quantitative analyses (tentative target: 1000 claims per country). The codebook will be pretested on a small sample of claims before starting the coding. Coders will be trained to the use of the codebook and intercoder reliability tests will be applied. The data from each country will be collected and merged into a comparative dataset. Task 3.3: Coding of political claims Coding will follow the method of political claims analysis. This method consists in standardizing the information on claims retrieved on media sources (in this case, newspapers) in numerical form by the use of categories at different levels of generality. A claim is a unit of strategic action in the public sphere. It consists of the expression of a political opinion by some form of physical or verbal action, regardless of the form this expression takes and regardless of the nature of the actor. Task 3.4: Analysis of political claims data The political claims data will be analyzed through traditional statistical methods (for example, cross-tabulations and regressions). It will be of two kinds. Firstly, descriptive analyses on key variables of interest such as actors, issues, positions, and frames will provide a picture of how populist discourse vary across countries as well as over time, which actors are more “populist” in discursive terms, which specific issues are more often emphasized in populist discourses, which specific “host” ideologies are associated with the “thin” ideology represented by populism, and so forth. Task 3.5: Drafting of integrated report on collective responses to crises in the public domain Participant X (UNIGE) will write the integrated report, summarizing the main findings of this workpackage. The report will consist consisting of a comparative assessment of populist and anti-populist discourses as they appear in the public domain.

Deliverables (brief description and month of delivery): D3.1: Codebook for the political claims analysis (month of delivery: ) Codebook for the political claims analysis including instructions concerning the definition, sampling, and coding of claims and the variables and categories to be used in the coding. D3.2: Integrated report on political claims analysis (month of delivery: ) Report, based on national reports provided by participants, summarizing the main findings of WP3, consisting of a comparative assessment of populist and anti-populist discourses as they appear in the public domain.