University of Sheffield (USFD) WP4 Survey analysis of individual attitudes and behaviours

Objectives

Building on the results from wp2 and wp3, the aim of this work-package is to study populist attitudes and correlates amongst citizens. To this end, the work-package will investigate by means of a population survey how populist attitudes are related to perceptions of the current crisis of legitimacy and responsibility affecting European democracies. This crisis is further compounded and exacerbated by the current economic crisis and rising inequality. In this juncture, xenophobic parties have used existing tensions within advanced democracies to scapegoat migrants, asylum seekers and other marginalised groups with the aim of garnering support within the pool of those groups that have been understood as ‘the losers of globalization’. On the other hand, social movements of various kinds have aimed to address the lack of democracy and socio-economic injustice of the current historical juncture, most recently by campaigning against austerity and public spending cuts which have disproportionately affected sectors of the population already at risk of deprivation. In this context, the current work-package investigates populist attitudes as well as the correlates of these attitudes amongst European citizens. We are particularly interested in examining social heterogeneity in attitudes and also the ways these link up with particular political behaviours such as party choice and protest activism. Firstly, we will investigate whether there is a consistent set of populist attitudes (Akkerman, Mudde, Zaslowe 2014; Rico, Guinjoan and Anduiza 2017) and second, we will turn to analysing how this relates to other types of values. Third, we will examine how this might link up with political participation more widely. More specifically, we are particularly interested in analysing the way in which populist attitudes relate to other political values such as economic left-right and social libertarian-authoritarian values and whether there are major differences in these patterns cross-nationally. Most importantly, we are interested in investigating whether young people which have come of age in the more recent crisis-ridden historical juncture marked by undermining legitimacy as well as rising inequality are more prone to espouse populist values than older generations that came of age in different contexts as well as if more marginalised social groups such as the unemployed, those in manual and more precarious occupations are more likely to hold populist attitudes and whether this translates into support for populist parties in terms of effective political action or whether it compounds pre-existing patterns of de-enfranchisement (Evans and Tilley 2017). Furthermore, the work-package aims to analyse how populist attitudes link to support for the European Union cross-nationally and to the extent that the crisis of legitimacy at the national level translates to patterns of trust and distrust for European institutions and various conceptions of further political and economic union.  As such, the work-package will provide a detailed analysis of which social groups agree with populist claims such as the idea of a major separation between ‘the people’ and ‘the elite’ (also known as ‘la casta’) and how citizens perceive and react to and perceive populist parties, and to what extent they agree with anti-immigrant, anti-elite, anti-EU and other such stances associated with these parties on the right. Through this detailed analysis, this workpackage will collect evidence to analyse how these values and attitudes are related to other kinds of individuals’ political attitudes and behaviours, their social relations and networks, lifestyle patterns and use of leisure time, their feelings of well-being and relative social status, etc. as well as collect classic socio-economic indicators such as gender, age, occupation, etc. in order to analyse whether there are key differences between different types of social groups (for example, the resource-rich and the resource-poor) in terms of both their populist attitudes and other types of political actions.

Do European citizens hold populist attitudes? If so, which groups cross-nationally do so the most? In which ways are these attitudes linked to the major problems which ordinary citizens see as undermining democratic politics and social justice today?  To what extent are populist values associated with other political values and how to what extent do they translate to political behaviours? To what extent do citizens support populist parties? Which groups cross-nationally are most likely to support them? Who turns out to vote for them? What types of sociodemographic profiles are linked to support for populist parties and how does this vary across European countries? Are young people coming of age in a context of crisis more likely to support populist parties than older generations that were socialised in a different historical juncture? Are more resource-poor groups more likely to hold populist attitudes? And do these translate into support for populist political actors or rather into further political disenfranchisement and abstention? How do all these patterns vary cross-nationally? Moreover, as noted, a particular focus of this workpackage will be to collect data that will enable us to evaluate citizens’ views about the role of the EU in relation to the current legitimation crisis and the emergence of populist challenger parties. Do European citizens feel that EU integration is progressing at the right speed with a solid balance of rights and obligations underlying a durable solidarity at the crossnational level? Where do they think are the most pressing problems that need immediate attention and solutions? How does Brexit and other challenges to integration and solidarity fit into this picture for citizens? Where do they see the future of a positive European governance? Do they think that EU reactions to current political and economic crises have been adequate? Do they see the EU as competent in its policy responses and offering enough choice for citizens across countries? What are the areas where citizens feel the EU could to more to assist the development of more human and fair policies for example with respect to migration? Are there important differences across social groups and countries on these and other important dimensions linked to populist claims and challenges? How do stances on all these EU issues link up to populist attitudes cross-nationally and amongst different groups?

Description of the work and role of partners

To tackle all the above questions we will conduct a population survey with N of 2000 in each of the countries included in the project. A specialized polling institute will be subcontracted to conduct the survey in each country through the CAWI method (Computer Assisted Web Interviewing) with online accessible questionnaires and data storage (using PHPSurveyor). Participant 4 (USFD) coordinates WP4. This also includes preparing the questionnaire with input from the other partners and writing the comparative report, which will consist of a publishable working paper examining key questions of this work-package from a comparative perspective. USFD also manages all contact with the survey company and provides scientific supervision for all aspects of the survey. All the beneficiaries will assist with questionnaire design and checking of translations for cross-national equivalence for the survey.

Task 4.1: Preparation of questionnaire for the population survey

This task consists in preparing the questionnaire for the population survey. The questionnaire for this part of the study will include questions measuring the material/economic dimension, the psychological/attitudinal dimension, and the behavioral dimension, as well as their personal background and individual characteristics, including their embeddedness in organizational networks. Particular emphasis will be put on making sense of the extent to which citizens agree with populist claims on the current economic and political crises affecting Europe and European publics. Moreover we will ask respondents about policy responses to such crises at both national and European level as well as on blame attribution, to attempt to garner evidence on the potential mismatch between citizen views and policy responses. The questionnaire will be translated in the national languages of the countries included in the project. Translation protocols will be applied to ensure equivalent translations in all the languages. Beneficiary 4 (USFD) will be responsible for the preparation of the questionnaire (English version).

Task 4.2: Sampling, pretest, and data retrieval

In order to be suitable for statistical analyses, each national sample will contain a minimum of 2000 respondents. This sample size is within the efficient zone in terms of confidence interval (sampling error). The questionnaire will be pretested before starting the coding. Data retrieval will be done through the CAWI method (Computer Assisted Web Interviewing). Robust methodological standards will be applied to ensure comparability of data across countries. This task will be subcontracted to a specialist polling institute.

Task 4.3: Analysis of survey data

The survey data will be analysed through traditional statistical methods, for example, cross-tabulations and regressions and multilevel analysis. It will be of two kinds. Firstly, descriptive analyses on key variables of interest will provide a picture of what proportions of citizens from different social groups agree with various attitudes linked to populist concerns as well as turnout to vote or support populist parties across the countries of the project. Secondly, explanatory analyses will study how these variables influence each other as applied for the comparative analytical report detailed below.

Task 4.4: Drafting of comparative report

Beneficiary 4 (USFD) will write the comparative report which will consist of a publishable working paper examining questions of this work-package from a comparative perspective.

Participation per partner

Suggestion: 2 pm per country team + 10pm for USFD as coordinator

D4.1 Questionnaire for the analysis of individual attitudes and behaviours

D4.2 Integrated report on individual attitudes and behaviours

Description of deliverables

D4.1) Questionnaire for the analysis of individual attitudes and behaviours

Questionnaire for the population survey (English version).

D4.2) Comparative report on the key findings of WP4: a publishable working paper examining the key questions of this work-package from a comparative perspective

Schedule of relevant milestones

Population survey questionnaire ready