# Proposal Part B: technical description

Democracy Between Complacency and Erosion

(DEMCORE)

## List of participants

| ##### Participant No. * | ##### Participant organisation name | ##### Short name | ##### Country |
| --- | --- | --- | --- |
| ##### 1 (Coordinator) | University of Amsterdam | UVA | Netherlands |
| ##### 2 | Bocconi University | UCLB | Italy |
| ##### 3 | SWPS University of Social Sciences and Humanities | SWPS | Poland |
| ##### 4 | Newcastle University | UNCL | UK |
| ##### 5 | GESIS – Leibniz Institute for the Social Sciences | GESIS | Germany |
| ##### 6 | University of Southern Denmark | SDU | Denmark |
| ##### 7 | London School of Economics and Political Science | LSE | UK |
| ##### 8 | Sciences Po Paris | SCPO | France |
| ##### 9 | Centre for European Policy Studies | CEPS | Belgium |

## Summary

Dgfsnghfm zsgs

## 1. EXCELLENCE

DEMCORE studies challenges to liberal democracy in the European Union (EU). While the EU aspires to defend core liberal democratic norms, including civil liberties and constitutional constraints on excessive executive power, and liberal democratic values such as gender equality, it has seen signs of democratic backsliding among some of its member states. While much of the scholarly focus has thus far dealt with the actions of political leaders that lead to erosion of democracy at the national level, DEMCORE offers a novel contribution by arguing that the resilience of liberal democracies depends largely upon whether democratic governments and citizens express complacency for the democratic institutions that are designed to constrain their power.

DEMCORE’s particular focus lies on the interactions between citizens and political elites. European citizens’ support for liberal democratic norms and values are crucial for ensuring the  legitimacy and resilience of liberal democracy across the continent. Political parties and politicians play a key role as they can both strengthen and uphold, but also seek to undermine, those same norms and values.

DEMCORE’s second innovative approach is its explicit focus on the role of the EU. On the one hand, the European Commission and the European Parliament have taken several measures to prevent further democratic backsliding. On the other hand, this leads to a further politicisation of EU integration, which might inadvertently provide a platform for political agents to challenge liberal democracy within and across the. DEMCORE will unpack this interplay between the supranational and national level in the EU.

In doing so, DEMCORE’s core objectives are:

1) To create an in-depth understanding of the long-term trends of support for liberal democracy among European citizens and political parties and the extent to which these are shaped by contextual factors and institutions. 2) To provide a comprehensive account of the challenges that liberal democracy in Europe is currently facing – both in terms of contestation of ideals in public discourse and in the electoral marketplace – and the role of historic, political and economic factors in this contestation. 3) To develop strategies to counter illiberal democrats and ensure liberal democratic resilience across Europe in the long run.

DEMCORE is designed by an interdisciplinary consortium of world-leading scholars and the first project to provide an integrated account of long-term trends, current challenges and future implications with respect to liberal democracy in the EU. Its theoretical innovation, analytical precision, open science approach, and evidence-based policy recommendations will provide for a lasting impact towards fostering a resilient liberal democracy within and across the EU. DEMCORE’s key features are that it:

- Develops an analytical framework of the way historic, political and economic contexts shape past and future developments and current challenges to liberal democratic norms and values across time and space in the EU.

- Goes beyond the state of the art by arguing that the interaction between political parties and citizens within and across countries is imperative in shaping and defending civil liberties and liberal democratic institutions in the EU.

- Is inclusive by considering the gender dimension in the substance of the project, as well as in the composition of the consortium.

- Is ambitious in its scope through studying long-term trends of and current challenges to liberal democracy across all EU member states, while an additional sub-sample of carefully selected countries serves to evaluate the effect of different strategies to consolidate liberal democratic values.

- Breaks new ground through methodological innovation with respect to measuring attitudes towards and preferences for liberal democratic values among citizens and voters, in party manifestos, in public discourse and in political messages and offers all innovation to relevant stakeholders for re-use.

- Stands out with its multi-method approach, combining (automated) content analyses of political communication and social media content with representative surveys alongside experimental methods, and generates novel data with respect to support for liberal democratic values in the EU.

- Actively engages with key stakeholders from politics, media and civil society throughout the project to learn from, test our ideas with and inform these communities, thereby proactively supporting the reinstating of the legitimacy and effectiveness of liberal democracy.

## 1.1 Objectives and ambition

Defining features of liberal democracy are respect for and protection of core civil liberties and constitutional constraints on excessive executive power. These constitutional constraints consists of various procedures and institutions that are designed to limit the power of the executive, often referred to as ‘checks and balances’. Thereby, liberal democracy is understood as extending the elementary definition of electoral democracy (e.g. Coppedge et al. 2016; Mechkova et al. 2017). The ‘liberal’ components of democracy do not only ensure that elections remain free, fair, and competitive in the long run, they also protect the rights of individuals and minority groups against the abuse of government power, even if that government has an electoral mandate. Consequently, there is an inherent tension between the electoral pillar (based on majoritarian principles) and the constitutional pillar (designed to protect basic rights) of liberal democracy. The tension exists when civil liberties, such as minority rights and press freedom, constrain the executive’s ability to enforce ‘the will of the people’. This tension is captured in the distinction between ‘electoral democracies’ and ‘liberal democracies’, also found in the V-Dem (Varieties of Democracy) classification (e.g. Coppedge et al. 2016). Both electoral and liberal democracies organise competitive elections, but liberal democracies also seek to protect “the rule of law ensuring respect for civil liberties, judicial constraints on the executive branch, and legislative checks and oversight of the executive” (Mechkova et al. 2017: 162).

The EU aspires to be a defender of liberal democracy: “The Union is founded on the values of respect for human dignity, freedom, democracy, equality, the rule of law and respect for human rights, including the rights of persons belonging to minorities” (Art. 2, TEU). However, in several EU member states, most particularly Hungary, Poland, and Slovenia, we observe processes of ‘democratic backsliding’, which is the gradual erosion of the institutions designed to protect citizens’ civil liberties, to guarantee the rule of law, and to constrain the power of the executive (e.g. Bermeo 2016; Mechkova et al. 2017; Plattner 2017; Levitsky and Ziblatt 2018; Freedom House 2020). These processes occur alongside political attacks on supranational institutions (EU, ECHR) that seek to promote democracy and protect minority rights (De Vries and Hobolt 2020). As the EU is founded on the principles of liberal democracy, democratic backsliding in these member states leads increasingly to conflicts between the European Commission and the European Parliament on the one hand, and the national governments of these countries on the other. Thus, conflicts about the future of liberal democracy are increasingly waged at different levels; national, supranational and transnationally between these levels. Supporters of liberal democratic norms and values expect the EU to take measures against authoritarian tendencies in some of its member states. Yet, by interfering in the internal affairs of these countries, the EU inadvertently provides a platform for nationalistic agents who claim national sovereignty. As a result, Euroscepticism becomes increasingly aligned with challenges to liberal democracy, particularly in countries where the institutions of liberal democracy are under siege (Van der Brug et al. 2021a). This dilemma constitutes the core of DEMCORE, which makes the project a perfect fit with the EC’s ambition to fuel innovative research on democracy and governance (‘Destination 1’ in the Work Programme 2021-2022 on Culture, Creativity and Inclusive Society).

Questions pertaining to challenges of liberal democracy within the EU have thus far been prominently addressed by scholars of political theory (e.g. Wolkenstein 2019), law (e.g. Castillo-Ortiz 2019; Halmai 2019; Kelemen 2017; 2020), international relations (e.g. Buzogány 2017; Sedelmeier 2014), and comparative politics (e.g. Buštíková and Guasti 2017; Cianetti et al. 2018; Schlipphak and Treib 2017). Among these kinds of scholars there is also a new interest in relation to the consequences of the Covid-19 pandemic for civil liberties as well as for checks and balances in democratic governance (e.g. Bolleyer and Salát 2021; Drinóczi and Bień-Kacała 2020; Engler et al. 2021; Guasti 2020). While all of these contributions are important and insightful, DEMCORE argues that the interaction between political elites and citizens within and across countries is imperative in shaping and defending civil liberties and liberal democratic institutions in the EU. After all, when democratic backsliding occurs, it happens gradually over a long period of time during which it will be subject to contestation of ideals of liberal democracy in public discourse and in the electoral marketplace (see also Bermeo 2016). Yet, this notion has received relatively little attention in extant research, which is why the interaction between citizens and political elites lies at the core of DEMCORE.

There is, of course, a large body of research into populism, a phenomenon which is often considered illiberal in itself (e.g. Mudde 2016). Populist claims tend to focus on the ‘will of the people’, anti-elitism and illiberal attitudes, such as against minorities, when brought to a fore in public discourse or in the electoral arena and have been therefore widely studied as such (e.g. Aalberg et al. 2016; Rooduijn et al. 2014; Stanley 2019). However, the contestation of civil liberties and the undermining of democratic institutions become more salient only once populist parties are in government (Mudde and Kaltwasser 2012), which is when these particular phenomena are also subject to empirical research (e.g. Bartha et al. 2020; Buštíková and Baboš 2020; Grzymala-Busse 2019). However, in order to understand key mechanisms and identify warning signs to ultimately counter illiberal tendencies, it is key to focus both on countries with and without populist governments (i.e. different European political contexts) when considering how liberal democratic norms, including civil liberties and constitutional elements, and liberal democratic values, such as gender equality, are challenged by political agents and their supporters (see also Van der Brug et al. 2021b). After all, illiberal tendencies are not only discernible in young democracies (e.g. Hungary, Poland), but also pose a threat to consolidated democracies in Western Europe (Levitsky and Way 2020). This is why the scope of the DEMCORE is wide and the project focuses on all EU member states in studying long-term trends of and current challenges to liberal democracy. In parallel to this, in an additional subsample of carefully selected EU countries, the project also evaluates the effect of different strategies to consolidate liberal democratic norms and values. This approach, then, enables DEMCORE to deliver key new insights into the way historic, political and economic contexts impact past and future developments and current challenges to liberal democratic norms and values across time and space in the EU. It not only makes the project unique, but also of critical importance for reinstating the legitimacy and effectiveness of European liberal democracy.

In doing so, DEMCORE will accomplish three ambitious objectives, among which the first one is to provide:

1) An in-depth understanding of the long-term trends of support for liberal democracy among European citizens and political parties and the extent to which these are shaped by contextual factors and institutions.

We study support for liberal democratic norms and values among citizens as well as parties and politicians. Citizens’ attitudes towards democracy have thus far covered a breadth of concepts, including support for democracy in general (e.g. Armingeon and Guthmann 2014; Foa and Mounk 2016; Inglehart 2003), satisfaction with democracy (e.g. Hobolt 2012; Karp et al. 2003; Linde and Ekman 2003), attitudes towards and support for the current system of government (Almond and Verba 1963) and trust in democratic institutions (e.g. Hakhverdian and Mayne 2012; Mauk 2020) to mention the major ones. However, there is little research into specific support for liberal democratic values and norms, bar two exceptions: Schedler and Sarsfield (2007) define liberal democratic attitudes by the combination of support for democracy and liberal values, expressed in support for female emancipation and tolerance towards homosexuals and ethnic minorities. Ferrin and Kriesi (2016) measure liberal democratic values by means of items included in the European Social Survey (ESS) of 2014 on the “relative importance of various democratic norms”, including independent courts, minority protection and freedom of the press. While we consider both approaches valuable because these items tap important aspects of liberal democracy, they miss one of its core features: the inherent tension between majoritarian principles and support for the ‘constitutional pillar’ when measuring popular support for liberal democracy. Only very recently have scholars designed survey questions, which tap into this tension and consortium members have conducted pioneering work in this respect (Van der Brug et al. 2021a, 2021b). Such types of questions are included in the most recent wave of the Comparative Study of Electoral Systems (fielded between 2018 and 2022) and in the European Elections Study 2019. While these do not lend themselves for longitudinal analyses, we will study the contexts in which support for liberal democracy is particularly low or high.

Political parties represent citizen preferences and attitudes and offer different choices for voters at the polls. Within the European party politics literature, there are two major strands that are relevant to us, namely research into patterns, antecedents and consequences of Euroscepticism (e.g. De Vries and Edwards 2009; Halikiopoulou et al. 2012; Taggart 1998) and populism (e.g. Mudde and Kaltwasser 2012; Rooduijn et al. 2014; Van Kessel 2015), respectively. Yet, and although the rhetoric of political parties can play a crucial role in undermining public support for liberal democracy, we still lack systematic evidence on how political parties have sought to challenge, or defend, liberal democracy in the EU over time. Manifesto research, for example, has mostly studied the extent to which parties employ populist rhetoric or engage in Euroscepticism (e.g. Braun et al. 2019; Gabel and Hix 2002; Rooduijn et al. 2014). A significant amount of studies using election manifestos or the Chapel Hill Expert Survey (CHES) assesses party positions on liberal-vs-authoritarian dimension as well as civil liberties (e.g. Jungar and Jupskås 2014; Norris and Inglehart 2019; Rovny and Edwards 2012). However, these studies rarely deal with preferences for maintaining or reforming the ‘constitutional pillar’ of liberal democracy, such as questions pertaining to the independence of public broadcasters or checks-and-balances in democratic governance. Likewise, the extent to which political parties attack gender equality and how this varies across member states and over time remains largely unexplored. DEMOCRE therefore  provides a comprehensive account of party positions towards liberal democratic norms and values, and by doing so, is the first research project conducting a thorough longitudinal analysis of partisan rhetoric on these issues. To do so, we rely on the outstanding conceptual and methodological expertise of the consortium’s leading scholars in the field of party politics.

Understanding longitudinal trends in support for liberal democratic values and norms allows DEMCORE to reflect upon and actualise what liberal democracy means in the 21st century in Europe – thereby delivering one of the key expected outcomes upon which the call “HORIZON-CL2-2021-DEMOCRACY-01-01: The future of liberal democracy in Europe” is based. This leads us to DEMCORE’s second objective, which will provide:

2) A comprehensive account of the challenges that liberal democracy in Europe is currently facing – both in terms of contestation of ideals in the public discourse and in the electoral marketplace – and what role historic, political and economic contexts play for this contestation.

Given the lack of knowledge about longitudinal developments in both citizen attitudes and party positions towards liberal democracy, there is also a considerable gap in the literature when it comes to understanding the interplay between citizens and politicians in the contestation of liberal democratic norms and values. We argue that this contestation is especially relevant in public discourse and the electoral market place. While recent studies investigate the reactions by Members of the European Parliament to anti-democratic developments in EU member states (Herman et al. 2021; Meijers and Van der Veer 2019; Norman 2021), their exchange with citizens on these issues remains underexplored. Public discourse has thus far been empirically investigated only with respect to populist discourse (e.g. Aalberg et al. 2016; Mudde 2004; Wodak et al. 2013) or Eurosceptic discourse (e.g. De Wilde and Trenz 2012; Michailidou 2015). However, we cannot ignore that the political rhetoric of challengers of liberal democracy become appealing transnationally (Levitsky and Way 2020) and that there are opportunities for both opponents and supporters of liberal democracy to distribute (il)liberal appeals across the EU. DEMCORE therefore studies how these appeals spread across social media and what reaction they trigger from the public. Given the rapidly changing information environment alongside the increasing dissemination of disinformation and populist appeals (Tucker et al. 2018) as well as the potential of social media to provide exposure to counter-attitudinal views (Barberá et al. 2015; Guess 2021), such study is now more important than ever; and members of the consortium possess the ideal expertise and experience to study the contestation of liberal democratic norms and values by politicians and citizens on social media (Fazekas et al. 2021; Kruikemeier et al. 2018; Theocharis et al. 2016, 2020).

When it comes to the electoral market place, challenges to liberal democracy often emerge from within a political system when voters are willing to vote for, or turn a blind eye to, politicians who seek to undermine core liberal democratic norms and values. Regarding demand, research has examined liberal democratic attitudes of European citizens (Van der Brug et al. 2021a, 2021b). Yet, we still do not know the extent to which these attitudes guide their voting behaviour. This same discrepancy also holds for the relationship between populist attitudes and support for liberal and anti-liberal parties (Stanley 2019; Van Hauwaert and Van Kessel 2018), although not for Eurosceptic attitudes and related preferences for Eurosceptic parties (e.g. De Vries 2018; Hobolt and De Vries 2016; Van Spanje and De Vreese 2011). On the ‘supply side’ of the electoral market, we do not know whether political parties act strategically in either promoting or undermining core liberal democratic norms and values in their election campaigns in order to gain votes, although such strategies are empirically recognised with respect to EU positions (e.g. Hooghe et al. 2002; Meijers and Rauh 2016; Van de Wardt et al. 2014) and populism (e.g. Mudde and Kaltwasser 2012; Vachudova 2021). In order to understand the challenges that European liberal democracy is facing today, DEMCORE also studies voter and party behaviour in order to provide comprehensive empirical insights into the relationship between voter attitudes and party positions. It is therefore imperative that we investigate voter and party behaviour in the electoral marketplace. Since our consortium comprises core members of the European Election Study (EES), DEMCORE is well-placed to advance the field by shedding light onto the extent to which liberal democracy is anchored in European citizens’ voting choices for parties with (il)liberal political platforms.

Understanding the interplay between citizen preferences and partisan rhetoric with respect to similar or competing visions of liberal democracy in Europe, ultimately provides the DEMCORE team with the conceptual and methodological tools to deliver the project’s third objective, that is to deliver:

3) To develop strategies to counter illiberal democrats and ensure liberal democratic resilience across Europe in the long run.

DEMOCRE’s third and final overarching objective also targets the call’s third and final expected outcome: that is, to contribute to producing a forward-looking perspective of how institutions of democratic governance can be made more resilient to illiberal narratives. For exploring such future vision and making it theoretically robust, we need to go beyond the analyses of past developments and current challenges. Having a better understanding of what liberal democracy means in the 21st century and of the extent to which liberal democratic norms and values are contested among European citizens and political elites, is thus not sufficient. What is needed, is insight into two additional dynamics. First, we require comprehensive knowledge about the mechanisms that underpin preferences for (il)liberal democratic norms and values. Understanding citizen preferences for different conceptions of democracy have received relatively little attention in the related literatures on populism and Euroscepticism (Goldberg et al. 2021; Jurado et al. 2018), let alone in research on liberal democracy itself. Interestingly, a recent study on the US context shows that political polarisation there plays a particularly significant role in disrupting the connection between normative support for liberal democracy and willingness to punish parties that depart from those norms (Graham and Svolik 2020). However, European cases remain conspicuously understudied in this regard, particularly in a comparative perspective. There is an important exception provided by members of our consortium: Arceneaux et al. (2020) shed light onto preferences for easing or restricting measures that affect civil liberties during the Covid-19 pandemic arguing that these are conditional upon the type of civil liberties at stake and – importantly – on the endorsement of political parties.

The empirical insights of these studies, and the methodological innovations they employ, will inform DEMCORE’s research into the distribution and motivations of preferences for various for (il)liberal democratic norms and values among European citizens, and the identification of methods to pre-emptively counter the spread of illiberal messages. Having identified the factors that increase the risk of illiberal democracy, and established the attitudes, values, socio-demographic factors and contextual factors that cause certain citizens of liberal democracies to be more susceptible than others to illiberal appeals, we then require the identification of effective strategies to ‘inoculate the vulnerable’ against illiberal appeals. In doing so, we will rely on consortium members’ expertise on the ‘illiberal playbook’ (Pirro and Stanley 2021) to devise messages that dissuade citizens who have adopted illiberal attitudes and beliefs. Using innovative methodologies (conjoint experiments) and narratives (inoculation messages) to accomplish its final objective, and in response to the call, DEMCORE will contribute to reinstating the legitimacy and effectiveness of European liberal democracy.

Final paragraph on IMPACT (once the section becomes clearer) + link back to beginning of this section, i.e. the struggle between the EU and the member states.

demonstrating how democratic governance can be reinvigorated through improving the accountability, effectiveness and trustworthiness of liberal democratic institutions and through the expansion of active and inclusive citizenship that is empowered by the safeguarding of fundamental rights.

From call: Develop recommendations, toolkits, narratives and methodologies to reinstate the legitimacy and effectives of liberal democracies

## 1.2 Methodology

In the following pages we describe our conceptual approach, methodology, and data that will enable us to accomplish DEMCORE’s objectives. We also describe our plan to successfully overcome any challenges in the methodology. The overarching design of the study is summarized in Figure 1 below. The design is structured around the three main objectives that the study wishes to realize. A more detailed description of each of the Work Packages, also the more management oriented ones, will be provided in section 3. In this section we elaborate on DEMCORE’s overarching analytical framework (section 1.2.1), after which we discuss how we intend to accomplish each of our objectives (sections 1.2.2 through 1.2.4). In the then following part (section 1.2.5) we underline the importance of gender in DEMCORE’s substantial focus and methodology. After that we describe DEMCORE’s vital links to national and international research and innovation activities (section 1.2.6) and highlight the project’s world-leading interdisciplinary expertise (section 1.2.7). We conclude with an elaboration on DEMCORE’s comprehensive open science approach (section 1.2.8) and describe our detailed data and research output management (section 1.2.9).

Figure 1: Study design and associated Work Packages.

>>  I would start here very briefly summarising the overall picture, e.g. that it’s a methodologically ambitious and innovative multi-method project, working with both primary and secondary data, etc.

### 1.2.1 Analytical framework: The context of liberal democracy in Europe

Liberal democracy does not evolve in a void. Living conditions in the national context, rules of the game within the liberal democratic context, and the functioning of institutions influence the interaction between citizens and political elites This interaction holds the key to the practice of liberal democracy, because electoral majorities, as well as political parties that hold governing power, need to respect the authority of the institutions that are designed to constrain the power of the executive. Once governing parties challenge the authority of those institutions and mobilize public support against their legitimacy, the delicate balance between the electoral and constitutional pillar of democracy is jeopardized. To assess the interactions between support for liberal democracy on the demand and supply side, we need to understand the long-term trends in the functioning of liberal democratic institutions in Europe and the contexts in which they operate.

Therefore, DEMCORE will develop an original analytical framework of the way historic, political and economic contexts may have presented challenges to support for (the core institutions) of liberal democracies over the past decades across Europe (e.g. the Great Recession, Cold War, dislocation of empires, “war on terror”, large inflows of mixed migration, the recent pandemic, etc.). DEMCORE’s analytical framework will derive the various ways in which contextual conditions and performance of institutions impact support for liberal democratic norms and values at the demand and supply side. The framework will also conceive the relevant trends needed for the understanding of the functioning of civil liberties (e.g. press freedom), civil rights (e.g. gender equality and LGTBQ-rights) and liberal democratic institutions (e.g. independent courts) of European liberal democracies. For example, attitudes towards democracy in general vary across generations and political contexts (e.g. Norris 2017) – also within the EU (e.g. Norris 2011; Zilinsky 2019); and crises, such as the global economic crisis, affect attitudes towards democracy in various ways (e.g. Cordero and Simón 2016; Teixeira et al. 2014). We expect similar dynamics when it comes to long-term trends in public opinion and partisan rhetoric towards liberal democratic norms and values. In other words, DEMCORE’s analytical framework will structure our analyses that lead to the accomplishment of our first objective. We will describe below how we do this (section 1.2.2).

To do so, we go back in time to the beginning of the 1990s. After the fall of communism, the third wave of democratization got a boost in the 1990s; and patterns of autocratisation or democratic backsliding have begun in the early 2000s. We will collect and combine data that describe the economic and political context citizens experience in their everyday lives on the national level. By combining contextual information with survey data and content analyses of party communication, DEMCORE’s analytical framework will offer insights for interactions between various contexts at the EU and the national level on the way in which the actions of elites influence public support for liberal democracies. The contextual indicators will be used for understanding challenges to liberal democracy in the public discourse and in the electoral arena, and will thereby help us to accomplish the second objective on which we will elaborate below (section 1.2.3).

Finally, DEMCORE’s analytical framework will also guide the case selection that is used to accomplish the third objective, namely to obtain a better understanding of the conditions that are favourable for sustaining public support for liberal democracy in the EU and beyond (section 1.2.4). Here, it will be important to include countries that have varying historical experiences with democracy, that exhibit variation in political and economic contexts, and that differ in their degree to which their liberal democratic institutions are resilient to internal and external challenges.

### 1.2.2 Understanding long-term trends in citizen attitudes and partisan rhetoric towards liberal democracy

To accomplish our first objective, we will unpack it by studying in parallel the long-term trends of citizen attitudes towards liberal democracy on the one hand, and conceptions of liberal democracy by political parties on the other:

| 1) An in-depth understanding of the long-term trends of support for liberal democracy among European citizens and political parties and the extent to which these are shaped by contextual factors and institutions. |  |
| --- | --- |
| Citizen attitudes towards liberal democracy | Conceptions of liberal democracy by political parties |

In this part of the study, we will combine three types of data sets in order to model the contextual conditions that are linked to support for liberal democracy at the level of voters and parties: 1) contextual data at the country-year level (WP2), survey data measuring support for liberal democracy among citizens (WP3) and support for liberal democracy among parties (WP4). The measurement has to cover the period between the early 1990s and 2022. The separate Work Packages are discussed in more detail in section 3 below. The relevant context variables are:

- National economic performance data to follow the overarching economic output of each country across time (eg. world bank, Eurostat)

- Demographic data capturing the changes in the consistence, immigration status and education levels of the population

- Work force data to be able to follow changes in the consistence of the work force and therefore changes in the nature of work across the period of thirty years

- Economic and gender equality indexes

- Government and European Union investment data that allow to follow the development of public investment over time, and especially the participation of the EU in the infrastructure investment in weaker member states.

- Data on government consistence and electoral results. These data will come from existing databases such as ParlGov and whogoverns.eu

- Data that capture institutional output of the democratic and the party system in operation in each country

  - For the democratic system the data will come from the existing dataset of the V-Dem Project

  - For the party system we will use pre-tested measures such as closure, electoral volatility, effective number of parties, polarisation, electoral disproportionality, party institutionalisation

As we discussed earlier, measuring support for liberal democracy is not straightforward. Defining principles of liberal democracy is the protection of civil rights of individuals as well as minority groups. Yet, liberal democracy consists of a complex set of institutions that are designed to protect these civil rights, also against governments that have received a democratic electoral mandate. To measure support for liberal democracy we must therefore not only measure ‘liberal’ attitudes towards underprivileged groups, but also support for the institutions of liberal democracy, as well as for the principle that these institutions should be allowed to overrule electoral majorities. We realize that most survey data will only contain some items that can be used for our purpose. DEMCORE will make an inventory of the available European data on these relevant attitudes from the 1990s onwards and, in as much as possible, harmonize and pool them into one original dataset. Relevant data sources include the European Social Survey (ESS), the European Values Study (EVS), and the European Election Study (EES) and the Comparative Study of Electoral Systems (CSES).

Likewise, while we have cross-national longitudinal datasets on the policy positions of political parties, such as the Manifesto Project (https://manifestoproject.wzb.eu/) and the Euromanifesto Project that was part of the EES and the Chapel Hill Expert Survey (CHES) on party positions, we lack systematic data that allows us to analyse and compare long-term trends in the party rhetoric towards liberal democracy, its key institutions and liberal democratic values, such as gender equality. Therefore, DEMCORE will collect raw material of national and European parliamentary manifestos and political speeches (from ParlSpeech and EUSpeech corpora). We will then build an original dataset, combining hand-coding and state-of-the-art computational text analysis, with the positions of political parties on core liberal democratic norms and values.

Once we have collected (and coded) relevant data that allow us to study the long-term trends in citizen attitudes and partisan rhetoric towards liberal democracy, we will link these two datasets with the contextual data generated by our analytical framework. This then allows us analyse the interplay of individual-level support for liberal democracy across generations and changes in party positions towards liberal democracy over time against the backdrop of and political and economic contexts across the EU. These analyses will first of all enable us to describe how citizen attitudes and partisan rhetoric have evolved over time. In addition, it will enable us to study the relationship between (the development of) support for liberal democracy among voters and among the parties they support. Finally, the link with contextual data will enable us to assess the contexts in which support for liberal democracy is high or low.

### 1.2.3 Assessing current challenges to liberal democracy in Europe

To accomplish our second objective, we will unpack it by studying in parallel the contestation over ideals of liberal democracy in public discourse on the one hand, and in the electoral marketplace on the other, which both involve citizens and political parties and politicians:

| 2) A comprehensive account of the challenges that liberal democracy in Europe is currently facing – both in terms of contestation of ideals in the public discourse and in the electoral marketplace – and what role historic, political and economic contexts play for this contestation. |  |
| --- | --- |
| Contestation of ideals in the public discourse | Electoral marketplace for different visions |

Liberal democracy is upheld by two pillars: the ‘popular pillar’, based on the principle of majority rule, and the ‘constitutional pillar’, based on the principle of individual and minority rights and the rule of law (Dahl 1956; Sartori 1995; Mény 2003). We have argued that, there is a possible tension between the two pillars of liberal democracy when civil liberties, such as equality of women and minorities, freedom of the press and court independence, constrains the executive’s ability to enforce ‘the will of the people’. Those who challenge liberal democracy often do not reject majoritarian democratic principles, but instead attack the civil liberties of individuals (particularly women, LGBTH-people and ethnic minorities) as well as the institutions designed to protect them. Existing survey questions focus more on civil liberties and tolerance than on the inherent tension between majoritarian principles and support for the ‘constitutional pillar’. Like in the first part of the study described in section 1.2.2, this part of the study also focuses on the relationship between parties and citizens in their support for liberal democracy. However, two aspects are different.

First of all, in this part of the study we will  collect survey data that focus on the inherent tension between the majoritarian principles and protection of civil rights. The existing literature does not really provide operational definitions for the study of citizen attitudes and partisan rhetoric towards liberal democratic norms and values. However, DEMCORE has the necessary expertise and experience to address this challenge and will develop reliable and valid measures and thereby contribute to advancing both the academic literature and our understanding of what liberal democracy means in the 21st century in Europe. Secondly, in this part we focus on the discourse of parties and citizens on social media, rather than on the more traditional platforms.  In the following, we explain how we will do this.

The 2024 European Parliament (EP) election serves as the arena in which we study both public discourse and electoral contestation. EP elections are traditionally considered second-order national elections (Reif and Schmitt 1980) – a notion that is still applicable today (e.g. Gattermann et al. 2021; Van der Brug and De Vreese 2016; Van der Brug et al 2016), which means that national instead of European political considerations dominate the election campaigns and guide the voting behaviour of European citizens. Nonetheless, EP elections have become increasingly politicised over time (Van der Brug et al. 2021c), and challenges to European liberal democracy in the form of democratic backsliding in some EU member states contribute to the contestation over EU integration (Van der Brug et al. 2021a). In other words, questions about national sovereignty vis-à-vis European integration are expected to be highly salient for citizens and political parties, which, as we argued at the outset, impacts the contestation of different ideals of liberal democracy in both the public discourse and in the electoral marketplace.

To assess the dynamics of public discourse, we study the social media discourse between political elites and the public during the 2024 EP election campaigns (in WP5). Recent years marked a move of politicians from websites and blogs to various social media platforms. Ease of use, the potential to bypass the mainstream media, and the limitless opportunities for personalized communication, have led politicians to use social media strategically (Barberá and Zeitzoff 2018; Dotti Sani and Magistro 2016; Goldberg 2010; Grant et al. 2010; Kruikemeier et al. 2018; Larsson 2015). Also citizens make more use of social media as a source of political information (Parmelee and Bickes 2012; Popa et al. 2019). This has led to social media becoming a legitimate and prevalent source of information (Harder et al. 2017; Popa et al. 2019) with approximately 36 percent of respondents in an August 2020 Eurobarometer survey indicating social media networks as one of their main sources of information (Eurobarometer 93.1, 2020). Moreover, citizens also make use of the new opportunities provided by social media platforms to follow and directly interact with formerly largely inaccessible individuals in the political elite (Levy et al. 2017; Fazekas et al. 2021).

DEMCORE will break new ground by examining the extent to which social media spread and shape (il)liberal attitudes in the public discourse. Illiberal attitudes, including the support for authoritarian rule and the challenging of liberal democratic norms and values, were previously considered “undemocratic”, thus unacceptable and marginalized in the mainstream political discourse (Tucker et al. 2017). We expect that the increasing importance of social media in structuring political debate (through both demand and supply-side mechanisms) facilitates the diffusion of such values by offering people who hold illiberal attitudes an uncensored platform to challenge the core of liberal democratic norms and values. This likely enables them to find like-minded others and form larger communities (Tucker et al. 2017). This process is reinforced by the absence of critical journalists acting as gatekeepers and by the insulated character of social media networks (Barberá et al. 2017). In this context, social media facilitates the surge of political outsiders which rely on an anti-system discourse that would have previously been suppressed by the traditional institutions structuring political discourse such as parties and legacy media (Jungherr et al. 2019). A classic example of such tendencies is populist parties, which owe their success at least in part to their reliance on social media (Ernst et al., 2017; Stier et al., 2017; Tucker et al., 2017). Given the established link between illiberal attitudes and support for populism (van der Brug et al. 2021b) and since social media platforms, Twitter in particular, have become a powerful tool for parties and groups that wish to challenge liberal democratic norms and values (e.g., Curiel 2020), similar assumptions underpin DEMCORE’s study regarding the contestation of liberal democratic ideals in the social media discourse.

Data will be collected using the Twitter Streaming API, which is free for academic research purposes, and CrowdTangle for Facebook during the four weeks leading up to the 2024 EP election. Methodologically, we will monitor and measure the spread of ideas that support illiberal attitudes and the role that political elites play in the diffusion of such messages through the use of supervised and unsupervised machine learning methods. Following a similar strategy that was employed by Consortium members in previous research (Theocharis et al., 2020; Fazekas et al., 2021), DEMCORE will use human annotation of a random sample of posts along the key dimensions that define illiberal democratic attitudes. We will further employ supervised machine learning to extend the content-coding from that done through human annotation to all the data collected across the EU.

DEMCORE will identify political actors that challenge or endorse liberal democratic norms and values on social media, analyse patterns of (il)liberal democratic discourse initiated by political elites and the public response, and assess the extent to which their messages appeal to a wide audience. In this respect, we will analyse three aspects of illiberal democratic appeals that could potentially explain their success: 1) the communication style (broadcasting vs. engaging) (Theocharis et al. 2016; Fazekas et al. 2021), 2) the use of emotive rhetoric (Osnabrügge et al. 2021), and 3) their association with other political issues (De Vries and Hobolt 2020). Lastly, DEMCORE will also assess the extent to which and under what conditions (il)liberal democratic appeals on social media travel across European countries (or not). This allows us to evaluate if political elites make use of a common ‘playbook’ (see Pirro and Stanley 2021) or if they contextualize these messages according to a given countries’ circumstances.

Regarding the electoral marketplace, EP elections provide an appropriate context to examine how both individual and contextual level factors shape electoral support for ‘illiberal democrats’ as they are held at the same point in time across European countries under very similar institutional rules. This allows us to hold constant important institutional and temporal factors. To measure voter attitudes towards liberal democratic norms and values in the electoral marketplace, we will integrate and advance existing work (in WP6), which consists of three approaches. The first is in line with Schedler and Sarsfield (2007) who define liberal democratic attitudes by the combination of support for democracy and various liberal values, such as tolerance towards homosexuals. There are various cross-national studies which contain these kinds of variables, such as the European Social Survey (ESS), the European Values Study (EVS), and the European Election Study (EES). Members of the consortium have played a leading role in the EES in the past few years. The second approach to measuring attitudes towards liberal democratic norms is by means of a battery of survey items included in the 2014 ESS on the “relative importance of various democratic norms”, including independent courts, minority protection and freedom of the press (Ferrin and Kriesi 2016). The third approach is a set of survey questions, which are explicitly designed by members of DEMCORE’s consortium to capture the tension between the popular and constitutional pillars of democracy (Van der Brug et al. 2021a, 2021b). These questions were previously included by DEMCORE’s consortium members in the EES and one of these survey items was also included in round 5 of the Comparative Study of Electoral Systems (CSES). We will apply these again in the study of contestation over liberal democracy in the electoral marketplace and develop additional measures to capture the breadth of the concept of attitudes towards liberal democratic norms and values.

By combining the content analyses of the public discourse (WP5) with individual survey data (WP6), we will examine voter support for ‘illiberal’ party platforms, the role of their own attitudes towards norms and values of liberal democracy in their voter behaviour and the appeal of those parties that challenge liberal democracy in the EU.

### 1.2.4 Producing a robust vision for the future of liberal democracy in Europe

In the previous section we described how we will study the ways in which illiberal messages are disseminated via the internet and how being exposed to these measures is related to electoral preferences and support for liberal democracy. However, we also wish to study the causal mechanisms that underpin preferences for (il)liberal democratic norms and values. Knowledge of such causal effects could also be useful for developing effective strategies to ensure liberal democratic resilience among European citizens. In this section we describe how we intend to study such causal effects.

| 3) To develop strategies to counter illiberal democrats and ensure liberal democratic resilience across Europe in the long run. |  |
| --- | --- |
| Understanding citizen preferences | Ensuring liberal democratic resilience |

Understanding citizen preferences for (il)liberal democratic norms and values and how these preferences come about is an important first step towards producing a robust vision for the future of European liberal democracy. While theorists have disputed the validity of ‘illiberal democracy’ as a concept (Müller 2016), in recent years many political parties and voters alike have continued to act as if illiberalism and democracy were compatible attributes of a legitimate political system, while at the same time rejecting authoritarian alternatives. Approaches that counterpose liberal democracy with authoritarianism may be normatively warranted but are empirically at odds with political practitioners’ understandings and representations of their actions, and with how those actions are received and processed by electorates, particularly in conditions of severe polarisation (Graham and Svolik 2020). As a set of practices and motivating ideas that contest the hegemony of liberalism while laying claim to democratic legitimacy (Coman and Volintiru 2021), illiberal democracy needs to be taken seriously. Even if a majority of voters pay ‘lip service’ to liberal democratic norms and values, the experience of recent years shows many of them to be willing to overlook violations of those norms and to de-prioritise them in favour of other political objectives.

However, we still understand little about the causal links between socio-demographic attributes and political attitudes on the one hand, and preferences for illiberal solutions on the other. Even in the case of the United States, where the majority of existing research into this phenomenon has been conducted, there is little consensus on the consequences of social sorting and polarisation on adherence to democratic norms. While Finkel et al (2020) argue that ‘political sectarianism’ poses a threat to these norms, Broockman et al (2021) and Voelkel et al (2021) find limited evidence to support such claims.  Neither is it clear whether, and to what extent, these pro-illiberal behaviours are persistent over time. To address these questions, and building on insights into attitudes towards and correlates of liberal democratic norms and values generated through the realization of DEMCORE’s earlier objectives, we will examine the causes of illiberal democratic preferences in a three-wave panel survey to be conducted in six EU member states. Our selection of states will vary in the extent to which they have recently experienced democratic backsliding, allowing us to explore the impact of context on the causes we identify.

Addressing these questions requires the deployment of innovative methods of analysis. In recent years a burgeoning line of political science research has sought to move beyond the methodological and inferential limitations of traditional survey questions on democratic values, using conjoint experiments to estimate the relative causal impacts of multidimensional respondent attributes and preferences in more realistic and holistic scenarios (Hainmueller et al. 2014). Using the orthodox model of liberal democratic practices and our conceptual model of illiberal democratic practices as sets of preferences, we will embed conjoint experiments in the panel survey using a decision task approach similar to that employed by Singh and Williams (2021), where respondents are presented with choices of political systems they would prefer to live under. These experiments will serve two purposes. First, by varying the characteristics of conceivable democratic systems with respect to liberalism and illiberalism, it will be possible to identify the key socio-demographic and attitudinal causes of support for illiberal democracy. Second, by varying characteristics of those political systems with respect to the policy outputs and institutional arrangements that our conceptual exploration indicates are likely to be responsible for attracting electorates to those offering illiberal solutions, it will be possible to identify political-institutional causes of support for illiberal democracy. Additionally, the panel design of this survey allows observing the stability of preferences for illiberal democracy over time. Both sets of findings will then provide a basis for the identification of demographics to be targeted in the countering of illiberal democracy and the political-institutional changes that could potentially encourage them to turn (back) towards the liberal-democratic model.

In order to ensure the resilience of liberal democratic norms, it is necessary to confront and refute illiberal messages. A promising approach to doing so comes from inoculation theory. The key insight from this theory is that it is possible to ‘inoculate’ people from an anticipated attempt at persuasion. The reference to inoculation is more than a clever analogy; it is core to theory itself. A vaccine protects people against infection from a virus by introducing a weakened version of the virus into the immune system, creating antibodies that neutralize the virus upon contact. In the same way, an inoculation message “is made with weakened versions of the anticipated persuasive challenges” (Compton et al. 2021: 3). In this project, we conceptualise illiberal messages to be like a virus. If left unchecked, they will spread and infect citizens by persuading them to support illiberal policies and parties. Inoculation messages can be used both as a prophylactic to protect citizens against illiberal messages that they may encounter in the future and retroactively to try to treat and dissuade citizens who have adopted illiberal attitudes and beliefs.

Inoculation messages consist of two components: 1) a forewarning that someone will attempt to persuade them to change their mind and 2) a pre-emptive refutation of the arguments that they will encounter (Ivanov et al. 2020). This two-fold approach creates resistance to future persuasive attempts through two psychological mechanisms. The forewarning lets people know that their attitudes are vulnerable to a threat and, thus, in need of protection, while the pre-emptive refutation provides people with counterarguments to repel the persuasive attempt when they encounter it (McGuire 1964). For example, Jolley and Douglas (2017) reduced parents’ hesitancy toward vaccinating their children by warning them that people with an anti-vaccine agenda will try to persuade them, followed by refutations of a number of anti-vaccine conspiracy theories. Similar to biological vaccines, inoculation messages work best when there is a delay of one week (Pfau and Burgoon 1988). Decades of research show that inoculation messages are effective at creating resistance to persuasive attempts across a number of domains from health communication to science communication to political campaigns (Compton and Ivanov 2013; Compton et al. 2021; Ivanov et al. 2020).

While inoculation messages have been shown to be effective at strengthening people’s pre-existing attitudes toward political candidates (Compston and Ivanov 2013) and policy issues (Pfau et al. 2020; Compton et al. 2021), the dynamics of partisan politics could limit the effectiveness of messages when the source of the message comes from a partisan source that the recipient does not trust (Pfau and Burgoon 1988; Pfau and Kenski 1990). This challenge is made worse in political contexts where people tend to possess strong emotional attachments to a political party and the divide between competing parties is deep. In deeply polarized context, people often reject out of hand any message that comes from opposing parties (Westwood et al. 2018). In these context, therapeutic inoculation messages (Compton et al. 2021) that are designed to change people’s prior beliefs (e.g., convince smokers that smoking is bad) and inoculate them from future attempts to persuade them may be less effective in the domain of politics. Nonetheless, when people are motivated to second guess themselves — that is, to engage in reflection (Stanovich and West 2000) — they become more open to messages that challenge their prior beliefs (Arceneaux and Vander Wielen 2017; Broockman and Kalla 2016; Groenendyk and Krupnikov 2021; Tappin et al 2020). As a result, it is possible that therapeutic inoculation messages could work in polarized political settings if they also contain a motivation for engaging in reflection.

To study the effectiveness of inoculation messages with the aim to ensure the resilience of liberal democratic norms, this part of DEMCORE’s research is structured in three phases. In Phase 1, we will pilot test the effectiveness of traditional pre-emptive refutation messages that are designed to strengthen and reinforce pro-democracy attitudes and beliefs among those who are already supportive of liberal democracy. The purpose of these messages is to combat attempts to persuade people to support illiberal policies and ideals. We will also test the effectiveness of therapeutic inoculation messages that are designed to persuade those who hold illiberal beliefs and/or support illiberal parties to support liberal democracy and then inoculate them from being re-persuaded to hold illiberal beliefs. We expect that it will be more difficult to find effective therapeutic inoculation messages and will experiment with approaches that have been found to increase people’s willingness to second guess their prior beliefs, such as informing people that support for democracy is widespread (see a similar approach for converting climate change deniers, Maertens, et al. 2020) as well as reminding people of the value of being open-minded (Groenendyk and Krupnikov 2021).

Once we have identified effective messages through pilot tests, we will investigate their effectiveness using a multi-country panel study with survey experiments in Phase 2. We envision using a panel study for three reasons: 1) previous research has found it useful to have a delay of one week between exposure to the inoculation message (i.e., a pro-liberal democracy message that refutes illiberal arguments) and exposure to the persuasion attempt (i.e., an illiberal message); 2) the effectiveness of inoculation messages decays with time and previous research has found that “booster messages” can extend effectiveness of the inoculation message (Ivanov et al. 2020); and 3) we are interested in studying whether events, such as elections, influence the effectiveness of inoculation messages. We envision conducting multi-country survey experiments so that we can assess whether the political context — such as, the level of partisan polarisation and the strength of illiberal parties — shapes the effectiveness and durability of inoculation messages.

In Phase 3, we will turn our attention to investigating whether pro-democracy therapeutic messages can work in a real-world context of social media, and Twitter in particular, building on the empirical insights that are generated in response to accomplishing DEMCORE’s second objective. One way to reduce the spread of illiberal messages is to persuade would-be supporters of these messages to not spread them. Following promising work by Munger (2017, 2020) who has successfully used bots to engage with Twitter users to reduce the use of racist slurs and partisan insults. We envision training Twitter bots to respond to illiberal tweets with a therapeutic inoculation message and then study the downstream effects of these messages. Do these tweeter users tweet fewer illiberal messages in the future? How do other observers engage with the therapeutic message? Answering these questions will offer insights into whether and how pro-democracy actors can effectively counter illiberal discourse on social media platforms and potentially beyond.

The country sample for both the conjoint experiment into preferences and the study of inoculation messages will be guided by the analytical framework and empirical insights that were generated when addressing DEMCORE’s previous objectives. To understand citizen preferences for ‘illiberal democracy’, the aim is to include two countries that have experienced sustained democratic backsliding (e.g., Hungary, Poland), two in which liberal democratic norms and values have proven relatively robust to attempted backsliding (e.g., Greece, Slovakia), and two in which there has been little or no pressure brought to bear on liberal democracy (e.g., Finland, Germany). To test the effectiveness of inoculation messages, we require a country sample that exhibits variation in terms of party polarisation and presence/absence of illiberal or anti-democratic movements and propose to consider Denmark, France, Germany, Poland, Italy, and Spain. SUMMING UP the great insights we would get here …

### 1.2.5 The importance of gender

There are two ways in which gender plays an important role in our study. First of all, respect for the equality of women is one of the key components of our measures of support for liberal democracy. One of the defining principles of liberal democracy is the protection of civil rights of individuals as well as minority groups. Equality of citizens irrespective of religion, ethnicity, sexual orientations or gender is therefore one of the corner stones of liberal democracy (Kittilson and Schwindt-Bayer 2012). However, a key part of the challenges that liberal democracy in Europe is currently facing is a growing backlash against gender equality, as well as the equality of other underprivileged groups, such as people from the LGBTQ-community and ethnic minorities. Gender equality is one of the core values of liberal democracy and a corner stone of EU treaties, such as in Articles 3 and 8, TEU, which is why challenges to gender equality constitute a key research area in DEMCORE (see WPs 2, 3, 4 & 6). While the intensity of these challenges is likely to vary across member states, illiberal policies share some aspects that threaten gender equality, such as restricting the space for egalitarian civil society organizations, marginalising gender equality institutions or redefining institutions and policies from a focus on gender equality to a focus on the family unit. It is important to carefully examine the extent to which gender equality is under threat by focussing on citizen support for it and party rhetoric about it. DEMCORE’s dedication to exploring these important topics is reflected in the key objectives and deliverables across the whole project (in particular WP3, WP4, WP5 and WP6).

Secondly, DEMCORE will also focus on the gender gap in support for liberal democracy. It builds upon important work on gender gaps in politics (Kittilson and Schwindt-Bayer 2012, Kittilson 2016), and particularly upon work on the gender gap in support for radical right parties, a topic on which consortium members have worked in the past (e.g., Harteveld et al. 2015, 2019a, 2019b). DEMCORE will explore gender gaps in support for liberal democratic values (WP3) and support for “illiberal” parties (WP6) by comparing the survey responses of men and women, and examine heterogenous treatment effects in our experimental data based on gender. In addition, we will consider intersectional aspects concerning race and ethnicity or socio-economic status for example. Finally, in the content analyses of party communication and social media messages we develop a measure of gender critical rhetoric by political parties using both hand coding and supervised machine-learning coding (WP4).

Combining the citizens and party data allows us to develop a heat map that clearly illustrates the challenge to gender equality across EU member states. This provides a key tool for civil society organizations and journalists focused on gender equality related matters.

### 1.2.6 Links to national and international research and innovation activities

- Describe any national or international research and innovation activities whose results will feed into the project, and how that link will be established; [e.g. 1 pages]

Catherine’s eupinions project

This is a bit tricky, but my immediate thought are the V-Dem project, and then the wider available data from Freedom House, Press Freedom and other indicators will feed into project, also Electoral Integrity project by Pippa Norris, for example. EUPINIONS as well, as we have the direct link 😊

Ideas:

Harmonisations of existing electoral data: The European Voters, True European Voter, CSES

Data Collection projects: The European Election Study, CHES, MARPOR, Euromanifestos, V-DEM, ParlGov

The PopuList https://popu-list.org/

The Scripts Research Cluster: https://www.fu-berlin.de/en/sites/inu/excellence-strategy/proposals/scripts/index.html

The European election study???!!!!

Before I forget again this can be mentioned in part 1.2.6 (I am the leader for WP4) https://www.mzes.uni-mannheim.de/proconeu/

Sebi

### 1.2.7 Interdisciplinarity

The objectives of DEMCORE cannot be answered by a single discipline. Instead, we have adopted an integrated interdisciplinary approach where world-leading experts from across the social sciences are working closely together in each of the Work Packages to maximise the scientific and societal impact. Notably, DEMCORE brings together perspectives from political science, psychology, communication science, European studies, methodology and data science to address the overarching questions of the project: Political science brings expertise in democratic processes, institutions and political actors; psychology provides a deeper understanding of how individual attitudes and norms are formed; communication science focuses on the rhetoric and messages of political parties and their effects on citizens; European studies expertise brings an in-depth understanding of the history and dynamics of European integration; and finally methodologists and data scientists ensure that the project uses state-of-the-art methods in data collection, integration and analysis. Crucially, the governance structure of DEMCORE ensures that these disciplinary perspectives are closely integrated in each of the Work Packages, rather than operating separately. This interdisciplinary perspective is also reflected in the wide range of rigorous methods from time-series econometric analysis, advanced quantitative text analysis, supervised and unsupervised machine learning methods, multi-level survey analysis, and experimental studies. By bringing together expertise across disciplines, DEMCORE is also in a better position to work more closely with policy-makers and stakeholders in addressing the critical questions of challenges to liberal democracy.

### 1.2.8 Open science approach

DEMCORE’s open science strategy is based on two main principles: (1) We aim to achieve high levels of scientific robustness by increasing transparency and reproducibility, that enables other scholars to inspect and verify published results (Klein et al. 2018). (2) We aim to achieve high levels of re-usability of our collected data, through sharing them, so we can improve the efficiency of science by allowing greater re-use and more collaboration (Van Atteveldt et al. 2019).

To achieve high levels of scientific robustness we need to facilitate transparency and reproducibility as well as active replication of our results. To do so our methodology, data collection instruments and data have to be shared in keeping with the criteria of transparent and open science (Miguel et al. 2014; Nosek et al. 2015). For robustness to be fully evaluated and reproducibility to be achieved the data in themselves are not enough. What is needed is a full formal account of data collection and data analysis (American Political Science Association 2012: 10). Additionally, to take a step further towards scientific robustness we need to take seriously the practice of experiment pre-registration. This helps towards elimination of selective reporting, disclosure of p-hacking, and distinction between exploratory and confirmatory research (Wuttke n.d.).

To achieve high levels of reusability of the data collected by DEMCORE we will base our open science activities on the FAIR principles requiring that data needs to be findable, accessible, interoperable, and re-usable (Wilkinson et al., 2016). For that purpose, we will ensure that the data will be deposited in widely known data sharing facilities that are adapted to the needs of our scientific community and reach the highest data management standards. In our case, CESSDA (Consortium of European Social Science Data Archives) and its service providers is the place where data collections on democratic processes are being curated and managed. The important issue here is that data will be easily found and accessed, and that will remain so well after the end of the project.

Specifically, we will take the following measures to implement our open science strategy. We will provide:

- detailed documentation of all methodological decisions in each stage of data collection

- high quality documentation of our data that will include a methods report

- pre-registration of all experiments conducted by the DEMCORE project

- sharing of all data collected in the project

- sharing of syntax files that produce harmonized datasets, visualisations, and models used in our reports

- sharing of data and syntax will be done through a trusted repository such as a CESSDA Service Provider

### 1.2.9 Data and research output management

Types of data/research outputs: The project will produce the following data outputs:

- Database of existing indicator from official statistics and international organisations

- Database of constructed indicators measuring phenomena on the national level

- International survey in form of personal data without any direct identifiers

- Twitter dataset that includes tweets by politicians, replies to these tweets, and all tweets which mention candidates during the election campaigns.

These datasets are not bigger than 1 GB, and all of them are in the form of two-dimensional matrixes.

Findability of data/research outputs: All data outputs will be shared to the scientific community through a CESSDA trusted repository, specifically the GESIS Data Archive. They will be given a persistent identifier in the form of a DOI.

Accessibility of data/research outputs: There will be an embargo of two years, so that the consortium ensure through its own analyses and tests on the data the highest data quality and corrects any possible errata. All data generated during the project will be considered the result of joint effort by the partners collaborating in the specific Work Package. Some of the data will be collected from existed data sources. In the cases that those data are no on a licence permitting reproduction and reuse, an agreement will be drafted for each secondary data set processed by the consortium. This agreement will detail how ownership and exploitation will be dealt with and specify any restrictions on processing techniques that may not be used.

Interoperability of data/research outputs: The data will be described using DDI standards for machine readable metadata as applied at the GESIS Data Archive. Data will be provided in form of STATA, SPSS and non-proprietary file format that allows a wider use on software programmes known in the community.

Reusability of data/research outputs: All of the data will be shared with licences permitting replication and reuse by the wider scientific community for non-commercial purposes.

Curation and storage/preservation costs: The GESIS Team will be responsible for the drafting of the data management plan, the curation and management of all data produced in the project until they will be delivered to the GESIS Data Archive, and the quality assurance of all documentation supporting the data.

Specifically, Careful data consistency checks will ascertain proper data quality, respectively documentation of remaining problems in the released data. A report about the checking results will be provided to the project group upon completion of the checks on the data. Within-data set metadata (i.e. variable and value labels), and external metadata, and further documentation in British English will be created. A package collating all relevant documents provided by the data collection team and the fieldwork organisation will be prepared for easy dissemination alongside the actual data. FAIR requirements will be fully met or over-achieved by using the standard repository services of the certified GESIS data repository, which include dissemination via GESIS Search with rich metadata; integration into CESSDA-wide data search portal and world-wide portals through DOI registration and DataCite, achieving optimal coverage for findability; long-term preservation, with an open-ended storage and preservation perspective. The work will be conducted with a view to allowing two staged releases of the data as part of DEMCORE’s commitment to open science practices. First, a public release of a preliminary version (with much reduced documentation but ready for first analyses by researchers from the project group, and for other competent data users) as fast as possible, and, second, a subsequent full release with full documentation and more careful checks as described above.

## 2. IMPACT

On the following pages we elaborate on DEMCORE’s contribution to the expected outcomes set out for the work programme topic over the medium term, and to the wider expected impacts set out in the ‘destination’ over the longer term (section 2.1), which also includes a description of the likely scale and significance of this contribution (section 2.1.2), before we identify requirements and potential barriers that arise from factors beyond the scope and duration of the project (section 2.1.3). Section 2.2 elaborates on our Impact Plan for co-creation, dissemination, exploitation and communication in order to maximise impact, which also comprises the public disclosure of research data (section 2.2.2), open access publications (section 2.2.3), and our strategy for the management of intellectual property (section 2.2.4). Section 2.3 summarises the key elements of the impact section.

## 2.1 Project’s pathways towards impact

Insert here text for your proposal: elaborate on summary below regarding outcomes and impact

- the outcomes specified in this topic, and (2) the wider impacts, in the longer term, specified in the respective destinations in the work programme.

- produce theoretically and empirically robust visions for the future of liberal democratic institutions.

- Develop recommendations, toolkits, narratives and methodologies to reinstate the legitimacy and effectiveness of liberal democracies.

- Reflect upon and actualise what liberal democracy means in the 21st century in Europe.

- Democratic governance is reinvigorated by improving the accountability, transparency, effectiveness and trustworthiness of rule-of-law based institutions and policies and through the expansion of active and inclusive citizenship empowered by the safeguarding of fundamental rights.

### 2.1.1 Expected outcomes and impacts

DEMCORE’s unique contribution to the expected outcomes in this topic is threefold. First, the project reflects upon and actualises what liberal democracy means in the 21st century in Europe.

Societal: Awareness of the support for, contestation of and external challenges to liberal democracy in Europe

Scientific:

•	A new conceptual framework that provides an integrated account of the support for, contestation of and external challenges to liberal democracy in Europe

•	New operationalisations of illiberal rhetoric, party communication and behaviour, citizen attitudes, behaviour and preferences

•	New data that complement existing data sources (e.g., Freedom House, Varieties of Democracy) and that can henceforth be used in future scientific research

Economic (or technological) – perhaps anything political instead???

Beyond the wider impacts, DEMCORE will also

### 2.1.2 Scale and significance

As elaborated above, the main subjects of our project comprise citizens and politicians political parties in Europe. We study their attitudes, political communication and political behaviour across all EU member states. With respect to citizens, we rely on representative samples from each country; as regards political parties, we consider a) all those parties that have gained seats in past European or national elections and b) those that compete in the 2024 EP election and for which polls predict that they will gain seats in the new Parliament. This approach also means that the subjects will ultimately benefit from the project’s results. In other words, the scale of DEMCORE’s contribution to the expected outcomes and impacts extends to all citizens and political actors across the EU.

The category ‘all EU citizens’ is obviously huge, but DEMCORE has a comprehensive dissemination, and exploitation plan as well as an inclusive communication strategy to ensure that many EU citizens become aware of the benefits that DEMCORE brings to them (see section 2.2). They will benefit most from DEMCORE: after all, they directly contribute to the future development of liberal democracy in Europe – as measured through their attitudes, preferences and behaviour. As such, it is imperative that they are aware of the challenges and opportunities associated with European liberal democracy and what they can do to ensure liberal democratic resilience in the long run.

Significance: Mapping of party positions, especially if transnational lists are implemented. Information is crucial for voting decisions (e.g., xxxx) and thus

- perhaps describe the focus on awareness training for journalists which has a great multiplier effect towards citizens???

### 2.1.3 Requirements and potential barriers

Our project studies the role that public opinion, political communication and political behaviour play for the development of liberal democracy in Europe

DEMCORE’s objectives provide us with a highly dynamic setup and we account for the following potential barriers:

- Key components of the project are implemented against the backdrop of the 2024 EP election. While we do not have any influence over the exact timing of the election, it is unlikely to take place before Spring 2024 because the EP cannot be dissolved and its legislative terms are fixed (Art. 14.3 TEU). The last two elections in 2014 and 2019 each took place in late May; the preceding elections at the beginning of June. We are thus confident that planning the project with the election likely taking place in May 2024 (= project month 21) will be feasible.

- Those who challenge liberal democracy might lose electoral significance. As outlined above xxx. Instead, we consider it more likely – as the project foresees – that these tendencies disperse beyond clearly identifiable illiberal political agents, such as populist radical right parties, within the domestic context and transnationally.

- Dispersion of illiberal tendencies could entail that these become more difficult to grasp methodologically. This challenge actually represents one of the main objectives of this project and will be addressed through the extensive analysis of a) past and current developments in citizen attitudes and political rhetoric; b) variation in public discourse and in the electoral marketplace which considers voices from across the political spectrum both among the supply and the demand side; and c) variation in preferences for key norms of liberal democracy. All of these analyses are conducted across different temporal and geographic contexts and the respective measures will be based on existing and new survey questions alongside manual and automated content analyses in order to maximise validity and reliability of our measures.

- @Alexia: are there any open access or data management requirements/barriers?

- Data availability?

Requirement: Around EP elections  first prepare by longitudinal trends, afterwards learn lessons (both substantively and methodologically) and apply them in future implications

11:50:58 From Alexia Katsanidou To Everyone:

•	Low response rates due to survey fatigue could reduce the quality of our data. Our data will be collected online, so they are dependent on well functioning internet. If anything happens to internet access, we will be in trouble. 
	•	Hacker attacks could influence data availability that can influence the work of the WPs dealing with existing data (this has happened before!)

11:52:15 From Claes de Vreese To Everyone:

intricate x-ntl data collection - mitigation: good pollster

11:52:23 From Claes de Vreese To Everyone:

esr=replacement

11:52:31 From Claes de Vreese To Everyone:

kG leaving: Wouter takes over

11:52:53 From Sara Hobolt To Everyone:

Excellent suggestions!

11:54:04 From Claes de Vreese To Everyone:

we can mention data handling as a risk. Mitigation: very strict protocols following national AND eu regluations

## 2.2 Measures to maximise impact - Dissemination, exploitation and communication

In order to maximise its impact on XXX and XXX, the consortium has developed a rigorous plan for the involvement of relevant stakeholders alongside the effective dissemination and perpetual communication of DEMCORE’s results, on which we elaborate below. DEMCORE will dedicate an entire Work Package (WP9) to the co-creation, dissemination, exploitation and communication of our results. One of the very first tasks of this Work Package will be to provide a detailed Impact Plan in month 5 of the project, on the basis of which the exploitation, dissemination and communication of DEMCORE’s results can be implemented successfully. This Impact Plan will be regularly reviewed – and adapted if necessary – throughout the project’s lifespan in order to maximise DEMCORE’s impact. Importantly, while the Impact Plan’s measures are bundled and coordinated in the dedicated Work Package, the consortium partners in the substantial Work Packages all contribute to the overall exploitation, dissemination, and communication strategy throughout the project’s lifetime. In addition, DEMCORE’s advisory board is composed of both key policy experts and leading academics and has the crucial function to advise the consortium on the development and implementation of the Impact Plan alongside the possible identification of new outreach opportunities and possible adjustment of individual measures during the project.

### 2.2.1 Impact Plan

DEMCORE’s Impact Plan distinguishes between co-creation, dissemination and exploitation activities (section 2.2.2.1) and communication activities (section 2.2.2.2). These activities are targeted at different groups of stakeholders.

The purpose of the co-creation, dissemination and exploitation activities is two-fold: 1) to facilitate co-creation by involving stakeholders for a two-way knowledge exchange at critical junctures within the project; and 2) to facilitate dissemination by sharing and discussing DEMCORE’s results with stakeholders. To do so, DEMCORE’s consortium will reach out to, among others, the following stakeholders:

#### Policy-makers at the EU level and in EU member states

DEMCORE’s results will have direct implications for democratic governance in the EU. Therefore, we specifically target key decision-makers in EU politics, such as Věra Jourová (Vice-President of the European Commission, Portfolio: Values and Transparency), Members of two European Parliament Committees, namely LIBE (Civil Liberties, Justice and Home Affairs) and AFCO (Constitutional Affairs), and Members of the CIVEX Commission (Citizenship, Governance, Institutional & External Affairs) of the European Committee of the Regions.

While members of the European Committee of the Regions will be able to disseminate DEMCORE’s insights across European regions, we also target national parliamentarians within EU member states, particularly in those countries in which consortium partners are based.

#### National human rights institutions

National human rights institutions are crucial for supporting civil liberties and citizen rights. By offering advice to national policy-makers, they strive to promote and protect human rights and raise awareness in case of their violation. These institutions can be either reached locally through direct contacts (e.g., the Polish Ombudsman through SWPS) or via the European Network of National Human Rights Institutions.

#### NGOs and civil society organisations

Input by NGOs and civil societal organisations will be imperative for DEMCORE to accomplish its major objectives. Vice-versa, DEMCORE’s results will be of crucial interest for these stakeholders in order to ensure liberal democratic resilience across Europe in the long-run. Therefore, DEMCORE specifically targets pan-European NGOs and civil society organisations, such as Civil Society Europe, which offers European Coordination of Civil Society Organisations, Amnesty International, the European Centre for Press and Media Freedom, and the Civil Liberties Union for Europe (Liberties), which currently comprises 20 national civil liberties associations from across the EU, including Poland, Hungary, Ireland, France, the Netherlands, Slovakia and many others.

#### European journalists and professional journalism associations

Journalists not only present key stakeholders for the dissemination of DEMCORE’s results across Europe, but are also crucial for co-creation and exploitation given their watchdog role in liberal democracies. Therefore, DEMCORE targets pan-European associations, namely the European Federation of Journalists and European Data Journalism Network, and additionally relies on individual contacts from the personal networks of consortium members, that include journalists from the Financial Times, Pravda (Slovakia), Het Financieele Dagblad (Netherlands), and Berlingske Tidende (Denmark) to mention just a few. Additionally, DEMCORE’s key consortium partner, who is in charge of co-creation, exploitation, dissemination and communication (WP9) – SDU – works in close collaboration with the Media Research and Innovation Centre (MFI Centre) at SDU. The MFI Centre which has extensive experience in producing materials for the media industry. Likewise, SDU also has an extensive network of other journalism schools, including both universities and vocational training institutions.

#### Scientific Community

DEMCORE’s results not only produce novel insights, but also innovative operationalisations of attitudes, preferences and rhetoric towards liberal democratic norms and values. They will therefore also be highly relevant for the scientific community. We will actively exchange with scholars from a wide range of subdisciplines within political science (comparative politics, European studies, political behaviour), psychology (political psychology, social psychology) social science methodology and communication science (political communication, journalism, persuasive communication, political marketing) and more widely with scholars of sociology, history, law, philosophy, and political economy with a regional focus on Europe/the EU.

The purpose of the communication activities is to raise public interest and awareness. As DEMCORE’s results will have significant implications for European citizens, it is imperative to reach out to stakeholders beyond the ones identified above. To do so, DEMCORE’s communication activities are aimed at fostering the project’s visibility and enhancing the public debate on the challenges of European liberal democracy. Here, stakeholders comprise, firstly, the media (i.e. journalists in Brussels and across the EU) through which European citizens will be reached indirectly. Secondly, we also target European citizens, and particularly young citizens, directly at both a local and a transnational level. We explain in Section 2.2.2.2 how DEMCORE will accomplish this.

### 2.2.1.1 Co-creation, dissemination and exploitation activities

DEMCORE’s consortium will initiate various co-creation, dissemination and exploitation activities. We list the eight most important ones below.

Type of activity: Online educational package for journalists. The purpose of this package is to raise awareness among journalists for the challenges to liberal democracy in Europe. It will have an interactive toolkit format in which journalists are presented with editorial challenges and choices and provided with feedback for different scenarios. The toolkit will include short reflexive contributions by key news journalists and news executives. The toolkit will be available ahead of the 2024 EP election. Type of strategy: Co-creation, dissemination and exploitation Targeted stakeholders: Journalists and professional journalism associations Measures to verify impact: Number of users, their feedback gathered by a user evaluation survey

Type of activity: Three stakeholder workshops in Brussels. DEMCORE plans each one stakeholder workshop at critical junctures of the project, namely (1) prior to the data collection in WP5 and WP6 and ahead of the 2024 EP election in order to facilitate co-creation in the study of current challenges to liberal democracy, (2) during the planning phase of WP7 in order to facilitate co-creation in the assessment of causal mechanisms that likely underpin preferences for ‘illiberal’ democracy, and (3) during the planning phase of WP8 in order to facilitate co-creation in the development of communicative strategies to counter illiberal messages. Type of strategy: Co-creation Targeted stakeholders: Policy-makers, NGOs and civil society organisations, and journalists based in Brussels Measures to verify impact: Participant profiles, their qualitative input and their expressions of interests to remain involved with DEMCORE during the remaining course of the project.

Type of activity: Two-Day Academic-Stakeholder Conference in 2025. This conference is to take place in Amsterdam one year after the EP election in May 2024. Its purpose is to invite external academics and interested stakeholders to a) share and discuss key results related to current challenges of liberal democracy (WP5 & WP6), b) receive input on DEMCORE’s further research plans, and c) learn more about related research projects. In the evening of Day 1, a public debate will be organised in the centre of Amsterdam (see ‘public debates in EU member states’). Type of strategy: Co-creation, dissemination, exploitation and communication Targeted stakeholders: Academics, national and regional policy-makers, journalists, and representatives from civil society organisations, local citizens Measures to verify impact: Number of participants, their feedback after the conference and their expressions of interests to learn more about and/or further engage with DEMCORE during the remaining course of the project, social media impact (see ‘Twitter account’ below).

Type of activity: Public debates in EU member states. DEMCORE’s consortium members will organise several public debates between academics and national/regional stakeholders to disseminate and openly discuss DEMCORE’s key findings and their implications with citizens and interested stakeholders. Prime locations include Amsterdam, Cologne, Copenhagen, Milan, Paris, and Warsaw. Type of strategy: Dissemination, exploitation and communication Targeted stakeholders: National and regional policy-makers, journalists, and representatives from civil society organisations, local citizens Measures to verify impact: Number of participants, their feedback after the public debate and their expressions of interests to learn more about and/or further engage with DEMCORE during the remaining course of the project, social media impact (see ‘Twitter account’ below).

Type of activity: Three flagship/spin-off reports. DEMCORE will publish three flagship reports that cut across the whole project. The first report will highlight the long-term trends in public support for liberal democracy in the past, present, and future. The second report will zoom in on the challenges related to the contestation of liberal democratic ideals in the interplay of political elites and European citizens. The third report will provide recommendations on how to address ‘illiberal democratic’ preferences and counter illiberal appeals. Type of strategy: Dissemination, exploitation and communication Targeted stakeholders: EU-level, national and regional policy-makers, NGOs and civil society organisations Measures to verify impact:

Type of activity: Specific policy reports. DEMCORE will publish a series of reports that are dedicated to specific findings in the individual Work Packages on the EU website (see deliverables in WPs 2-8). Type of strategy: Dissemination, exploitation and communication Targeted stakeholders: EU-level, national and regional policy-makers, NGOs and civil society organisations Measures to verify impact:

Type of activity: Liberal democracy knowledge clips. DEMCORE will create a series of short knowledge clips about developments in liberal democracy and journalism. The clips will be made in collaboration with the MFI Center at SDU, which has extensive experience in making media industry-oriented materials and is well centred for (inter)national networks. Type of strategy: Dissemination, exploitation and communication Targeted stakeholders: Journalism students, journalists and professional journalism associations Measures to verify impact: Uptake and feedback by journalism schools within SDU’s network

Type of activity: Heatmaps (for sharing). DEMCORE will produce a series of so-called heatmaps to illustrate the level and geographical distribution of current challenges to liberal democracy in a data visualisation that is facilitating for the media and policy-makers to engage with. Several heatmaps are produced tapping XXX Type of strategy: Dissemination and exploitation Targeted stakeholders: Journalists, policy-makers, NGOs and civil society organisations (Europe-wide) Measures to verify impact: Uptake by journalists in their publications and by other stakeholders (e.g., on their websites).

#### Additional exchange with the scientific community

DEMCORE’s consortium members will regularly present their findings and organise panels at international conferences (e.g. APSA, EPSA, ECPR, EUSA, ICA) and in invited public or academic talks that take place virtually (e.g., academic podcasts) or physically in various locations. Apart from the research exchange at the conference mentioned above, another aim is to collect papers at this conference for the publication of a joint Special Issue in a major academic journal (e.g. European Union Politics; Journal of European Public Policy).

### 2.2.1.2 Communication activities

DEMCORE’s communication activities are aimed at fostering the project’s visibility and enhancing the public debate on the challenges of European liberal democracy. Thus, in addition to reaching out to journalists and civil society organisations for dissemination and exploitation, DEMCORE has the following direct means of communication:

Type of activity: Website. DEMCORE will build a project website at the beginning of the project and maintain it throughout by adding new information on research outputs, events and other project activities by the Consortium members. It will be professionally designed, visually appealing and easy to navigate also for a non-specialist audience, with some interactive elements (see ‘Heatmaps’) alongside a Twitter feed (see ‘Twitter account’) and blogposts (see ‘blogposts’) in relation to our public reports delivered to the European Commission. Type of strategy: Communication and dissemination Targeted stakeholders: Specific stakeholders identified above + media + public at large Measures to verify impact: Website analytics, including page views, clicks on links.

Type of activity: Heatmaps (website). The series of heatmaps that DEMCORE will produce for journalists, policy-makers and civil society organisations (see ‘heatmaps (for sharing)’ above) will also be made available as an interactive tool on our website. Type of strategy: Communication and dissemination Targeted stakeholders: Specific stakeholders identified above + media + public at large Measures to verify impact: Website analytics, including page views, clicks on links.

Type of activity: Twitter account. DEMCORE will open a Twitter account at the beginning of the project and manage it throughout by regularly tweeting about new information on research outputs, events and other project activities by the Consortium members and by regularly provide links to the project website. A dedicated social media manager will ensure an active and keen engagement with the public on Twitter. Type of strategy: Communication and dissemination Targeted stakeholders: Specific stakeholders identified above + media + public at large Measures to verify impact: Growth of followers over time; interaction with tweets (likes, retweets, responses).

Type of activity: Blogposts. Upon publication of every public report, DEMCORE will publish a blogpost for a non-specialist audience on its website. Additional blogposts that are connected to the scientific publications of DEMOCORE’s members will be published on the websites of renowned Blogs (e.g., LSE EUROPP, Monkey Cage, ECPR’s the Loop) – also beyond the lifespan of the project. Type of strategy: Communication and dissemination Targeted stakeholders: Specific stakeholders identified above + media + public at large Measures to verify impact: Website analytics, including page views, clicks on links.

### 2.2.2 Public disclosure of research data

When it comes to the disclosure of research data the consortium is guided by the principle, as open as possible as restricted as necessary. We will therefore make sure that an anonymized and data protection conform version of our data will be easily accessible through publicly funded data archive, to ensure quick and easy access for as many interested stakeholders as possible.

### 2.2.3 Open access publications

DEMCORE’s scientific publications, including journal articles, special issues and – if possible – books and book chapters, will be made freely accessible online through either Gold or Green Open Access. To associated costs have been accounted for in DEMCORE’s budget.

### 2.2.4 Strategy for the management of intellectual property

The Consortium Agreement will explicate the handling of intellectual property rights (IPR). In all events, three guiding principles will be followed:

- Background (existing knowledge): unless expressly agreed otherwise, each partner grants to all other partners in the consortium access rights to background disclosed for the execution of the project.

- Foreground (generated knowledge): any foreground generated during the project will be considered the result of joint effort by the partners collaborating in the specific Work Package. As such, it shall be jointly owned, entitling all WP partners to exploit it for non-commercial purposes such as academic research, training and teaching activities. Commercial exploitation is only possible when  the joint owners give prior consent and agree on fair and reasonable compensation.

- For the use of data owned by external parties, an agreement will be drafted for each secondary dataset processed by the consortium. This agreement will detail how ownership and exploitation will be dealt with and specify any restrictions on processing techniques that may not be used.

## 2.3 Summary

KEY ELEMENT OF THE IMPACT SECTION

SPECIFIC NEEDS

What are the specific needs that triggered this project? 1) We require an in-depth understanding of the long-term trends of public legitimacy among European citizens and political rhetoric of political parties towards liberal democratic norms and values and the extent to which these are shaped by contextual factors and institutions across Europe. 2) We require a comprehensive account of the challenges that liberal democracy in Europe is currently facing – both in terms of contestation of ideals in public discourse and in the electoral marketplace – and what role historic, political and economic contexts play for this contestation. 3) We require a robust vision for the future of liberal democracy in Europe, particularly for institutions of democratic governance, across various domestic contexts in order to counter illiberal democrats and ensure liberal democratic resilience in the long run.

D & E & C MEASURES

What dissemination, exploitation and communication measures will you apply to the results? Exploitation: Providing “heat maps” to data journalists at major European newspapers (e.g., The Guardian, de Volkskrant, Süddeutsche Zeitung) and new media for visualization purposes; public reports for policy-makers and representatives of pan-European NGOs Dissemination towards the scientific community: conference presentations and dedicated panels; open access scientific publications; an academic workshop; a Special Issue in a major academic journal; make data openly available for scientific analyses, active Twitter account, project website Communication towards citizens: Heat maps” ahead of the 2024 European Parliament elections; public events in major European cities; DEMCORE podcast series, active Twitter account, project website

EXPECTED RESULTS

What do you expect to generate by the end of the project? Thorough and pioneering knowledge of: - the extent to which citizens’ attitudes towards liberal democracy have evolved over different generations across Europe and those factors (historic, political and economic contexts, external events) that explain generational differences. - the way political parties have defended liberal democratic norms and values over the past 40 years, how this has changed during recent European crises, whether there are indications of transnational convergence, and the reciprocal relationship between institutional change and partisan rhetoric. - the dynamics of public discourse with respect to the contestation of different ideals and perceptions of (liberal) democracy against the backdrop of varying domestic contexts and experiences and their potential to create tensions between challengers and defenders of liberal democracy in European society. - the function of European elections in offering a marketplace of supply and demand with respect to potentially contrasting visions of (liberal) democracy in Europe as well as under what conditions, among whom, and where in Europe challengers of liberal democracy are successful or not among voters. - the structure of European citizens’ preferences for liberal democratic norms and values beyond attitudes and behaviour, the extent to which these are shaped by institutional and political mechanisms and how these counter illiberal democrats in Europe. - the implications of past and current developments that affect European citizens and political parties and how they inform the future of liberal democracy and ensure resilience against illiberal tendencies.

TARGET GROUPS

Who will use or further up-take the results of the project? Who will benefit from the results of the project? Policy-makers at EU level: - Věra Jourová (Vice-President of the European Commission, Portfolio: Values and Transparency) - Members of two European Parliament Committees, namely LIBE (Civil Liberties, Justice and Home Affairs) and AFCO (Constitutional Affairs) - Members of the CIVEX Commission (Citizenship, Governance, Institutional & External Affairs) of the European Committee of the Regions Pan-European NGOs: - Civil Society Europe, the European Coordination for Civil Society Organisations - European Schoolnet - European Centre for Press and Media Freedom Journalists (through personal networks) and journalistic associations, namely the European Federation of Journalists and European Data Journalism Network European citizens (indirectly or locally) Scientific community (specifically European politics and communication; and more widely to scholars of sociology, history, law, philosophy, and political economy with a regional focus on Europe/the EU)

OUTCOMES

What change do you expect to see after successful dissemination and exploitation of project results to the target group(s)? Policy-makers at EU level: - Understanding patterns of citizen attitudes, behaviour and preferences for key liberal democratic norms and values across generations and different political and economic contexts - Developing susceptibility towards illiberal rhetoric in public discourse and during election campaigns and its consequences across Europe - Recognition of the relationship between the supply-demand-interplay and historic, institutional, political and economic contexts for the development of European liberal democracy Pan-European NGOs and citizens: - Awareness of conditions and communicative actors that foster illiberal developments, of the variety of visions of liberal democracy (among citizens and political parties) and of ways to counter illiberal tendencies Journalists and journalistic associations: - Data uptake to perform watchdog function Scientific community - Acknowledgement of [our core theoretical argument] - Use of our concepts, operationalisations and scientific data to further investigate the phenomenon in future research

IMPACTS

What are the expected wider scientific, economic and societal effects of the project contributing to the expected impacts outlined in the respective destination in the work programme? Scientific: - A new conceptual framework that provides an integrated account of the support for, contestation of and external challenges to liberal democracy in Europe - New operationalisations of illiberal rhetoric, party communication and behaviour, citizen attitudes, behaviour and preferences - New data that complement existing data sources (e.g., Freedom House, Varieties of Democracy) and that can henceforth be used in future scientific research and will be kept alive within the MEDem Infrastructure Economic (or technological) – perhaps anything political instead??? Societal: Awareness of the support for, contestation of and external challenges to liberal democracy in Europe alongside a wide range of tools to counter illiberal democrats and to ensure democratic resilience

## 3. QUALITY AND EFFICIENCY OF THE IMPLEMENTATION

## 3.1 Work plan and resources

Insert here text for your proposal: just briefly describe the set-up, we must fill this and the following page in between the two landscape pages

### Figure 3.1a: Relationship between work packages

### Table 3.1a: List of work packages

| Work package No | Work Package Title | Lead Participant No | Lead Participant Short Name | Person-Months | Start Month | End month |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Management | 1 | UVA |  | 1 | 48 |
| 2 | Connecting time and space: The context of liberal democracy | 5 | GESIS |  | 1 | 36 |
| 3 | Citizen attitudes towards liberal democracy | 1 | UVA |  | 1 | 30 |
| 4 | Conceptions of liberal democracy by political parties | 2 | UCLB |  | 1 | 24 |
| 5 | Contestation of ideals in the public discourse | 4 | UNCL |  | 17 | 42 |
| 6 | Electoral marketplace for different visions of liberal democracy | 7 | LSE |  | 1 | 48 |
| 7 | Understanding preferences for “illiberal democracy” | 3 | SWPS |  |  | 48 |
| 8 | Ensuring liberal democratic resilience | 8 | SCPO |  |  | 48 |
| 9 | Co-creation, exploitation, dissemination and communication | 9 | SDU |  | 1 | 48 |
| Total person-months |  |  |  |  |  |  |

### Figure 3.1b: Timing of the different work packages and their components

## Table 3.1b: Work package description

#### WP1 – Management (lead: UVA)

| Work package number | 1 | Lead beneficiary |  |  |  |  |  | UVA |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Management |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO | CEPS |
| Person months per participant: | 19.2 |  |  |  | 12 |  |  |  |  |
| Start month | 1 | End month |  |  |  |  |  | 48 |  |

Objectives This Work Package is non-substantive supportive WP facilitating the work that is done in the WPs 2-9. It does so by ensuring an effective administrative and financial implementation of DEMCORE; monitoring progress; designing and installing procedures to initiate and monitor compliance with high-quality procedures for data management, research ethics and quality assurance; mitigating risks and consulting on intellectual property rights (IPR) and legal issues; and by facilitating optimal liaison both among project partners and with the Research Executive Agency.

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 1.1. Administrative and financial management (lead UVA; partners: none; duration: months 1-48) This task concerns proper (periodic) reporting on the administrative and financial operations of the project, and the timely delivery of deliverables. This will be achieved through detailed planning, frequent communication with all consortium partners, and close liaison with the Research Executive Agency. Task 1.2. Initiate and monitor quality assurance (lead UVA; partners: none; duration: months 1-48) This task involves the installation of consortium-wide quality assessment procedures in the form of an internal review to ensure that the implementation of the project and its outcomes is of high quality. The respective measures will be subject to continuous assessment and will be modified when necessary. Task 1.3. Data management (lead GESIS; partners: all partners who collect data, namely UVA, UCLB, SWPS, UNCL, SDU, LSE, SCPO; duration: months 1-48) This task concerns comprehensive and effective data management procedures as described in section 1.2.9. The main output of this task will be fully checked and labelled datasets, ready for analysis in SPSS, Stata, and R readable formats, for data collected in WP3, WP4, WP5, WP6, WP7, and WP8 as part of DEMCORE’s commitment to open science practices (see section 1.2.8). Task 1.4. Project coordination (lead UVA; partners: all; duration: months 1-48) This task involves the monitoring of research tasks and activities in close cooperation with all Work Package leaders and the provision of prompt and effective assistance to consortium partners in order to ensure that these tasks and activities – and thus the project as a whole – are implemented successfully. This task also includes the initiation of the tenders for the research data collection in WP6, WP7, and WP8, alongside the organisation of consortium meetings, which are carefully timed ahead of major milestones, and the meetings with the advisory board(s).

Deliverables (brief description and month of delivery) D1.1. Quality assurance plan (month of delivery: 1) D1.2. Data management plan (month of delivery: 4) D1.3. Data checking report (month of delivery: X) D1.4. Fully documented dataset(s) in public release (month of delivery: X) D1.5. Minutes consortium meeting 1 (month of delivery: 1) D1.6. Minutes consortium meeting 2 (month of delivery: 9) D1.7. Minutes consortium meeting 3 (month of delivery: 18) D1.8. Minutes consortium meeting 4 (month of delivery: 26) D1.9. Minutes consortium meeting 5 (month of delivery: 34) D1.10. Minutes consortium meeting 6 (month of delivery: 46)

#### WP2 – Connecting time and space: The context of liberal democracy (lead: GESIS)

| Work package number | 2 | Lead beneficiary |  |  |  |  |  |  | GESIS |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Connecting time and space: The context of liberal democracy |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO |  | CEPS |
| Person months per participant: |  |  |  |  |  |  |  |  |  |  |
| Start month | 1 | End month |  |  |  |  |  |  | 36 |  |  |

Objectives WP2 is a work package which frames and feeds into the analyses conducted in the substantive WPs 3-8. Its objective is to develop an analytical framework of the relevant historic, political and economic contexts to evaluate liberal democracies and their legitimacy. It identifies relevant indicators for each of these contexts, collects and harmonizes relevant data across time (from 1990 onwards) and space (from all EU member states), and then relates these indicators to the major political and economic challenges of the past three decades. In doing so, WP2 is targeted at analysing, firstly, how institutional and political mechanisms built into European liberal democracies have functioned as limits or as responses to democratic backsliding in governance and illiberal developments in the interaction of demand for and supply of liberal democracy. Secondly, WP2e examines the resistance of liberal democratic institutions to internal challenges within countries, such as demographic shifts and changes in the information environment, and external challenges to liberal democracy, including the Great Recession, the changing geo-political world order, climate change and the Covid-19 pandemic. More specifically, WP2 provide answers to the following questions: - How have liberal democratic institutions developed over time? Have the changes in the structure of modern societies and the internal and external challenges of the past decades lead to resilience and potential for adaptation for liberal democratic institutions? Or do they signify the beginning of the end? - What indicators are best to capture a) the contexts of the developments and challenges of liberal democracy and b) the mechanisms that show complacency or erosion of liberal democracy as a response to these developments and challenges. Which are the relevant contexts at the EU and national level that influence the interaction of demand for and supply of liberal democracy?

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 2.1. Providing analytical framework (lead GESIS; partners: all; duration: months 1-12) This task will provide the analytical framework of the way historic, political and economic contexts may have presented challenges to the evolvement of liberal democracies over the past decades across Europe. The goal of this task is to identify indicators for Tasks 2.2 and 2.3. It will also embed the work in WP3 and WP4 in a larger context, act as the basis for the methodological work in the whole project, and guide the case selection in WP7 and WP8. Task 2.2. Building a database of indicators and instruments (lead GESIS; partners: none; duration: months 10-36) In this task we will collect, structure and harmonize indicators and instruments that characterize liberal democracy across time and space within Europe. In this work we will rely heavily on already tested measures of political and societal processes (e.g., XXX), and to some extent also on existing datasets, such as V-Dem. Task 2.3. Building a database of the context and conditions in which political institutions operate (lead GESIS; partners: ???; duration: months 10-36) In this task we will collect, structure and harmonize economic and political indicators at the national level to depict context. We will draw heavily on existing sources of context data such as official statistics, economic and gender equality measures, and political science data collection projects. An important part of our proposed work will also be to collect and harmonize subnational data on deindustrialization, automation, and the shift to knowledge-intensive sectors as well as data on the impacts of these processes on unemployment, wage levels, unionization, and skill levels. We will also collect data on the impact of the various crises on national and subnational level: the Great recession, migration, the covid-19 pandemic and climate change. Task 2.4 Improving the understanding of liberal democracy (lead: GESIS, partners: ???; duration: months 18-36) In this task we will use the collected data to improve the understanding of democratic performance across time and within the economic and social context as provided by the various experienced crises and societal changes. Using the key facts at hand on economic and political performance and equality in economic and gender terms, we will answer major questions about the development of liberal democratic institutions, and we will demystify public discourse and test the resilience and adaptation hypotheses and test the thesis of the end of liberal democracy. Task 2.5 Understanding how EU institutions promote liberal democracy and respond to democratic backsliding in EU member states (lead: CEPS, partners: ???; duration: months 18-36) In this task – through document analysis – we will describe the current relevant political context at the EU level that influences the interaction of demand for and supply of liberal democracy. We will take stock of the way the EC, the EP and the Council have promoted liberal democracy since the coming into force of the Maastricht Treaty and how they have responded thus far to democratic backsliding in its member states. Aspects under investigation will be the legal groundwork for those measures; the measures that have been taken; the effects of those; as well as other, potentially unused, ones. It will further be assessed whether and what kind of updates have the EU institutions undergone to bolster liberal democracy due to the Conference on the Future of Europe.

Deliverables (brief description and month of delivery) D2.1. Conceptual roadmap for entire project (lead: GESIS; month of delivery: 9) Please elaborate a bit here of what this roadmap could be and how it is of any use to the other WPs/analyses, as suggested in its title D2.2. Report on the analytical framework (lead: GESIS; month of delivery: 12) Please elaborate a bit of what this deliverable will look like D2.3. Database on political indicators/instruments for use in other WPs (lead: GESIS; month of delivery: 36) The final database will be structured in such a way that it will provide linking opportunities for all other data collected or used within the project (first internal release: month 18). D2.4. Database on economic and social conditions for use in other WPs (lead: GESIS; month of delivery: 36) The final database will be structured in such a way that it will provide linking opportunities for all other data collected or used within the project (first internal release: month 18). D2.5 Report on the development of liberal democracy across time (lead: GESIS; month of delivery: 36) Xxxx D2.6 Report on the response of EU institutions (lead: CEPS; month of delivery: 36)

#### WP3 – Citizen attitudes towards democracy (Lead: Wouter van der Brug)

| Work package number | 3 | Lead beneficiary |  |  |  |  |  | UVA |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Citizen attitudes towards liberal democracy |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO | CEPS |
| Person months per participant: |  |  |  |  |  |  |  |  |  |
| Start month | 1 | End month |  |  |  |  |  | 30 |  |

Objectives WP3 runs the longitudinal study of citizen attitudes towards liberal democracy. It does so on the basis of European survey data and focuses on the EU-27 (PLUS UK??). Although existing research does mostly not focus on these elements of liberal democracy, past surveys do include comprehensive information about highly related attitudes, such as tolerance towards minorities, support for female emancipation, and authoritarianism. In WP3, we therefore make an inventory of the available European data on these relevant attitudes from the 1990s onwards and, in as much as possible, harmonize and pool them. The objectives of WP3 are threefold: - Identify and combine all available European survey data from data archives that measure support for liberal democracy and highly related attitudes since 1990. - Analyse and compare – in collaboration with WP2 and WP4 – long-term trends in support for liberal democratic norms and values across contexts, and relate these to partisan rhetoric and the impacts of recent events, in particular the European debt crisis starting in 2009, the so-called refugee crisis of 2015 and the Covid-19 pandemic. - Analyse individual level correlates of support for liberal democracy and related attitudes, with a particular focus on generations over time.

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 3.1. Building a dataset of survey data measuring public support for liberal democracy (lead UVA; partners: SWPS; duration: months 1-12) This tasks involves a) the identification of relevant data, b) their collection, and c) their integration into one cohesive dataset. The latter requires harmonisation of file formats, variable names and operationalisations. Task 3.2. Linking individual survey data contextual data (WP2) and partisan rhetoric (WP4) (lead UVA; partners: GESIS, UCLB; duration: months 13-15) In order to understand long-term trends in public support for liberal democracy, this task involves linking the individual survey data from task 3.1 with data on political indicators/instruments (D2.2) and economic conditions (D2.3) and party positions towards liberal democracy provided (D4.3, see WP4). Task 3.3. Analyse the correlates of support for liberal democracy (lead UVA; partners: UCLB, UNCL, LSE, SDU; duration: months 16-30) This tasks concerns the analysis of individual-level support for liberal democracy across generations and across the EU, measured against the backdrop of changes in party positions and political and economic contexts. This is a challenging task, but crucial for understanding XXX. This multi-partner task is relies on interaction with and input from WP2, WP4 and WP5.

Deliverables (brief description and month of delivery) D3.1. Report on the integrated survey dataset (lead: UVA; month of delivery: 17) This report relates to tasks 3.1 and 3.2 and includes a description of the data building procedure and a user guide. The integrated dataset will be added to DEMCORE’s data repository that is managed by GESIS within 6 months after the end of the project. D3.2. Report on the main findings and their implications (lead: UVA; month of delivery: 30) The report will summarise the main findings of the analyses conducted in task 3.3 and their implications for measuring and describing public support for liberal democracy.

#### WP4 – Conceptions of liberal democracy by political parties (lead: Catherine)

| Work package number | 4 | Lead beneficiary |  |  |  |  |  | UCLB |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Conceptions of liberal democracy by political parties |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO | CEPS |
| Person months per participant: | X | X |  |  | X | X | X |  | X |
| Start month | 1 | End month |  |  |  |  |  | 24 |  |

Objectives WP4 conducts a thorough and pioneering longitudinal analysis of party positions towards liberal democratic norms and values. Its objectives are fourfold: - Examine how the rhetoric on, and challenges to, liberal democracy in general and gender equality in particular, by European parties has developed over time (2000-2024) and across EU member states. - Through the integration of data collected in WP2 (contexts and institutions) and WP3 (citizen attitudes), we will compare the long-term trends in elite rhetoric and public legitimacy, and explore the impact of major political and economic challenges over the past decades. - Create a heat map of health of liberal democracy in Europe today that will highlight both party political challenges (WP4), public support for liberal democracy (WP6) and the state of liberal democratic institutions (WP2). - Create a heat map of health of gender equality in Europe today that will highlight both party political rhetoric about gender equality (WP4) and public support for gender equality (WP6). To meet these objectives, WP4 builds an original dataset, combining hand-coding and state-of-the-art computational text analysis, with the positions of political parties on core liberal democratic norms and values, using raw national and European parliamentary manifestos and political speeches (from ParlSpeech and EUSpeech corpora). This will be integrated with the citizen survey data and economic and political events data to allow for a longitudinal analysis of the long-term trends in the functioning of liberal democratic norms and the state of equality. Finally, a more fine-grained analysis of current party positions on liberal democracies, combining text analysis with expert data will allow us to create heat maps of current challenges to liberal democracy and gender equality across the continent on different dimensions.

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 4.1. Collecting raw materials for analysing partisan rhetoric (lead: UCLB; partners: none; duration: months 1-2) This tasks involves collecting the raw material, i.e. party manifestos of national and European parties and political speeches building on ParlSpeech and EUSpeech corpora data. The data will be transformed into computer readable format. Task 4.2. Development of coding schemes of (il)liberal rhetoric and gender threats (lead: UCLB; partners: SCPO; duration: months 3-12) This tasks concerns the creation of a hand-coding coding scheme and the use of computational analysis to develop a computerized coding scheme. Task 4.3. Measuring party positions towards liberal democracy and gender equality in party communication over time (lead: UCLB; partners: GESIS, SWPS; duration: months 12-18) This tasks involves the coding of party positions towards liberal democracy and gender equality since 2000 up to and including 2024 across the EU (from task 4.1?). This will be done through a mix of hand-coding and automated procedures to ensure validity and reliability of the coded positions. Task 4.4. Time-series analysis: the relationship between partisan rhetoric, public legitimacy and institutional change in liberal democracies (lead: UCLB; partners: UVA, GESIS, SDU; duration: months 12-18) This tasks concerns linking the dataset on party positions towards liberal democracy and gender equality over time and across countries to public opinion data (D3X) and context data (D2.X), followed by a longitudinal analysis of changes in party positions across the EU against the backdrop of changes in individual-level support for liberal democracy (WP3??) and political and economic contexts (WP2??). Task 4.5. Heatmaps of health of liberal democracy and gender equality (lead: UCLB; partners: LSE, CEPS; duration: months 18-24) This task involves the building of datasets (‘heatmap’) of party positions towards a) liberal democracy and b) gender equality collected from the 2024 EP election campaigns

Deliverables (brief description and month of delivery) D4.1. Report on the measures on party positions towards liberal democracy (lead: UCLB; month of delivery: 12) This report relates to task 4.3 and also includes a description of the coding scheme. It will be added to DEMCORE’s data repository that is managed by GESIS. D4.2. Report on the measures on party positions towards gender equality (lead: UCLB; month of delivery: 12) This report relates to task 4.3 and includes a description of the coding scheme. It will be added to DEMCORE’s data repository that is managed by GESIS. D4.3. Report on the longitudinal development of party positions towards liberal democracy (lead: UCLB; month of delivery: 18) D4.4. Report on the longitudinal development of party positions towards gender equality (lead: UCLB; month of delivery: 18) D4.5. Parts A and B of the heat maps visualising challenges to liberal democracy and gender equality: party positions ((lead: UCLB; month of delivery: 24) These parts of the heat map on party positions in 2024 complements the heat map of public support (D6.3). Combined, the heat map illustrates the variation and geographical distribution of voter attitudes and party positions towards liberal democracy and gender equality in a data visualisation It will be published on DEMCORE’s website and distributed among the project’s stakeholders.

#### WP5 - Contestation of ideals in the public discourse (lead: UNCL)

| Work package number | 5 | Lead beneficiary |  |  |  |  |  | UNCL |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Contestation of ideals in the public discourse |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO | CEPS |
| Person months per participant: |  |  |  |  |  |  |  |  |  |
| Start month | 17 | End month |  |  |  |  |  | 42 |  |

Objectives WP5 studies how illiberal appeals spread across on social media and what reaction they trigger from the public. It examines the dynamic between the supply side (political actors) and the demand side (citizens) when it comes to the proliferation of (il)liberal views in the transnational setting of the EU. In particular, it focuses on how the discourse of political elites shapes and is shaped by citizens’ attitudes towards liberal democracy. WP5 has the following objectives: - Identify who are the main challengers and the supporters of liberal democratic norms and values. - Assess the extent to which these actors and their communication strategies are influential on social media. - Given the potential of social media to provide exposure to counter-attitudinal views (Barberá et al. 2015; Guess 2021), examine the tension between these discourses and how this tension shape attitudes towards liberal democracy among both the public and elites. - Analyse the diffusion of (il)liberal democratic discourse across time and space and under what conditions this diffusion can be countered.

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 5.1. Development of codebook (lead UNCL; partners: UVA, SDU, UCLB; duration: months 17-21) Based on the analytical framework developed in WP2, input from WP3 and in co-ordination with Task 4.2, this task develops a codebook to code (il)liberal discourse on social media. It also includes the compiling of a list of social media profiles on Facebook and Twitter of candidates running in the 2024 EP election to be used for the data collection alongside meta-information (e.g. party affiliation, party position, gender). Task 5.2. Data collection (lead UNCL; partners: none; duration: months 21-22) Based on the list of social media profiles we will collect via the Twitter Streaming API: tweets by politicians, replies to these tweets, and all tweets which mention candidates during the election campaigns. Using CrowdTangle for Facebook we will also collect: politicians’ public posts alongside the number of likes, comments and shares for the same four-week-period before the EP election. Task 5.3. Social media analysis of the content generated by political actors (lead UNCL; partners: SDU, UVA ???; duration: months 23-33) This task will analyse patterns of (il)liberal democratic discourse initiated by political elites and the public response. Since similar data were collected at the time of the 2019 EP election by the Work Package leader (Fazekas et al. 2021), we will be able to compare the diachronic evolution of (il)liberal discourse assess the extent to which if illiberal democratic discourse has a growing appeal among elites and the public. Task 5.4. Identify successful communicational strategies that promote illiberal appeals (lead SDU; partners: UNCL, UVA; duration: months 33-38) This task will analyse how (il)liberal democratic appeals are promoted in terms of communication style, the use of emotive rhetoric and their association with political issues during the 2024 EP election campaigns in order to assess the success of such appeals. Taking advantage of the data availability from 2019, we will also be able to assess the degree to which any changes in illiberal democratic appeals contribute to their popularity. Task 5.5. The diffusion of illiberal democratic appeal idea across Europe (lead UVA; partners: UNCL ???; duration: months 37-42) In this task we will assess the extent to which and under what conditions (il)liberal democratic appeals on social media travel across European countries (or not). This allows us to evaluate if political elites make use of a common playbook or if they contextualize these messages according to a given countries’ circumstances.

Deliverables (brief description and month of delivery) D5.1. Codebook for the coding of social media content (lead: UNCL; month of delivery: 22) The codebook is generated in task 5.1 and will also be used in the remaining tasks. It will be added to DEMCORE’s data repository that is managed by GESIS. D5.2. Dataset of (il)liberal social media communication by political elites (lead: UNCL; month of delivery: 29) The dataset will be developed based on Task 5.2 and consists of the content coding of the communication by political elites on Facebook and Twitter will be added to DEMCORE’s data repository that is managed by GESIS. D5.3. Report on the spread of illiberal democratic discourse on social media((lead: UNCL; month of delivery: 33) This report will summarise the main findings and their implications of the empirical analysis of task 5.3. D5.4. Report on the promotion of illiberal democratic appeals and their effects (lead: SDU; month of delivery: 38) This report will summarise the findings and their implications of the empirical analysis performed in task 5.4. D5.5. Report on the diffusion of illiberal democratic appeals across EU member states (lead: UVA; month of delivery: 42) The report will summarise main findings of the empirical analysis of task 5.5 and their implications.

#### WP6 - Electoral marketplace for different visions of liberal democracy (lead: LSE/Sara)

| Work package number | 6 | Lead beneficiary |  |  |  |  |  | LSE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Electoral marketplace for different visions of liberal democracy |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO | CEPS |
| Person months per participant: | X | X |  | X | X |  | X |  | X |
| Start month |  | End month |  |  |  |  |  |  |  |

Objectives In order to understand the extent to which liberal democracy is anchored in people’s voting choices, this Work Package aims to answer the following questions: When and why do voters elect politicians with ‘illiberal’ platforms? What role do voters’ own attitudes towards norms and values of liberal democracy play in their voting behaviour? What makes some parties that challenge liberal democratic norms and values appealing? To address these questions, this Work Package will design and conduct a post-election voter survey in the immediate aftermath of the 2024 EP election across all EU member states. The design builds on key questions from the long-term trends in attitudes (WP3) to capture the tension between liberal ideals and other salient interests to citizens. We also integrate the coding of party positions in WP4 and the contextual data in WP2 to build a multilevel model of how individual, party- and country-level factors shape the success (or failure) of illiberal democratic parties in the electoral arena. By integrating voter and party level data in an electoral context, we can explore the importance of both demand (voter) and supply (party) factors. In addition, by collecting new voter data we delve deeper into the political gender gaps that have been shown to characterise support for more illiberal party platforms of radical right political parties. In close collaboration with impact activities of WP9, the 2024 EP election provides a unique arena to communicate with policy-makers and other stakeholders about how to reduce the appeal of both new and sustained attacks on liberal democracy (also in collaboration with WP8). This Work Package will also analyse the survey data on public support for liberal democracy to contribute to the heat map of challenges to liberal democracy to illustrate the level and geographical distribution of current challenges in a data visualisation that it facilitating for the media and policy-makers to engage with. Specially, the objectives of this Work Package are: - Examine which voters are more likely to elect politicians with ‘illiberal’ platforms by combining existing voter data (WP3), collecting novel voter data and party data (WP4). - Examine heterogeneity across contexts and voters in when it comes to support for illiberal platforms. Here, we are especially interested in gender differences in support for illiberal platforms to test a hypothesis in the literature showing that female voters are less likely to support the radical right. - Contribute to a heat map of health of liberal democracy in Europe today that will highlight public support for liberal democracy (WP6).

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 6.1. Questionnaire development and design (lead LSE; partners: UVA, UNCL, CEPS, GESIS, SCPO; duration: months 1-21) This tasks concerns the development of the master questionnaire and its translations into all relevant languages in order to implement the survey in 27 EU member states. Some of the questions will be based on previous EES voter surveys, particularly from 2019, for which the complementary expertise by UNCL and UVA is imperative. Building on key questions from the long-term trends in attitudes (WP3) under the lead of UVA, an extensive battery of new survey questions will measure the attitudes towards and support for liberal democratic norms and values. Task 6.2. Conduct voter survey (lead GESIS; partners: LSE; duration: months 20-24) This tasks involves the implementation of the 2024 EP post-election study in 27 EU member states. It requires careful organisation, potential pre-tests, data collection, data checks and harmonisation of all 27 country samples into one single and cohesive dataset. Task 6.3. Integrate voter, party and contextual data and analyse party choice (lead LSE; partners: UNCL, UCLB, GESIS, SWPS; duration: months 21-42) In order to integrate data within the project and understand long-term trends, this task involves linking the individual survey data from task 6.2 with data on political indicators/instruments (D2.2) and economic conditions (D2.3) provided by GESIS as well as party positions towards liberal democratic norms that were held at the time of the 2024 EP election (D4.4) that are delivered by UCLB. SWPS’s and UNCL’s methodological expertise will be required to complete this task. Task 6.4. Contribute to the heat map about the health of liberal democracy across the EU (WP4 ) (lead: UCLB; partners: LSE, CEPS; duration: months X-X) This task involves the contribution of data on public support for liberal democracy to the ‘heat map’ developed in WP4 on party positions (task 4.4) under the lead of UCLB so that the data can be shared and exploited further by stakeholders of the project, for which CEPS will be responsible.

Deliverables (brief description and month of delivery) D6.1 Stakeholder workshop in Brussels (lead CEPS; Month of delivery: 18) A researchers-meet-policy-makers workshop (bringing together consortium members and Members of the European Parliament, high-ranking Commission officials, and other policy-makers) will be held prior to the data collection, in order to get input and feedback from stakeholders and practitioners. D6.1. Survey questionnaire (month of delivery: 19) The final survey questionnaire, in all relevant languages, will be used in the 2024 EP post-election study. It will be added to DEMCORE’s data repository that is managed by GESIS. D6.2. Report on the electoral market place for different visions of liberal democracy (month of delivery: 46) This report summarises the main findings from the analysis of the electoral market place for different visions of liberal democracy in the 2024 EP election and their implications for understanding current challenges to liberal democracy in Europe. D6.3. Part C of the heat map visualising challenges to liberal democracy: public support (month of delivery: 48) This part of the heat map on public support complements the heat map of party positions (D4.X). Combined, the heat map illustrates the variation and geographical and gender distribution of voter attitudes and party positions towards liberal democracy in a data visualisation that is facilitating for journalists and policy-makers to engage with. It will be published on DEMCORE’s website and distributed among the project’s stakeholders.

#### WP7 – Understanding preferences for “illiberal democracy” (Ben)

| Work package number | 7 | Lead beneficiary |  |  |  |  |  | SWPS |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Understanding preferences for “illiberal democracy” |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO | CEPS |
| Person months per participant: |  |  | X |  |  |  |  |  |  |
| Start month | 21 | End month |  |  |  |  |  | 48 |  |

Objectives The objectives of the Work Package are two-fold: - Examine the causal links between socio-demographic attributes and political attitudes on the one hand, and preferences for illiberal solutions on the other. - Analyse the extent to which extent, ‘pro-illiberal’ behaviours are persistent over time. To meet these objective, this Work Package will carry out a three-wave panel survey in six EU member states. The case selection will be guided by findings of WP2, WP3, WP4, WP5 and WP6 alongside current developments at the time of investigation. Building on insights into attitudes towards and correlates of liberal democratic norms and values generated by WP3 and WP6, this Work Package will focus on the causes of illiberal democratic preferences, using conjoint experiments with decision tasks concerning preferences for political regimes and outcomes (see Singh and Williams (2021) for a representative implementation). This approach will make it possible to estimate the relative causal impacts of multidimensional respondent attributes and policy preferences on preferences for illiberalism in more realistic and holistic scenarios (Hainmueller et al. 2014). Additionally, the panel design of this survey allows observing the stability of preferences for illiberal democracy over time.

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 7.1. Questionnaire development and design (lead SWPS; partners: LSE, UCLB, SCPO; duration: months 21-26) This tasks concerns the development of the master questionnaire and its translations into all relevant languages in order to implement the panel-survey across six countries. While building on the operationalisations identified (WP3) or used (WP6) in earlier Work Packages, a comprehensive battery of survey questions will be developed that tap citizen preferences (as opposed to attitudes) for liberal democratic norms and values in order to study causal mechanisms underpinning these preferences. Task 7.2. Conduct three-wave panel survey with embedded conjoint experiments (lead SWPS; partners: GESIS; duration: months 27-43) This tasks involves the implementation of the panel survey with embedded conjoint experiments over three waves in six EU member states. It requires careful organisation, potential pre-tests, data collection, data checks and harmonisation of all six country samples into one single and cohesive dataset. Task 7.3. Analyse the causes of illiberal democratic preferences (lead SWPS; partners: CEPS, LSE, UCLB, SCPO; duration: months 36-48) This tasks involves the analysis of the causes for varying preferences for liberal democratic norms and values. Thereby, it analyses the results from the conjoint experiments and assess the extent to which preferences for (il)liberal democracy change over time.

Deliverables (brief description and month of delivery) D7.1. Stakeholder workshop (lead: CEPS; month of delivery: 25) A researchers-meet-policy-makers workshop (bringing together consortium members and Members of the European Parliament, high-ranking Commission officials, and other policy-makers) will be held prior to the data collection, in order to get input and feedback from stakeholders and practitioners. D7.2. Survey questionnaire (lead: SWPS; month of delivery: 26) The final survey questionnaire will be used in the three-wave panel survey across six countries. It will be added to DEMCORE’s data repository that is managed by GESIS. D7.3. Ethical approval and pre-registration (lead: SWPS; month of delivery: 26) The hypotheses for the analyses will be pre-registered prior to data collection. D7.4. Open access dataset (month of delivery: 48) The dataset consisting of the three survey waves will be added to DEMCORE’s data repository that is managed by GESIS. D7.5. Report on the causes of illiberal democratic preferences (lead: SWPS; month of delivery: 48) The report will summarise the main comparative findings and their implications for understanding preferences for “illiberal democracy”.

#### WP8 - Ensuring liberal democratic resilience (lead: Sciences Po)

| Work package number | 8 | Lead beneficiary |  |  |  |  |  | SCPO |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Ensuring liberal democratic resilience |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO | CEPS |
| Person months per participant: |  |  |  |  |  |  |  |  |  |
| Start month |  | End month |  |  |  |  |  |  |  |

Objectives The objectives of this Work Package are twofold, namely to: - Develop and test the effectiveness of “inoculation” messages that are designed to strengthen support for liberal democracy in the face of illiberal appeals. - Investigate whether these inoculation messages are effective in real-world settings on social media. In doing so, we envision three phases of empirical research. In Phase 1, the WP leader will pilot test the effectiveness of traditional pre-emptive refutation messages that are designed to strengthen and reinforce pro-democracy attitudes and beliefs among those who are already supportive of liberal democracy. In Phase 2, we will investigate their effectiveness using a multi-country panel study with survey experiments. In Phase 3, we will turn our attention to investigating whether pro-democracy therapeutic messages can work in a real-world context of social media in collaboration with WP5. One way to reduce the spread of illiberal messages is to persuade would-be supporters of these messages to not spread them. For this, we plan to train Twitter bots to respond to illiberal tweets with a therapeutic inoculation message and then study the downstream effects of these messages.

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 8.1. Develop inoculation messages (lead SCPO; partners: SWPS, LSE, UCLB; duration: months XX-XX) This task serves to develop pre-emptive refutation messages that are designed to confront illiberal messages. Task 8.2. Pilot effectiveness of inoculation messages (lead SCPO; partners: none; duration: months XX-XX) This task serves to pilot test the effectiveness of inoculation messages in a small sample within the larger multi-country sample. Task 8.3. Questionnaire development and design (lead SCPO; partners: SWPS, LSE; duration: months XX-XX) This tasks involves the design of survey questionnaire and of the experiments using the inoculation messages selected through the pilot study. Task 8.4. Administer multi-country survey experiment (lead SCPO; partners: SWPS, LSE; duration: months XX-XX) This task involves the implementation of the multi-country panel study with survey experiments. Task 8.5 Analyse experimental data collected from the multi-country survey experiment. Task 8.5. Investigate the effectiveness of inoculation messages on Twitter (lead SCPO; partners: SWPS, LSE, UCLB; duration: months XX-XX) This task serves to investigate whether pro-democracy therapeutic messages can work in a real-world context on Twitter following the training of Twitter bots.

Deliverables (brief description and month of delivery) D8.1. Stakeholder workshop (lead: CEPS; month of delivery: 1 month before the study goes into the field) A researchers-meet-policy-makers workshop (bringing together consortium members and Members of the European Parliament, high-ranking Commission officials, and other policy-makers) will be held prior to the data collection, in order to get input and feedback from stakeholders and practitioners. D8.1. Report summarizing findings from pilot study on which inoculation messages were most effective. (June 2023) D8.2. Ethical approval and preregistration of survey experiments to be conducted in multi-country study (December 2023) D8.3. Codebook and data from multi-country survey (Spring 2024) D8.4. Report summarizing findings from multi-country survey experiments and providing recommendations for Twitter inoculation intervention (Fall 2024) D8.5. IRB approval of and preregistration of Twitter intervention (December 2024) D8.6. Report summarizing findings from Twitter Intervention (Fall 2025)

#### WP9 – Exploitation, Dissemination and Communication (lead: SDU)

| Work package number | 9 | Lead beneficiary |  |  |  |  |  | SDU |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Co-Creation, Exploitation, Dissemination and Communication |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| Short name of participant | UVA | UCLB | SWPS | UNCL | GESIS | SDU | LSE | SCPO | CEPS |
| Person months per participant: |  |  |  |  |  |  |  |  |  |
| Start month | 1 | End month |  |  |  |  |  | 48 |  |

Objectives WP9 is responsible for facilitating both co-creation and dissemination and for the effective communication and exploitation of DEMCORE’s results in order to maximise outreach and impact. Its specific objectives are: - Develop a comprehensive and detailed overview of relevant stakeholders at the EU, national and regional level alongside a rigorous Impact Plan for the dissemination and exploitation of results, including co-creation and communication. - Raise awareness and generate informed discussion on liberal democracy in Europe among its stakeholders, the media and European citizens in general. - Effectively monitor and consult the Advisory Boards on the implementation of DEMCORE’s Impact Plan and adapt the Impact Plan should the need arise. - Coordinate with consortium partners or implement DEMCORE’s major impact activities.

Description of work (where appropriate, broken down into tasks), lead partner and role of participants Task 9.1 Developing and regularly updating detailed Stakeholder Overview and Impact Plan (lead SDU; partners: none; duration: months 1-48) This tasks involves the development of a detailed plan for co-creation, dissemination and exploitation including communication activities’ based on our current plan provided in section 2.2.1. The detailed plan will be delivered in month 6 of the project and will be periodically updated in alignment with the project’s progress. Task 9.2 Building and maintaining a project website (lead UVA; partners: none; duration: months 1-48) This tasks involves building a project website at the beginning of the project and maintaining it throughout by adding new information on research outputs, events and other project activities by the Consortium members, including the ‘heatmaps’, blogposts and the feed from the Twitter account. Task 9.3 Creating and managing a Twitter account (lead UVA; partners: none; duration: months 1-48) This task involves building a project website at the beginning of the project and maintaining it throughout by adding new information on research outputs, events and other project activities by the Consortium members. Task 9.4 Developing education package (lead SDU; partners: ???; duration: months 5-12) This will provide an online educational package for journalists. It will have an interactive toolkit format in which journalists are presented with editorial challenges and choices. These will include options for focusing on different news topics, different news frames, and different sources. The choices made will be the starting point for providing feedback for different scenarios. The toolkit will include short reflexive contributions by key news journalists and news executives. The toolkit will be developed in 2023 and available ahead of the 2024 EP elections. Task 9.5 Developing series of knowledge clips (lead SDU; partners: ???; duration: months 5-24) This task involves the making of short knowledge clips about developments in democracy and journalism . One version will be made for journalists and one for journalism schools. Task 9.6 Organising three stakeholder events in Brussels (lead CEPS; partners: UNCL, LSE, SWPS, SCPO; duration: months XX-XX) Together with leaders of WP5, WP6, WP7 and WP8, DEMCORE plans each one stakeholder workshop at critical junctures of the project (see 2.2.1.1). Task 9.7 Organising two-day academic-stakeholder conference in Amsterdam (lead UVA; partners: all; duration: months 29-35) Task 9.8 Coordinating public debates series in EU member states (lead ???; partners: UVA, GESIS, UCLB, SCPO, SWPS; duration: months 1-48) This tasks involves the coordination of public debates, which are organised by Consortium members on location throughout the project. Task 9.9 Writing and distributing three flagship reports (lead CEPS; partners: all; duration: months 1-48) Together with leaders of all substantive WPs, DEMCORE will produce three flagship reports that cut across the whole project (see 2.2.1.1). Task 9.10 Coordinating specific report series (lead CEPS; partners: all; duration: months 1-48) This tasks involves the coordination of public reports, which are provided by responsible lead partners in the substantive WPs. Task 9.11 Coordinating ‘heatmap’ series (lead UVA?; partners: GESIS, UCLB, UNCL, LSE; duration: months 1-48) This tasks involves the coordination of the publication of the heatmaps, which are provided by WP4, WP5 and WP6.

Deliverables (brief description and month of delivery) D9.1. Project website (lead: UVA; month of delivery: 1) D9.2. Project Twitter account (lead: UVA; month of delivery: 1) D9.3. Detailed Impact Plan for co-creation, dissemination and exploitation including communication activities and stakeholders (lead: SDU; month of delivery: 5 or 6) D9.4. Inventory report existing educational packages (lead: SDU; month of delivery: 5) D9.5. Toolkit outline for initial user group feedback (lead: SDU; month of delivery: 6) D9.6. Toolkit completed and offered for online rollout (lead: SDU; month of delivery: 12) D9.7. Story development and user input for knowledge clips (lead: SDU; month of delivery: 15) D9.8. Knowledge clips for dissemination for specific audiences (lead: SDU; month of delivery: 24) D9.9. Three stakeholder workshops in Brussels (lead: CEPS; months of delivery: X, X, and XX) D9.10 Academic-stakeholder conference in Amsterdam (lead: UVA; month of delivery: 33) D9.11. Three flagship reports (lead: CEPS; months of delivery: X, X, and XX) Note that the specific reports are listed as deliverables in the respective Work Packages.

## Table 3.1c:	List of Deliverables

| Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date (in months) |
| --- | --- | --- | --- | --- | --- | --- |
| D1.1 |  | 1 |  |  |  |  |
| D1.2 |  | 1 |  |  |  |  |
| D1.3 |  | 1 |  |  |  |  |
| D1.4 |  | 1 |  |  |  |  |
| D1.5 |  | 1 |  |  |  |  |
| D1.6 |  | 1 |  |  |  |  |
| D1.7 |  | 1 |  |  |  |  |
| D1.8 |  | 1 |  |  |  |  |
| D1.9 |  | 1 |  |  |  |  |
| D1.10 |  | 1 |  |  |  |  |
| D2.1 |  | 2 |  |  |  |  |
| D2.2 |  | 2 |  |  |  |  |
| D2.3 |  | 2 |  |  |  |  |
| D2.4 |  | 2 |  |  |  |  |
| D3.1 |  | 3 |  |  |  |  |
| D3.2 |  | 3 |  |  |  |  |
| D4.1 |  | 4 |  |  |  |  |
| D4.2 |  | 4 |  |  |  |  |
| D4.3 |  | 4 |  |  |  |  |
| D4.4 |  | 4 |  |  |  |  |
| D4.5 |  | 4 |  |  |  |  |
| D5.1 |  | 5 |  |  |  |  |
| D5.2 |  | 5 |  |  |  |  |
| D5.3 |  | 5 |  |  |  |  |
| D5.4 |  | 5 |  |  |  |  |
| D5.5 |  | 5 |  |  |  |  |
| D6.1 |  | 6 |  |  |  |  |
| D6.2 |  | 6 |  |  |  |  |
| D6.3 |  | 6 |  |  |  |  |
| D7.1 |  | 7 |  |  |  |  |
| D7.2 |  | 7 |  |  |  |  |
| D7.3 |  | 7 |  |  |  |  |
| D7.4 |  | 7 |  |  |  |  |
| D7.5 |  | 7 |  |  |  |  |
| D8.1 |  | 8 |  |  |  |  |
| D8.2 |  | 8 |  |  |  |  |
| D8.3 |  | 8 |  |  |  |  |
| D8.4 |  | 8 |  |  |  |  |
| D8.5 |  | 8 |  |  |  |  |
| D8.6 |  | 8 |  |  |  |  |
| D9.1 |  | 9 |  |  |  |  |
| D9.2 |  | 9 |  |  |  |  |
| D9.3 |  | 9 |  |  |  |  |
| D9.4 |  | 9 |  |  |  |  |
| D9.5 |  | 9 |  |  |  |  |
| D9.6 |  | 9 |  |  |  |  |
| D9.7 |  | 9 |  |  |  |  |
| D9.8 |  | 9 |  |  |  |  |
| D9.9 |  | 9 |  |  |  |  |

## Table 3.1d: List of milestones

| Milestone number | Milestone name | Related work package(s) | Due date (in month) | Means of verification |
| --- | --- | --- | --- | --- |

## Table 3.1e: Critical risks for implementation

| Description of risk (indicate level of (i) likelihood, and (ii) severity: Low/Medium/High) | Work package(s) involved | Proposed risk-mitigation measures |
| --- | --- | --- |

## Table 3.1f: Summary of staff effort

|  | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | WP9 | Total Person-Months per Participant |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UVA | X |  |  |  |  |  |  |  |  |  |
| UCLB |  |  |  | X |  |  |  |  |  |  |
| SWPS |  |  |  |  |  |  | X |  |  |  |
| UNCL |  |  |  |  | X |  |  |  |  |  |
| GESIS |  | X |  |  |  |  |  |  |  |  |
| SDU |  |  |  |  |  |  |  |  | X |  |
| LSE |  |  |  |  |  | X |  |  |  |  |
| SCPO |  |  |  |  |  |  |  | X |  |  |
| CEPS |  |  |  |  |  |  |  |  |  |  |
| Total Person Months |  |  |  |  |  |  |  |  |  |  |

## Table 3.1g: ‘Subcontracting costs’ items

| Participant Number/Short Name |  |  |
| --- | --- | --- |
|  | Cost (€) | Description of tasks and justification |
| Subcontracting |  |  |

## Table 3.1h: ‘Purchase costs’ items (travel and subsistence, equipment and other goods, works and services)

| Participant Number/Short Name |  |  |
| --- | --- | --- |
|  | Cost (€) | Justification |
| Travel and subsistence |  |  |
| Equipment |  |  |
| Other goods, works and services |  |  |
| Remaining purchase costs (<15% of pers. Costs) |  |  |
| Total |  |  |

## Table 3.1i: ‘Other costs categories’ items (e.g. internally invoiced goods and services)

| Participant Number/Short Name |  |  |
| --- | --- | --- |
|  | Cost (€) | Justification |
| Internally invoiced goods and services |  |  |
| … |  |  |

## Table 3.1j: ‘In-kind contributions’ provided by third parties

| Participant Number/Short Name |  |  |  |
| --- | --- | --- | --- |
| Third party name | Category | Cost (€) | Justification |
|  | Select between Seconded personnel Travel and subsistence Equipment Other goods, works and services Internally invoiced goods and services |  |  |

## 3.2 Capacity of participants and consortium as a whole

The DEMCORE consortium has been formed to ensure that (a) that the membership brings together a critical mass of top class academic institutions involving the core disciplines of political science, political psychology, communication and data sciences; (b) that the participating scholars are leaders in their fields and could contribute the complementary knowledge and skills necessary to produce a comprehensive knowledge base and have a proven track-record of collaboration; (c) that the consortium expresses our commitment to gender representation and geographical diversity across Europe; and (d) that the consortium – including CEPS as a core partner– reflects the commitment to undertake policy relevant research and engage with relevant stakeholders.

In essence, the DEMCORE consortium brings together world-leading scholars across the social sciences with complementary of expertise in the areas of democracy, public opinion, political parties, institutions and media, a geographical spread across Northern, Southern and Central and Eastern Europe, strong female leadership and a track-record of engaging with policy-makers and practitioners.

### 3.2.1 Academic Excellence, Disciplinary Range and Methodological Range and Gender

DEMCORE brings together top scholars in the disciplines of political science, communication, political psychology and data science, based at some of the very best research universities in Europe and partnering with one of the leading think tanks in European Affairs – CEPS – as well as the largest German infrastructure institute for the social sciences, GESIS. The consortium consists of top grade and senior researchers and will provide unique career development opportunities for a pool of postdoctoral and doctoral researchers who will benefit from DEMCORE and the mentoring experience of the senior scholars involved. The participating scholars are leaders in their fields who have published in top journals and quality presses and who regularly present papers at major international and national conferences. Importantly, the consortium spans both the academic and policy relevant knowledge necessary for the research outlined in this proposal and has the theoretical, analytical and methodological capacity needed to deliver high quality, policy relevant research output. One of the partners, CEPS, is among the top think tanks in Europe, offering an extensive network of partner institutes throughout the world and the ability to analyse policy-relevant questions and disseminate research findings with relevance to European affairs. In addition, the consortium members have extensive networks and established relationships with many of the actors who are directly concerned with the subject matter of this proposal: European institutions, national governments, NGOs and wider civil society groups. The advisory board also combines academic expertise and linkages with the policy world and will strengthen the consortium’s capacity to link innovative research with policy-relevant engagement with key actors.

The consortium brings together experts in political science, communication science, political psychology and data science with particular expertise in challenges to liberal democracy. From the perspective of political science, Wouter van der Brug (UVA) is a world-leading scholar of the radical right parties, voting behaviour and challenges to liberal democracy. Catherine De Vries (UCLB) is an internationally renowned expert of public opinion and parties, and has recently written an award-winning book on Euroscepticism. Another acclaimed scholar is Sara Hobolt (LSE), who has also published high impact research on voters and parties, as well as on Brexit and referendums more generally. Based at SWPS in Poland, Ben Stanley provides essential scholarship on democratic backsliding and populism in Central and Eastern Europe. From the communication perspective, Katjana Gattermann (UVA) is a rising star in the field of political communication and journalism, political behaviour and public opinion within the European Union. Claes De Vreese (SDU) is a world-leading scholar of political communication, focusing on AI, media and democracy. He is the scientific director of the Digital Democracy Center and recently served as President of the International Communication Association. Further expertise in the area of social media is brought to the project by Sebastian Popa (UNCL) who specializes in using state-of-the art methods to analyse the of social media in electoral campaigns. From the perspective of political psychology, Kevin Arceneaux (SCPO) provides world-leading expertise in the study of attitude formation, the role of human biology, and experimental methodology. Finally, the consortium has excellent expertise and infrastructure in the data management and data sciences with Alexia Katsanidou, who is the scientific director of the GESIS Department Survey Data Curation and an expert in social science data infrastructures, management and methods. Methodologically, the team brings together expertise in survey methods and questionnaire design (van der Brug, Hobolt, De Vries, Katsanidou), quantitative analysis of texts and (social) media (Popa, Gattermann, De Vries, Hobolt, De Vreese), experimental methods (Arceneaux, Stanley, Hobolt, Gattermann), focus groups (De Vries) and data science and data infrastructures (De Vreese, Katsanidou).

The consortium is coordinated by Katjana Gattermann (UVA), who has considerable research management experience as Director of the former Erasmus Academic Network on Parliamentary Democracy in Europe (PADEMIA), which was funded by European Union Lifelong Learning Programme and the EACEA and brought together 56 academic institutions from 31 European countries between 2013 and 2016. She is also the Co-Founder of the ECPR Standing Group ‘Political Communication’ and has served as the first Convenor, and was Principal Investigator of a recently concluded NWO-funded project. She is supported by a strong team of scholars and administrative support at the University of Amsterdam [MORE]. This consortium thus puts emphasis on strong female leadership and gender representation, with four substantive Work Packages led by women (Gattermann, De Vries, Hobolt and Katsanidou). In the recruitment of researchers for DEMCORE, we will ensure that the calls for posts are designed to attract female candidates, that interview boards are balanced and that there is mentoring of early career scholars, both female and male, in the consortium. All activities of the consortium, conferences, workshops and stakeholder forums will be designed to ensure balanced gender representation.

Our Advisory Board also has outstanding female members, who play a leading role in the policy debate on democracy Europe. It includes Heather Grabbe, director of the Open Society European Policy Institute, who works to ensure that open society values are at the heart of EU policies and actions, both inside and outside its borders, and will provide invaluable advice to DEMCORE on how the findings on liberal democracy can inform EU policies and action. Another member of the Board is Isabell Hoffmann of the Bertelsmann Foundation, who is founder of eupinions, an independent platform for European public opinion. Hoffmann also brings expertise from the media as a former political editor at the German weekly newspaper Die Zeit. A third member of the Board is R. Daniel Kelemen, professor and Jean Monnet Chair at Rutgers University, US, and one of the leading scholars of democratic backsliding within the EU. Erik Jones, Director of the Robert Schuman Centre for Advanced Studies at the European University Institute, is another distinguished member of the advisory board who brings unparalleled expertise on EU affairs and engagements with EU institutions. The Advisory Board was thus chosen to bring both academic expertise as well as policy engagement to the project, and members will be invited to contribute to the project with advice at insights from the very inception.

### 3.2.2 Complementarity, Cross-Institutional Collaboration

The consortium is well-placed to deliver its ambitious objectives, not only due to the complementarity and expertise of the network, but also because the researchers involved have a track-record of working effectively together in other collaborative projects and infrastructures. The researchers in this project have worked together on ambitious collaborative infrastructure and research projects, such as the European Elections Study (van der Brug, Gattermann, Hobolt, Popa, De Vreese), the European Voter (Katsanidou, van der Brug), eupinions (De Vries, Hoffmann, Hobolt), Monitoring Electoral Democracy MEDem (van der Brug, Hobolt, Katsanidou, Popa, De Vreese) and the Comparative Study of Electoral Systems CSES (van der Brug, De Vries, Hobolt). These successful collaborative efforts have shown that the researchers involved in the consortium complement each other and can  work effectively together within and across the Work Packages. Every node of the consortium has at least one person who has worked intensively with a colleague in another institution. This greatly reduces the transaction costs, facilitates working together to deliver the project as conceived and will make mutual support across the consortium easier to achieve. It also illustrates the wealth of experience in the consortium in terms of data collection, questionnaire design and data analysis in a cross-national setting. The scholars working on deepening and expanding data sets on Work Packages 3 and 4 are building on already existing high quality data sets, thus maximising the potential for DEMCORE to produce a unique resource on liberal democracy of substantial added value. In addition, the consortium will jointly collect original data, both cross-national survey data (Work Package 6) and micro-level experimental data (Work Packages 7 and 8) alongside social media data (Work Package 5).

Given the experience of the researchers involved, and the outstanding expertise of GESIS on data infrastructures, the consortium is very well placed to undertake and deliver on the integration, development and analysis.

### 3.2.3 Engagement and Impact

The DEMCORE consortium is well-placed to deliver the evidence-based policy recommendation and wider engagement that that is a core part of its objectives. All of the researchers involved in the project have considerable experience in engagement with stakeholders, policy-makers and EU institutions. They also have access to important networks that allow them to engage with policy-makers and the wider public, For example, De Vries frequently provides commentary in newspaper outlets, including as columnist for the Dutch Het Financieele Dagblad, and she serves as the scientific advisor for eupinions funded by the Bertelsmann Foundation and a member of European Integration Committee of the Dutch Advisory Council on Foreign Affairs. Another example is De Vreese who is director the Digital Democracy Centre at SDU, and who will work closely on impact in collaboration with the Media Research and Innovation Centre (MFI Centre) at SDU, which has extensive experience in making industry oriented materials. Likewise, the Amsterdam Centre for European Studies (ACES) at UVA is an interdisciplinary centre of excellence on contemporary Europe, the European Union, and its member states. Its objectives include increasing the wider visibility and policy impact of European research at the UVA while enhancing the quality of the public debate on contemporary Europe, by engaging a variety of audiences within and beyond the Netherlands. Moreover, CEPS has access to a wide range of networks and institutional settings, comprising research institutes and non-for profit organisations from all over Europe and beyond, that will enable DEMCORE to extend its outreach. The consortium’s strong networks in Brussels as well as in European capitals are an asset and will assure that the research findings and recommendations are disseminated effectively. The consortium will also lead to the establishment of new networks by integrating early career scholars and researchers into a European-wide community of scholars working on aspects of liberal democracy, populism, public opinion and party competition.

If space: highlight commitment to Open Access (Vin as Editor of JEPS; GESIS providing the data infrastructure for open access; other members’ commitment to open science, e.g., through pre-registration of research)

Add something about the illiberal processes in Poland and control of universities. As Poland is part of the consortium, this might be an issue if they go the same way as Hungary.

People leaving the consortium.

## References

Aalberg T, Reinemann C, Esser F, Strömbäck J and De Vreese CH (eds) (2016) Populist Political Communication in Europe. New York: Routledge.

Almond GA and Verba S (1963) The Civic Culture: Political Attitudes and Democracy in Five Nations. Princeton: Princeton University Press.

American Political Science Association (2012) A guide to professional ethics in political science. Available at: https://www.apsanet.org/portals/54/Files/Publications/APSAEthicsGuide2012.pdf

Arceneaux K and Vander Wielen R (2017) Taming Intuition: How Reflection Promotes Minimizes Partisan Reasoning and Promotes Democratic Accountability. Cambridge: Cambridge University Press.

Arceneaux K, Bakker BN, Hobolt SB and De Vries CE (2020) Is COVID-19 a Threat to Liberal Democracy? Preprint from PsyArXiv, DOI: 10.31234/osf.io/8e4pa

Armingeon K and Guthmann K (2014) Democracy in crisis? The declining support for national democracy in European countries, 2007–2011. European Journal of Political Research 53(3): 423-442.

Barberá P, Jost JT, Nagler J, Tucker JA and Bonneau R (2015) Tweeting From Left to Right: Is Online Political Communication More Than an Echo Chamber? Psychological Science 26(10): 1531-1542.

Barberá P, Vaccari C and Valeriani A (2017) Social Media, Personalisation of News Reporting, and Media Systems’ Polarisation in Europe. In: Barisione M and  Michailidou A (eds.) Social Media and European Politics: Rethinking Power and Legitimacy in the Digital Era. London: Palgrave Macmillan, pp. 25-52.

Barberá P and Zeitzoff T (2018) The New Public Address System: Why Do World Leaders Adopt Social Media? International Studies Quarterly 62(1): 121-130.

Bartha A, Boda Z and Szikra D (2020) When Populist Leaders Govern: Conceptualising Populism in Policy Making. Politics and Governance 8(3): 71-81.

Bermeo N (2016) On Democratic Backsliding. Journal of Democracy 27(1): 5-19.

Bolleyer N and Salát O (2021) Parliaments in times of crisis: COVID-19, populism and executive dominance. West European Politics 44(5-6): 1103-1128.

Braun D, Popa SA and Schmitt H (2019) Responding to the crisis: Eurosceptic parties of the left and right and their changing position towards the European Union. European Journal of Political Research 58(3): 797-819.

Broockman D and Kalla J (2016) Durably reducing transphobia: A field experiment on door-to-door canvassing. Science 352(6282): 220-224.

Buštíková L and Guasti P (2017) The Illiberal Turn or Swerve in Central Europe? Politics and Governance 5(4): 166-176.

Buštíková L and Baboš P (2020) Best in Covid: Populists in the Time of Pandemic. Politics and Governance 8(4): 496-508.

Buzogány A (2017) Illiberal democracy in Hungary: authoritarian diffusion or domestic causation? Democratization 24(7): 1307-1325.

Castillo-Ortiz P (2019) The Illiberal Abuse of Constitutional Courts in Europe. European Constitutional Law Review 15(1): 48-72.

Cianetti L, Dawson L and Hanley S (2018) Rethinking “democratic backsliding” in Central and Eastern Europe – looking beyond Hungary and Poland. East European Politics 34(3): 243-256,

Coman R and Volintiru C (2021) Anti-liberal ideas and institutional change in Central and Eastern Europe. European Politics and Society, Epub ahead of print 26 July 2021 DOI: 10.1080/23745118.2021.1956236

Compton J and Ivanov B (2013) Vaccinating Voters: Surveying Political Campaign Inoculation Scholarship. Annals of the International Communication Association 37(1): 251-283.

Compton J, Linden S, Cook J and Basol M (2021) Inoculation Theory in the Post‐truth Era: Extant Findings and New Frontiers for Contested Science, Misinformation, and Conspiracy Theories. Social and Personality Psychology Compass 15(6). DOI: 10.1111/spc3.12602.

Coppedge M, Lindberg S, Skaaning S-E and Teorell J (2016) Measuring high level democratic principles using the V-Dem data. International Political Science Review 37(5): 580-593.

Cordero G and Simón P (2016) Economic Crisis and Support for Democracy in Europe. West European Politics 39(2): 305-325.

Curiei CP (2020) Trend towards extreme right-wing populism on Twitter. An analysis of the influence on leaders, media and users. Communication & Society 33(2): 175-192.

Dahl RA (1956) A Preface to Democratic Theory: How Does Popular Sovereignty Function in America? Chicago, IL: University of Chicago Press.

De Vries CE (2018) Euroscepticism and the Future of European Integration. Oxford: Oxford University Press.

De Vries CE and Edwards EE (2009) Taking Europe to its Extremes: Extremist Parties and Public Euroscepticism. Party Politics 15(1): 5-28.

De Vries CE and Hobolt SB (2020) Political Entrepreneurs: The Rise of Challenger Parties in Europe. Princeton: Princeton University Press.

De Wilde P and Trenz H-J (2012) Denouncing European integration: Euroscepticism as polity contestation. European Journal of Social Theory 15(4): 537-554.

Dotti Sani GM and Magistro B (2016) Increasingly Unequal? The Economic Crisis, Social Inequalities and Trust in the European Parliament in 20 European Countries. European Journal of Political Research 55(2): 246-264.

Drinóczi T and Bień-Kacała A (2020) COVID-19 in Hungary and Poland: extraordinary situation and illiberal constitutionalism. The Theory and Practice of Legislation 8(1-2): 171-192.

Engler S, Brunner P, Loviat R et al. (2021) Democracy in times of the pandemic: explaining the variation of COVID-19 policies across European democracies. West European Politics 44(5-6): 1077-1102.

Ernst N, Engesser S, Büchel F, Blassnig S and Esser F (2017) Extreme Parties and Populism: An Analysis of Facebook and Twitter across Six Countries. Information, Communication & Society 20(9): 1347-1364.

European Commission (2021) Eurobarometer 93.1 (2020). Kantar Public, Brussels [producer]. GESIS Data Archive, Cologne. ZA7649 Data file Version 1.2.0, https://doi.org/10.4232/1.13746

Fazekas Z, Popa SA, Schmitt H, Barberá P and Theocharis Y(2021) Elite-Public Interaction on Twitter: EU Issue Expansion in the Campaign. European Journal of Political Research 60(2): 376-396.

Ferrin M and Kriesi H (eds) (2016) How Europeans View and Evaluate Democracy. Oxford: Oxford University Press.

Foa RS and Mounk Y (2016) The Danger of Deconsolidation: The Democratic Disconnect. Journal of Democracy 27(3): 5-17.

Freedom House (2020) Freedom in the World 2020: A leaderless struggle for democracy. Washington.

Gabel M and Hix S (2002) Defining the EU Political Space: An Empirical Study of the European Elections Manifestos, 1979-1999. Comparative Political Studies 35(8): 934-964.

Gattermann K, De Vreese CH and Van der Brug W (2021) Introduction: No longer second-order? Explaining the European Parliament elections of 2019. Politics 41(4): 423-432.

Goldberg G (2010) Rethinking the Public/Virtual Sphere: The Problem with Participation. New Media & Society 13(5): 739-754.

Goldberg AC, Van Elsas EJ and De Vreese CH (2021) One union, different futures? Public preferences for the EU’s future and their explanations in 10 EU countries. European Union Politics. Epub ahead of print 3 August 2021. DOI: 10.1177/14651165211034150

Graham MH and Svolik MW (2020) Democracy in America? Partisanship, Polarization, and the Robustness of Support for Democracy in the United States. American Political Science Review 114(2): 392-409.

Grant WJ, Moon B and Busby Grant J (2010) Digital Dialogue? Australian Politicians’ Use of the Social Network Tool Twitter. Australian Journal of Political Science 45(4): 579-604.

Groenendyk E and Krupnikov Y (2021) What Motivates Reasoning? A Theory of Goal‐Dependent Political Evaluation. American Journal of Political Science 65(1): 180-196.

Grzymala-Busse A (2019) How Populists Rule: The Consequences for Democratic Governance. Polity 51(4): 707-717.

Guasti P (2020) The Impact of the COVID-19 Pandemic in Central and Eastern Europe: The Rise of Autocracy and Democratic Resilience. Democratic Theory 7(2): 47-60.

Guess AM (2021) (Almost) Everything in Moderation: New Evidence on Americans’ Online Media Diets. American Journal of Political Science. Epub ahead of print 19 February 2021. DOI:10.1111/ajps.12589.

Hainmueller J, Hopkins DJ and Yamamoto T (2014) Causal Inference in Conjoint Analysis: Understanding Multidimensional Choices via Stated Preference Experiments. Political Analysis 22(1): 1-30.

Hakhverdian A and Mayne Q (2012) Institutional Trust, Education, and Corruption: A Micro-Macro Interactive Approach. The Journal of Politics 74(3): 739-750.

Halikiopoulou D, Nanou K and Vasilopoulou S (2012) The paradox of nationalism: The common denominator of radical right and radical left Euroscepticism. European Journal of Political Research 51(4): 504-539.

Halmai G (2019) Populism, authoritarianism and constitutionalism. German Law Journal 20(3): 296-313.

Harder RA, Sevenans J and Van Aelst P (2017) Intermedia Agenda Setting in the Social Media Age: How Traditional Players Dominate the News Agenda in Election Times. The International Journal of Press/Politics 22(3): 275-293.

Herman LE, Hoerner J and Lacey J (2021) Why does the European Right accommodate backsliding states? An analysis of 24 European People’s Party votes (2011–2019). European Political Science Review 13(2): 169-187.

Harteveld E, Van Der Brug W, Dahlberg S and Kokkonen A (2015) The gender gap in populist radical-right voting: examining the demand side in Western and Eastern Europe. Patterns of Prejudice 49(1-2): 103-134.

Harteveld E, Dahlberg S, Kokkonen A and Van Der Brug W (2019a) Gender differences in vote choice: Social cues and social harmony as heuristics. British Journal of Political Science 49(3): 1141-1161.

Harteveld E, Dahlberg S, Kokkonen A and Van Der Brug W (2019b). Social stigma and support for the populist radical right: an experimental study. Scandinavian Political Studies 42(3-4): 296-307.

Hobolt SB (2012) Citizen Satisfaction with Democracy in the European Union. Journal of Common Market Studies 50(S1): 88-105.

Hobolt SB and De Vries CE (2016) Turning against the Union? The impact of the crisis on the Eurosceptic vote in the 2014 European Parliament elections. Electoral Studies 44: 504-514.

Høyland B, Hobolt SB and Hix S (2019) Career Ambitions and Legislative Participation: The Moderating Effect of Electoral Institutions. British Journal of Political Science 49(2): 491-512.

Hooghe L, Marks G and Wilson CJ (2002) Does left/right structure party positions on European integration? Comparative Political Studies 35(8): 965-989.

Inglehart R (2003) How Solid is Mass Support for Democracy – And How Can We Measure It? PS: Political Science & Politics 36(1): 51-57.

Ivanov B, Parker KA and Dillingham L (2020) Inoculation Theory as a Strategic Tool. In: O’Hair HD and O’Hair MJ (eds) The Handbook of Applied Communication Research (Vol. 1). Hoboken: Wiley, pp. 11-28.

Jungar AC and Jupskås AR (2014) Populist Radical Right Parties in the Nordic Region: A New and Distinct Party Family? Scandinavian Political Studies 37(3): 215-238.

Jungherr A, Schroeder R and Stier S (2019) Digital Media and the Surge of Political Outsiders: Explaining the Success of Political Challengers in the United States, Germany, and China. Social Media & Society 5(3): 1-12.

Jurado I, Léon S and Walter S (2018) European Preferences for Brexit: Evidence from a conjoint experiment in Germany and Spain. Paper presented at the 2018 APSA Conference in Boston.

Jolley D and Douglas KM (2017) Prevention Is Better than Cure: Addressing Anti-Vaccine Conspiracy Theories. Journal of Applied Social Psychology 47(8): 459-469.

Karp JA, Banducci SA and Bowler S (2003) To know it is to love it? Satisfaction with democracy in the European Union. Comparative Political Studies 36(3): 271-292.

Kelemen RD (2017) Europe’s Other Democratic Deficit: National Authoritarianism in Europe’s Democratic Union. Government and Opposition 52(2): 211-238.

Kelemen RD (2020) The European Union’s authoritarian equilibrium. Journal of European Public Policy 27(3): 481-499.

Kittilson MC (2016) Gender and Political Behavior. Oxford Research Encyclopedia of Politics. DOI: 10.1093/acrefore/9780190228637.013.71

Kittilson MC and Schwindt-Bayer LA (2012) The Gendered Effects of Electoral Institutions: Political Engagement and Participation. Oxford: Oxford University Press.

Klein O, Hardwicke TE, Aust F et al. (2018) A practical guide for transparency in psychological science. Collabra: Psychology 4(1): 20.

Kriesi H and Morlino L (2016) Conclusion: What Have We Learnt, and Where Do We Go from Here? In: Ferrin M and Kriesi H (eds) How Europeans View and Evaluate Democracy. Oxford: Oxford University Press, pp. 307-325.

Kruikemeier S, Gattermann K and Vliegenthart R (2018) Understanding the dynamics of politicians’ visibility in traditional and social media. The Information Society 34(4): 1-14.

Larsson AO 2(015) The EU Parliament on Twitter - Assessing the Permanent Online Practices of Parliamentarians. Journal of Information Technology & Politics 12(2): 149-166.

Levitsky S and Way LA (2020) The New Competitive Authoritarianism . Journal of Democracy 31(1): 51-65.

Levitsky S and Ziblatt D (2018) How Democracies Die: What History Reveals about our Future. New York: Crown

Linde J and Ekman J (2003) Satisfaction with democracy: A note on a frequently used indicator in comparative politics. European Journal of Political Research 42(3): 391-408.

Maertens R, Anseel F and Van der Linden S (2020) Combatting Climate Change Misinformation: Evidence for Longevity of Inoculation and Consensus Messaging Effects. Journal of Environmental Psychology 70(August): 101455.

Mauk M (2020) Rebuilding Trust in Broken Systems? Populist Party Success and Citizens’ Trust in Democratic Institutions. Politics and Governance 8(3): 45-58.

McGuire WJ (1964) Some contemporary approaches. In: Berkowitz L (ed) Advances in experimental social psychology (Vol. 1). New York and London: Academic Press, pp. 191-229.

Mechkova V, Lührmann A and Lindberg SI (2017) How much democratic backsliding? Journal of Democracy 28(4): 162-169.

Meijers M and Rauh C (2016) Has Eurosceptic Mobilization Become More Contagious? Comparing the 2009 and 2014 EP Election Campaigns in The Netherlands and France. Politics and Governance 4(1): 83-103.

Meijers MJ and Van der Veer H (2019) MEP Responses to Democratic Backsliding in Hungary and Poland: An Analysis of Agenda-Setting and Voting Behaviour. Journal of Common Market Studies 57(4): 838-856.

Mény Y (2003) De La Démocratie en Europe: Old Concepts and New Challenges. Journal of Common Market Studies 41(1): 1-13.

Michailidou A (2015) The role of the public in shaping EU contestation: Euroscepticism and online news media. International Political Science Review 36(3): 324-336.

Miguel E, Camerer C, Casey K et al. (2014) Promoting Transparency in Social Science Research. Science 343(6166): 30-31.

Mudde C (2004) The Populist Zeitgeist. Government and Opposition 39(4): 541-563.

Mudde C (2016) Europe’s Populist Surge: A Long Time in the Making. Foreign Affairs 95(6): 25-30.

Mudde C and Kaltwasser CR (eds) (2012) Populism in Europe and the Americas: Threat or Corrective for Democracy? New York: Cambridge University Press.

Müller JW (2016). What Is Populism? Philadelphia: University of Pennsylvania Press.

Munger K (2021) Don’t @ Me: Experimentally Reducing Partisan Incivility on Twitter. Journal of Experimental Political Science 8(2): 102-116.

Munger K (2017) Tweetment Effects on the Tweeted: Experimentally Reducing Racist Harassment. Political Behavior 39(3): 629-649.

Newman N, Fletcher R, Kalogeropoulos A, Levy DAL and Kleis Nielsen R (2017) Reuters Institute Digital News Report 2017. Reuters Institute, University of Oxford. Available at: https://bit.ly/38FV8tB

Norman L (2021) To Democratize or to Protect? How the Response to Anti‐System Parties Reshapes the EU’s Transnational Party System. Journal of Common Market Studies 59(3): 721-737.

Norris P (2011) Democratic Deficit: Critical Citizens Revisited. New York: Cambridge University Press.

Norris P (2017) Is Western Democracy Backsliding? Diagnosing the Risks. Journal of Democracy Web Exchange, https://bit.ly/3DOcsLl

Norris P and Inglehart R (2019) Cultural Backlash: Trump, Brexit, and the Rise of Authoritarian Populism. New York: Cambridge University Press.

Nosek BA, Alter G, Banks GC et al. (2015) Promoting an open research culture. Science 348(6242):1422-1425.

Osnabrügge M, Hobolt SB and Rodon T (2021) Playing to the Gallery: Emotive Rhetoric in Parliaments. American Political Science Review 115(3): 885-899.

Parmelee JH and Bickes SL (2012) Politics and the Twitter Revolution: How Tweets Influence the Relationship between Political Leaders and the Public. Plymouth: Lexington Books.

Pfau M and Burgoon M (1988) Inoculation in Political Campaign Communication. Human Communication Research 15(1): 91-111.

Pfau M, Holbert RL, Zubric SJ et al. (2000) Role and Influence of Communication Modality in the Process of Resistance to Persuasion. Media Psychology 2(1): 1-33.

Pirro ALP and Stanley B (2021) Forging, Bending, and Breaking: Enacting the “Illiberal Playbook” in Hungary and Poland. Perspectives on Politics. Epub ahead of print 9 July 2021. DOI:10.1017/S1537592721001924

Plattner MF (2017) Liberal Democracy’s Fading Allure. Journal of Democracy 28(4): 5-14.

Popa SA, Fazekas Z ,Braun D and Leidecker-Sandmann MM (2019) Informing the Public: How Party Communication Builds Opportunity Structures. Political Communication 37(3): 329-349.

Reif K and Schmitt H (1980) Nine second order national elections: A conceptual framework for the analysis of European election results. European Journal of Political Research 8(1): 3-44.

Rooduijn M, De Lange SL and Van der Brug W (2014) A populist Zeitgeist? Programmatic contagion by populist parties in Western Europe. Party Politics 20(4): 563-575.

Rovny J and Edwards EE (2012) Struggle over Dimensionality Party Competition in Western and Eastern Europe. East European Politics and Societies 26(1): 56-74.

Sartori G (1995) How far can free government travel? Journal of Democracy 6(3): 101-111.

Schedler A and Sarsfield R (2007) Democrats with adjectives: Linking direct and indirect measures of democratic support. European Journal of Political Research 46(5): 637-659.

Schlipphak B and Treib O (2017) Playing the blame game on Brussels: the domestic political effects of EU interventions against democratic backsliding. Journal of European Public Policy 24(3): 352-365.

Sedelmeier U (2014) Anchoring Democracy from Above? The European Union  and Democratic Backsliding in Hungary and Romania after Accession. Journal of Common Market Studies 52(1): 105-121.

Singh SP and Williams NS (2021) What type of democracy do Chileans want? Research & Politics 8(3): 1-8.

Stanley B (2019) A New Populist Divide? Correspondences of Supply and Demand in the 2015 Polish Parliamentary Elections. East European Politics and Societies and Cultures 33(1): 17-43.

Stanovich KE and West RF (2000) Individual Differences in Reasoning: Implications for the Rationality Debate. Behavioral and Brain Sciences 23(January): 645-726.

Stier S, Posch L, Bleier A and Strohmaier M (2017) When Populists Become Popular: Comparing Facebook Use by the Right-Wing Movement Pegida and German Political Parties. Information, Communication & Society 20(9): 1365-1388.

Taggart P (1998) A touchstone of dissent: Euroscepticism in contemporary Western European party systems. European Journal of Political Research 33: 363-388.

Tappin BM, Pennycook G and Rand DG (2020) Rethinking the Link between Cognitive Sophistication and Politically Motivated Reasoning. Journal of Experimental Psychology: General. DOI: 10.1037/xge0000974.

Teixeira CP, Tsatsanis E and Belchior AM (2014) Support for Democracy in Times of Crisis: Diffuse and Specific Regime Support in Portugal and Greece. South European Society and Politics 19(4) 501-518.

Theocharis Y, Barberá P, Fazekas Z, Popa SA and Parnet O (2016) A Bad Workman Blames His Tweets: The Consequences of Citizens’ Uncivil Twitter Use When Interacting With Party Candidates. Journal of Communication 66(6): 1007-1031.

Theocharis Y, Barberá P, Fazekas Z and Popa SA (2020) The Dynamics of Political Incivility On Twitter. Sage Open 10(20): 1-15.

Tucker JA, Theocharis Y, Roberts ME and Barberá P (2017) From Liberation to Turmoil: Social Media And Democracy. Journal of Democracy 28(4): 46-59.

Tucker, JA, Guess A, Barberá P et al. (2018) Social Media, Political Polarization, and Political Disinformation: A Review of the Scientific Literature (19 March 2018). Available at SSRN: https://ssrn.com/abstract=3144139

Vachudova MA (2021) Populism, Democracy, and Party System Change in Europe. Annual Review of Political Science 24: 471-498.

Van Atteveldt W, Strycharz J, Trilling D and Welbers K (2019) Toward Open Computational Communication Science: A Practical Road Map for Reusable Data and Code. International Journal of Communication 13: 3935-3954.

Van der Brug W and De Vreese CH (eds) (2016) (Un)intended Consequences of European Parliamentary Elections. Oxford: Oxford University Press.

Van der Brug W, Gattermann K and De Vreese CH (2016) Introduction: How different were the European elections of 2014? Politics and Governance 4(1): 1-8.

Van der Brug W, Popa SA, Hobolt SB and Schmitt H (2021a) Illiberal democratic attitudes and support for the EU. Politics. Epub ahead of print 15 February 2021. DOI:10.1177/0263395720975970.

Van der Brug W, Popa SA, Hobolt SB and Schmitt H (2021b, in press) Incumbency, populism and support for liberal democratic norms. Journal of Democracy 32(4)

Van der Brug W, Gattermann K and De Vreese CH (2021c, in press). Electoral responses to the increased contestation over European integration. The European Elections of 2019 and beyond. European Union Politics, DOI: 10.1177/14651165211036263

Van de Wardt M, De Vries CE and Hobolt SB (2014) Exploiting the cracks: Wedge issues in multiparty competition. The Journal of Politics 76(4): 986-999.

Van Hauwaert SM and Van Kessel S (2018) Beyond protest and discontent: A cross-national analysis of the effect of populist attitudes and issue positions on populist party support. European Journal of Political Research 57(1): 68-92.

Van Kessel S (2015) Populist Parties in Europe: Agents of Discontent? Basingstoke: Palgrave MacMillan.

Van Spanje J and De Vreese CH (2011) So what’s wrong with the EU? Motivations underlying the Eurosceptic vote in the 2009 European elections. European Union Politics 12(3): 405-429.

Westwood SJ, Iyengar S, Walgrave S et al. (2018) The Tie That Divides: Cross-National Evidence of the Primacy of Partyism: The Tie That Divides. European Journal of Political Research 57(2): 333-54.

Wilkinson MD, Dumontier M, Aalbersberg IJ et al. (2016) The FAIR Guiding Principles for scientific data management and stewardship. Scientific data 3(1): 1-9.

Wirz DS (2018) Persuasion Through Emotion? An Experimental Test of the Emotion-Eliciting Nature of Populist Communication. International Journal of Communication 12: 1114-1138.

Wodak R, KhosraviNik M and Mral B (eds) (2013) Right-Wing Populism in Europe: Politics and Discourse. London and New York: Bloomsbury.

Wolkenstein F (2019) Populism, liberal democracy and the ethics of peoplehood. European Journal of Political Theory 18(3): 330-348.

Wuttke A (n.d.) JOP’s new pre-registration policy. Blogpost available at: https://www.alexander-wuttke.de/jops-new-pre-registration-policy/

Zilinksy J (2019) Democratic deconsolidation revisited: Young Europeans are not dissatisfied with democracy. Research & Politics 6(1): 1-8.